## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of existing Ground Water Based Piped Water Supply Scheme for Falakata | SM/06268 | Augmentation | Quotation for new Service Connection at Falakata Z-III,TW-II ,Application No- 4002584842 |  |  | VCH/001116/2020-2021 | 184/20-21 | 08/12/2020 |  | WBSEDCL | 1.35 | 0 | 0 | 0
2 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of existing Ground Water Based Piped Water Supply Scheme for Falakata | SM/06268 | Augmentation | Quotation for new Service Connection at Falakata ,TW-III ,Application No- 4002584851 |  |  | VCH/001117/2020-2021 | 184/20-21 | 08/12/2020 |  | WBSEDCL | 1.35 | 0 | 0 | 0
3 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of existing Ground Water Based Piped Water Supply Scheme for Falakata | SM/06268 | Augmentation | Quotation for new Service Connection at Falakata Z-I,TW-I ,Application No- 4002584841 |  |  | VCH/001112/2020-2021 | 184/20-21 | 08/12/2020 |  | WBSEDCL | 1.35 | 0 | 0 | 0
4 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of existing Ground Water Based Piped Water Supply Scheme for Falakata | SM/06268 | Augmentation | Quotation for new Service Connection at Falakata Z-I,TW-II ,Application No- 4002584784 |  |  | VCH/001113/2020-2021 | 184/20-21 | 08/12/2020 |  | WBSEDCL | 1.35 | 0 | 0 | 0
5 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of existing Ground Water Based Piped Water Supply Scheme for Falakata | SM/06268 | Augmentation | Quotation for new Service Connection at Falakata Z-II,TW-I ,Application No- 4002584845 |  |  | VCH/001114/2020-2021 | 184/20-21 | 08/12/2020 |  | WBSEDCL | 1.35 | 0 | 0 | 0
6 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of existing Ground Water Based Piped Water Supply Scheme for Falakata | SM/06268 | Augmentation | Quotation for new Service Connection at Falakata Z-II,TW-II ,Application No- 4002584849 |  |  | VCH/001115/2020-2021 | 184/20-21 | 08/12/2020 |  | WBSEDCL | 1.35 | 0 | 0 | 0
7 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of existing Ground Water Based Piped Water Supply Scheme for Falakata | SM/06268 | Augmentation | Quotation for meter shifting at Falakata W/SS Apllication no. 4002654693 |  |  | VCH/000574/2021-2022 | null | 11/08/2021 |  | WBSEDCL | 0.08 | 0 | 0 | 0
8 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of existing Ground Water Based Piped Water Supply Scheme for Falakata | SM/06268 | Augmentation | Quotation for new service connection at Falakata W/SS TW No-IV,Z-III (Near Gope nagar) |  |  | VCH/001389/2021-2022 | null | 18/11/2021 |  | WBSEDCL | 0.87 | 0 | 0 | 0
9 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of existing Ground Water Based Piped Water Supply Scheme for Falakata | SM/06268 | Augmentation | Quotation for Load enhancement at Falakata W/SS TW no-I |  |  | VCH/001388/2021-2022 | null | 18/11/2021 |  | WBSEDCL | 1.56 | 0 | 0 | 0
10 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of existing Ground Water Based Piped Water Supply Scheme for Falakata | SM/06268 | Augmentation | Load Enhancement at Falakata W/SS, TW No. I |  |  | VCH/001466/2021-2022 | null | 09/12/2021 |  | WBSEDCL | 1.56 | 0 | 0 | 0
11 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of existing Ground Water Based Piped Water Supply Scheme for Falakata | SM/06268 | Augmentation | Quotation for new service connection at Falakata W/SS TW No-IV,Z-III (Near Gope nagar) Application no. 4002791801 |  |  | VCH/001831/2021-2022 | 151/21-22 | 10/12/2021 |  | WBSEDCL | 0.87 | 0 | 0 | 0
12 | ALIPURDUAR |  | Alipurduar Division | Augmentation of existing Ground Water Based Piped Water Supply Scheme for Falakata | SM/06268 | Augmentation | SUPPLY OF HSD FOR THE MONTH OF MARCH 2022 UNDER ALIPURDUAR DIV. PHE DTE. |  |  | VCH/001341/2021-2022 | 491/21-22 | 15/03/2022 |  | SHIVAM SERVICE STATION | 0.94 | 0 | 0 | 0
13 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of existing Ground Water Based Piped Water Supply Scheme for Falakata | SM/06268 | Augmentation | Operation and Guarding of Pumping machinery at Pump House No. I OF ZONE-II , Under FALAKATA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000771/2021-2022 | 1225/NMD-II | 28/10/2021 | 28/07/2022 | DIPALI CONSTRUCTION | 2.22 | 0 | 0 | 0
14 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of existing Ground Water Based Piped Water Supply Scheme for Falakata | SM/06268 | Augmentation | Supply, delivery & installation of 25 KVA, Servo Motor operated Copper wound line voltage stabilizer. of Falakata Water Supply Scheme TW No.-IV of Zone-III under NMD-II, PHE. Dte, Alipurduar. |  |  | ORD/000772/2021-2022 | 1375/NMD-II | 22/12/2021 | 21/01/2022 | NUPUR CHANDRA HALDER | 2.76 | 0 | 0 | 0
15 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of existing Ground Water Based Piped Water Supply Scheme for Falakata | SM/06268 | Augmentation | quotation for load enchantment Falakata ,Application no. 4002791941 |  |  | VCH/002871/2021-2022 | 172/21-22 | 04/03/2022 |  | WBSEDCL | 1.56 | 0 | 0 | 0
16 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of existing Ground Water Based Piped Water Supply Scheme for Falakata | SM/06268 | Augmentation | Supply & delivery of Electrical accessories (Fuse unit) for emergency breakdown purpose at Falakata W/S scheme and other adjacent sites in the dist. of alipurduar under Alipurduar Mechanical Sub-division ,PHE Dte. |  |  | ORD/000760/2021-2022 | 771/AMSD | 29/12/2021 | 08/01/2022 | M/S MATRI CONSTRUCTION | 0.84 | 0 | 0 | 0
17 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of existing Ground Water Based Piped Water Supply Scheme for Falakata | SM/06268 | Augmentation | Operation and Guarding of Pumping machinery at Pump House No. II OF ZONE-I , Under FALAKATA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000685/2021-2022 | 1221/NMD-II | 28/10/2021 | 28/07/2022 | QUAZI NOZRUL ISLAM | 2.22 | 0 | 0 | 0
18 | ALIPURDUAR |  | Alipurduar Division | Augmentation of existing Ground Water Based Piped Water Supply Scheme for Falakata | SM/06268 | Augmentation | Laying of Distribution of DI/UPVC line at aug. of Falakata PWSS under Alipurduar Division, PHED (College area Zone-II) Part-A |  |  | ORD/000437/2019-2020 | 1744/ALD | 14/02/2020 |  | JAL PRAVAHIKA PVT. LTD. | 34.94 | 22.17 | 63.45 | 0
19 | ALIPURDUAR |  | Alipurduar Division | Augmentation of existing Ground Water Based Piped Water Supply Scheme for Falakata | SM/06268 | Augmentation | Laying of Distribution of DI/UPVC line at Aug. of Falakata PWSS under Alipurduar Division P.H.E Dte. |  |  | ORD/000390/2019-2020 | 1743/ALD | 14/02/2020 |  | S DUTTA | 34.94 | 20.46 | 58.56 | 0
20 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of existing Ground Water Based Piped Water Supply Scheme for Falakata | SM/06268 | Augmentation | Operation and Guarding of Pumping machinery at Pump House No. II,Zone-II Under FalakataW/S Scheme, in the dist. Of Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000118/2022-2023 | 871/NMD-II | 08/07/2022 | 08/07/2023 | PRAGATI CONSTRUCTION COMPANY | 2.97 | 0 | 0 | 0
21 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of existing Ground Water Based Piped Water Supply Scheme for Falakata | SM/06268 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Falakata Water Supply Scheme TW No.-IV of Zone-III under NMD-II,PHE Dte. Alipurduar. |  |  | ORD/000754/2021-2022 | 66/NMD-II | 24/01/2022 | 23/02/2022 | COMBINE ENTERPRISES | 8 | 0 | 0 | 0
22 | ALIPURDUAR |  | Alipurduar Division | Augmentation of existing Ground Water Based Piped Water Supply Scheme for Falakata | SM/06268 | Augmentation | Laying of UPVC/DI/MS/CI distribution pipeline and others misc works near Dhupgurimore and SSB Camp for AUG of Falakata PWSS under Alipurduar Division, PHE Dte. | Birpara A.E |  | ORD/000430/2021-2022 | 2628/ALD | 18/02/2022 | 19/04/2022 | SREE MAA CONSTRUCTION | 10.54 | 0 | 0 | 0
23 | ALIPURDUAR |  | Alipurduar Division | Augmentation of existing Ground Water Based Piped Water Supply Scheme for Falakata | SM/06268 | Augmentation | Restoration of pipe line by providing stel piles at Mujhnai river for Barodoba village area at Aug. of Falakata WSS Alipurduar Division , PHE Dte. | Birpara A.E |  | ORD/000099/2022-2023 | 463/ALD | 13/05/2022 | 12/06/2022 | HARI CONSTRUCTION | 4.93 | 0 | 0 | 100
24 | ALIPURDUAR |  | Alipurduar Division | Augmentation of existing Ground Water Based Piped Water Supply Scheme for Falakata | SM/06268 | Augmentation | Sinking of Big Dia Tubewell , Construction of pump house incl B/wall and construction of 550 Cum capacity RCC Elevated reservior at AUG of Falakata Zone-II WSS at Falakata Block |  |  | ORD/000059/2019-2020 | 757/ALD | 07/06/2019 | 05/06/2024 | TAPASH KUMAR BHOWMICK | 116.07 | 110.51 | 95.21 | 100
Total | [13 empty] | 236.02 | 153.14 | 64.89