## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of computers, printers and peripherals at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings at 1st, 4th, 5th and 7th floor" for the period of 03 months i.e. from 01.04.2021 to 30.06.2021.¿ | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000323/2020-2021 | 777 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 2.1 | 0 | 0 | 0
2 | BANKURA |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of computers, printers and peripherals at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings at 1st, 4th, 5th and 7th floor" for the period of 03 months i.e. from 01.04.2021 to 30.06.2021.¿ | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000323/2020-2021 | 777 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 2.1 | 0 | 0 | 0
3 | BIRBHUM |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of computers, printers and peripherals at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings at 1st, 4th, 5th and 7th floor" for the period of 03 months i.e. from 01.04.2021 to 30.06.2021.¿ | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000323/2020-2021 | 777 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 2.1 | 0 | 0 | 0
4 | COOCHBEHAR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of computers, printers and peripherals at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings at 1st, 4th, 5th and 7th floor" for the period of 03 months i.e. from 01.04.2021 to 30.06.2021.¿ | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000323/2020-2021 | 777 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 2.1 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of computers, printers and peripherals at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings at 1st, 4th, 5th and 7th floor" for the period of 03 months i.e. from 01.04.2021 to 30.06.2021.¿ | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000323/2020-2021 | 777 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 2.1 | 0 | 0 | 0
6 | DARJEELING |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of computers, printers and peripherals at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings at 1st, 4th, 5th and 7th floor" for the period of 03 months i.e. from 01.04.2021 to 30.06.2021.¿ | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000323/2020-2021 | 777 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 2.1 | 0 | 0 | 0
7 | HOOGHLY |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of computers, printers and peripherals at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings at 1st, 4th, 5th and 7th floor" for the period of 03 months i.e. from 01.04.2021 to 30.06.2021.¿ | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000323/2020-2021 | 777 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 2.1 | 0 | 0 | 0
8 | HOWRAH |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of computers, printers and peripherals at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings at 1st, 4th, 5th and 7th floor" for the period of 03 months i.e. from 01.04.2021 to 30.06.2021.¿ | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000323/2020-2021 | 777 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 2.1 | 0 | 0 | 0
9 | JALPAIGURI |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of computers, printers and peripherals at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings at 1st, 4th, 5th and 7th floor" for the period of 03 months i.e. from 01.04.2021 to 30.06.2021.¿ | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000323/2020-2021 | 777 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 2.1 | 0 | 0 | 0
10 | JHARGRAM |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of computers, printers and peripherals at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings at 1st, 4th, 5th and 7th floor" for the period of 03 months i.e. from 01.04.2021 to 30.06.2021.¿ | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000323/2020-2021 | 777 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 2.1 | 0 | 0 | 0
11 | KALIMPONG |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of computers, printers and peripherals at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings at 1st, 4th, 5th and 7th floor" for the period of 03 months i.e. from 01.04.2021 to 30.06.2021.¿ | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000323/2020-2021 | 777 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 2.1 | 0 | 0 | 0
12 | MALDAH |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of computers, printers and peripherals at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings at 1st, 4th, 5th and 7th floor" for the period of 03 months i.e. from 01.04.2021 to 30.06.2021.¿ | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000323/2020-2021 | 777 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 2.1 | 0 | 0 | 0
13 | MURSHIDABAD |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of computers, printers and peripherals at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings at 1st, 4th, 5th and 7th floor" for the period of 03 months i.e. from 01.04.2021 to 30.06.2021.¿ | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000323/2020-2021 | 777 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 2.1 | 0 | 0 | 0
14 | NADIA |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of computers, printers and peripherals at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings at 1st, 4th, 5th and 7th floor" for the period of 03 months i.e. from 01.04.2021 to 30.06.2021.¿ | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000323/2020-2021 | 777 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 2.1 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of computers, printers and peripherals at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings at 1st, 4th, 5th and 7th floor" for the period of 03 months i.e. from 01.04.2021 to 30.06.2021.¿ | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000323/2020-2021 | 777 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 2.1 | 0 | 0 | 0
16 | PASCHIM BARDHAMAN |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of computers, printers and peripherals at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings at 1st, 4th, 5th and 7th floor" for the period of 03 months i.e. from 01.04.2021 to 30.06.2021.¿ | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000323/2020-2021 | 777 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 2.1 | 0 | 0 | 0
17 | PASCHIM MEDINIPUR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of computers, printers and peripherals at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings at 1st, 4th, 5th and 7th floor" for the period of 03 months i.e. from 01.04.2021 to 30.06.2021.¿ | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000323/2020-2021 | 777 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 2.1 | 0 | 0 | 0
18 | PURBA BARDHAMAN |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of computers, printers and peripherals at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings at 1st, 4th, 5th and 7th floor" for the period of 03 months i.e. from 01.04.2021 to 30.06.2021.¿ | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000323/2020-2021 | 777 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 2.1 | 0 | 0 | 0
19 | PURBA MEDINIPUR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of computers, printers and peripherals at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings at 1st, 4th, 5th and 7th floor" for the period of 03 months i.e. from 01.04.2021 to 30.06.2021.¿ | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000323/2020-2021 | 777 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 2.1 | 0 | 0 | 0
20 | PURULIA |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of computers, printers and peripherals at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings at 1st, 4th, 5th and 7th floor" for the period of 03 months i.e. from 01.04.2021 to 30.06.2021.¿ | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000323/2020-2021 | 777 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 2.1 | 0 | 0 | 0
21 | SOUTH 24 PARGANAS |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of computers, printers and peripherals at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings at 1st, 4th, 5th and 7th floor" for the period of 03 months i.e. from 01.04.2021 to 30.06.2021.¿ | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000323/2020-2021 | 777 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 2.1 | 0 | 0 | 0
22 | UTTAR DINAJPUR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of computers, printers and peripherals at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings at 1st, 4th, 5th and 7th floor" for the period of 03 months i.e. from 01.04.2021 to 30.06.2021.¿ | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000323/2020-2021 | 777 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 2.1 | 0 | 0 | 0
23 | ALIPURDUAR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of printers and fax at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings for the period of for the period of 03 months (i.e. from 01.04.2021 to 30.06.2021).¿ | Assistant Engineer, Barasat Arsenic Sub-Division |  | ORD/000324/2020-2021 | 784 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 0.37 | 0 | 0 | 0
24 | BANKURA |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of printers and fax at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings for the period of for the period of 03 months (i.e. from 01.04.2021 to 30.06.2021).¿ | Assistant Engineer, Barasat Arsenic Sub-Division |  | ORD/000324/2020-2021 | 784 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 0.37 | 0 | 0 | 0
25 | BIRBHUM |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of printers and fax at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings for the period of for the period of 03 months (i.e. from 01.04.2021 to 30.06.2021).¿ | Assistant Engineer, Barasat Arsenic Sub-Division |  | ORD/000324/2020-2021 | 784 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 0.37 | 0 | 0 | 0
26 | COOCHBEHAR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of printers and fax at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings for the period of for the period of 03 months (i.e. from 01.04.2021 to 30.06.2021).¿ | Assistant Engineer, Barasat Arsenic Sub-Division |  | ORD/000324/2020-2021 | 784 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 0.37 | 0 | 0 | 0
27 | DAKSHIN DINAJPUR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of printers and fax at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings for the period of for the period of 03 months (i.e. from 01.04.2021 to 30.06.2021).¿ | Assistant Engineer, Barasat Arsenic Sub-Division |  | ORD/000324/2020-2021 | 784 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 0.37 | 0 | 0 | 0
28 | DARJEELING |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of printers and fax at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings for the period of for the period of 03 months (i.e. from 01.04.2021 to 30.06.2021).¿ | Assistant Engineer, Barasat Arsenic Sub-Division |  | ORD/000324/2020-2021 | 784 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 0.37 | 0 | 0 | 0
29 | HOOGHLY |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of printers and fax at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings for the period of for the period of 03 months (i.e. from 01.04.2021 to 30.06.2021).¿ | Assistant Engineer, Barasat Arsenic Sub-Division |  | ORD/000324/2020-2021 | 784 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 0.37 | 0 | 0 | 0
30 | HOWRAH |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of printers and fax at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings for the period of for the period of 03 months (i.e. from 01.04.2021 to 30.06.2021).¿ | Assistant Engineer, Barasat Arsenic Sub-Division |  | ORD/000324/2020-2021 | 784 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 0.37 | 0 | 0 | 0
31 | JALPAIGURI |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of printers and fax at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings for the period of for the period of 03 months (i.e. from 01.04.2021 to 30.06.2021).¿ | Assistant Engineer, Barasat Arsenic Sub-Division |  | ORD/000324/2020-2021 | 784 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 0.37 | 0 | 0 | 0
32 | JHARGRAM |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of printers and fax at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings for the period of for the period of 03 months (i.e. from 01.04.2021 to 30.06.2021).¿ | Assistant Engineer, Barasat Arsenic Sub-Division |  | ORD/000324/2020-2021 | 784 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 0.37 | 0 | 0 | 0
33 | KALIMPONG |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of printers and fax at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings for the period of for the period of 03 months (i.e. from 01.04.2021 to 30.06.2021).¿ | Assistant Engineer, Barasat Arsenic Sub-Division |  | ORD/000324/2020-2021 | 784 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 0.37 | 0 | 0 | 0
34 | MALDAH |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of printers and fax at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings for the period of for the period of 03 months (i.e. from 01.04.2021 to 30.06.2021).¿ | Assistant Engineer, Barasat Arsenic Sub-Division |  | ORD/000324/2020-2021 | 784 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 0.37 | 0 | 0 | 0
35 | MURSHIDABAD |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of printers and fax at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings for the period of for the period of 03 months (i.e. from 01.04.2021 to 30.06.2021).¿ | Assistant Engineer, Barasat Arsenic Sub-Division |  | ORD/000324/2020-2021 | 784 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 0.37 | 0 | 0 | 0
36 | NADIA |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of printers and fax at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings for the period of for the period of 03 months (i.e. from 01.04.2021 to 30.06.2021).¿ | Assistant Engineer, Barasat Arsenic Sub-Division |  | ORD/000324/2020-2021 | 784 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 0.37 | 0 | 0 | 0
37 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of printers and fax at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings for the period of for the period of 03 months (i.e. from 01.04.2021 to 30.06.2021).¿ | Assistant Engineer, Barasat Arsenic Sub-Division |  | ORD/000324/2020-2021 | 784 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 0.37 | 0 | 0 | 0
38 | PASCHIM BARDHAMAN |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of printers and fax at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings for the period of for the period of 03 months (i.e. from 01.04.2021 to 30.06.2021).¿ | Assistant Engineer, Barasat Arsenic Sub-Division |  | ORD/000324/2020-2021 | 784 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 0.37 | 0 | 0 | 0
39 | PASCHIM MEDINIPUR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of printers and fax at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings for the period of for the period of 03 months (i.e. from 01.04.2021 to 30.06.2021).¿ | Assistant Engineer, Barasat Arsenic Sub-Division |  | ORD/000324/2020-2021 | 784 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 0.37 | 0 | 0 | 0
40 | PURBA BARDHAMAN |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of printers and fax at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings for the period of for the period of 03 months (i.e. from 01.04.2021 to 30.06.2021).¿ | Assistant Engineer, Barasat Arsenic Sub-Division |  | ORD/000324/2020-2021 | 784 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 0.37 | 0 | 0 | 0
41 | PURBA MEDINIPUR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of printers and fax at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings for the period of for the period of 03 months (i.e. from 01.04.2021 to 30.06.2021).¿ | Assistant Engineer, Barasat Arsenic Sub-Division |  | ORD/000324/2020-2021 | 784 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 0.37 | 0 | 0 | 0
42 | PURULIA |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of printers and fax at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings for the period of for the period of 03 months (i.e. from 01.04.2021 to 30.06.2021).¿ | Assistant Engineer, Barasat Arsenic Sub-Division |  | ORD/000324/2020-2021 | 784 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 0.37 | 0 | 0 | 0
43 | SOUTH 24 PARGANAS |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of printers and fax at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings for the period of for the period of 03 months (i.e. from 01.04.2021 to 30.06.2021).¿ | Assistant Engineer, Barasat Arsenic Sub-Division |  | ORD/000324/2020-2021 | 784 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 0.37 | 0 | 0 | 0
44 | UTTAR DINAJPUR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER for ¿Comprehensive maintenance and repair of printers and fax at the PHE Department and the office of the Chief Engineer, Headquarters, P.H.E Directorate, New Secretariat Buildings for the period of for the period of 03 months (i.e. from 01.04.2021 to 30.06.2021).¿ | Assistant Engineer, Barasat Arsenic Sub-Division |  | ORD/000324/2020-2021 | 784 / B.Ar.D | 22/03/2021 | 22/06/2021 | IONET | 0.37 | 0 | 0 | 0
45 | ALIPURDUAR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Supply and delivery of Support Services of Server Operating Systems, Annual Maintenance of Server & Network Hardware of Data Centre at Head Quarter for P.H.E. Department, Govt of West Bengal. (w.e.f. 09.09.2021 to 31.12.2021 i.e. 114 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000310/2021-2022 | 1498/B.Ar.D. | 07/09/2021 | 30/12/2021 | ALTAVISTA TECH SOLUTIONS | 14.05 | 0 | 0 | 0
46 | BANKURA |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Supply and delivery of Support Services of Server Operating Systems, Annual Maintenance of Server & Network Hardware of Data Centre at Head Quarter for P.H.E. Department, Govt of West Bengal. (w.e.f. 09.09.2021 to 31.12.2021 i.e. 114 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000310/2021-2022 | 1498/B.Ar.D. | 07/09/2021 | 30/12/2021 | ALTAVISTA TECH SOLUTIONS | 14.05 | 0 | 0 | 0
47 | BIRBHUM |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Supply and delivery of Support Services of Server Operating Systems, Annual Maintenance of Server & Network Hardware of Data Centre at Head Quarter for P.H.E. Department, Govt of West Bengal. (w.e.f. 09.09.2021 to 31.12.2021 i.e. 114 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000310/2021-2022 | 1498/B.Ar.D. | 07/09/2021 | 30/12/2021 | ALTAVISTA TECH SOLUTIONS | 14.05 | 0 | 0 | 0
48 | COOCHBEHAR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Supply and delivery of Support Services of Server Operating Systems, Annual Maintenance of Server & Network Hardware of Data Centre at Head Quarter for P.H.E. Department, Govt of West Bengal. (w.e.f. 09.09.2021 to 31.12.2021 i.e. 114 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000310/2021-2022 | 1498/B.Ar.D. | 07/09/2021 | 30/12/2021 | ALTAVISTA TECH SOLUTIONS | 14.05 | 0 | 0 | 0
49 | DAKSHIN DINAJPUR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Supply and delivery of Support Services of Server Operating Systems, Annual Maintenance of Server & Network Hardware of Data Centre at Head Quarter for P.H.E. Department, Govt of West Bengal. (w.e.f. 09.09.2021 to 31.12.2021 i.e. 114 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000310/2021-2022 | 1498/B.Ar.D. | 07/09/2021 | 30/12/2021 | ALTAVISTA TECH SOLUTIONS | 14.05 | 0 | 0 | 0
50 | DARJEELING |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Supply and delivery of Support Services of Server Operating Systems, Annual Maintenance of Server & Network Hardware of Data Centre at Head Quarter for P.H.E. Department, Govt of West Bengal. (w.e.f. 09.09.2021 to 31.12.2021 i.e. 114 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000310/2021-2022 | 1498/B.Ar.D. | 07/09/2021 | 30/12/2021 | ALTAVISTA TECH SOLUTIONS | 14.05 | 0 | 0 | 0
51 | HOOGHLY |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Supply and delivery of Support Services of Server Operating Systems, Annual Maintenance of Server & Network Hardware of Data Centre at Head Quarter for P.H.E. Department, Govt of West Bengal. (w.e.f. 09.09.2021 to 31.12.2021 i.e. 114 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000310/2021-2022 | 1498/B.Ar.D. | 07/09/2021 | 30/12/2021 | ALTAVISTA TECH SOLUTIONS | 14.05 | 0 | 0 | 0
52 | HOWRAH |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Supply and delivery of Support Services of Server Operating Systems, Annual Maintenance of Server & Network Hardware of Data Centre at Head Quarter for P.H.E. Department, Govt of West Bengal. (w.e.f. 09.09.2021 to 31.12.2021 i.e. 114 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000310/2021-2022 | 1498/B.Ar.D. | 07/09/2021 | 30/12/2021 | ALTAVISTA TECH SOLUTIONS | 14.05 | 0 | 0 | 0
53 | JALPAIGURI |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Supply and delivery of Support Services of Server Operating Systems, Annual Maintenance of Server & Network Hardware of Data Centre at Head Quarter for P.H.E. Department, Govt of West Bengal. (w.e.f. 09.09.2021 to 31.12.2021 i.e. 114 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000310/2021-2022 | 1498/B.Ar.D. | 07/09/2021 | 30/12/2021 | ALTAVISTA TECH SOLUTIONS | 14.05 | 0 | 0 | 0
54 | JHARGRAM |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Supply and delivery of Support Services of Server Operating Systems, Annual Maintenance of Server & Network Hardware of Data Centre at Head Quarter for P.H.E. Department, Govt of West Bengal. (w.e.f. 09.09.2021 to 31.12.2021 i.e. 114 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000310/2021-2022 | 1498/B.Ar.D. | 07/09/2021 | 30/12/2021 | ALTAVISTA TECH SOLUTIONS | 14.05 | 0 | 0 | 0
55 | KALIMPONG |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Supply and delivery of Support Services of Server Operating Systems, Annual Maintenance of Server & Network Hardware of Data Centre at Head Quarter for P.H.E. Department, Govt of West Bengal. (w.e.f. 09.09.2021 to 31.12.2021 i.e. 114 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000310/2021-2022 | 1498/B.Ar.D. | 07/09/2021 | 30/12/2021 | ALTAVISTA TECH SOLUTIONS | 14.05 | 0 | 0 | 0
56 | MALDAH |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Supply and delivery of Support Services of Server Operating Systems, Annual Maintenance of Server & Network Hardware of Data Centre at Head Quarter for P.H.E. Department, Govt of West Bengal. (w.e.f. 09.09.2021 to 31.12.2021 i.e. 114 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000310/2021-2022 | 1498/B.Ar.D. | 07/09/2021 | 30/12/2021 | ALTAVISTA TECH SOLUTIONS | 14.05 | 0 | 0 | 0
57 | MURSHIDABAD |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Supply and delivery of Support Services of Server Operating Systems, Annual Maintenance of Server & Network Hardware of Data Centre at Head Quarter for P.H.E. Department, Govt of West Bengal. (w.e.f. 09.09.2021 to 31.12.2021 i.e. 114 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000310/2021-2022 | 1498/B.Ar.D. | 07/09/2021 | 30/12/2021 | ALTAVISTA TECH SOLUTIONS | 14.05 | 0 | 0 | 0
58 | NADIA |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Supply and delivery of Support Services of Server Operating Systems, Annual Maintenance of Server & Network Hardware of Data Centre at Head Quarter for P.H.E. Department, Govt of West Bengal. (w.e.f. 09.09.2021 to 31.12.2021 i.e. 114 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000310/2021-2022 | 1498/B.Ar.D. | 07/09/2021 | 30/12/2021 | ALTAVISTA TECH SOLUTIONS | 14.05 | 0 | 0 | 0
59 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Supply and delivery of Support Services of Server Operating Systems, Annual Maintenance of Server & Network Hardware of Data Centre at Head Quarter for P.H.E. Department, Govt of West Bengal. (w.e.f. 09.09.2021 to 31.12.2021 i.e. 114 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000310/2021-2022 | 1498/B.Ar.D. | 07/09/2021 | 30/12/2021 | ALTAVISTA TECH SOLUTIONS | 14.05 | 0 | 0 | 0
60 | PASCHIM BARDHAMAN |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Supply and delivery of Support Services of Server Operating Systems, Annual Maintenance of Server & Network Hardware of Data Centre at Head Quarter for P.H.E. Department, Govt of West Bengal. (w.e.f. 09.09.2021 to 31.12.2021 i.e. 114 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000310/2021-2022 | 1498/B.Ar.D. | 07/09/2021 | 30/12/2021 | ALTAVISTA TECH SOLUTIONS | 14.05 | 0 | 0 | 0
61 | PASCHIM MEDINIPUR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Supply and delivery of Support Services of Server Operating Systems, Annual Maintenance of Server & Network Hardware of Data Centre at Head Quarter for P.H.E. Department, Govt of West Bengal. (w.e.f. 09.09.2021 to 31.12.2021 i.e. 114 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000310/2021-2022 | 1498/B.Ar.D. | 07/09/2021 | 30/12/2021 | ALTAVISTA TECH SOLUTIONS | 14.05 | 0 | 0 | 0
62 | PURBA BARDHAMAN |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Supply and delivery of Support Services of Server Operating Systems, Annual Maintenance of Server & Network Hardware of Data Centre at Head Quarter for P.H.E. Department, Govt of West Bengal. (w.e.f. 09.09.2021 to 31.12.2021 i.e. 114 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000310/2021-2022 | 1498/B.Ar.D. | 07/09/2021 | 30/12/2021 | ALTAVISTA TECH SOLUTIONS | 14.05 | 0 | 0 | 0
63 | PURBA MEDINIPUR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Supply and delivery of Support Services of Server Operating Systems, Annual Maintenance of Server & Network Hardware of Data Centre at Head Quarter for P.H.E. Department, Govt of West Bengal. (w.e.f. 09.09.2021 to 31.12.2021 i.e. 114 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000310/2021-2022 | 1498/B.Ar.D. | 07/09/2021 | 30/12/2021 | ALTAVISTA TECH SOLUTIONS | 14.05 | 0 | 0 | 0
64 | PURULIA |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Supply and delivery of Support Services of Server Operating Systems, Annual Maintenance of Server & Network Hardware of Data Centre at Head Quarter for P.H.E. Department, Govt of West Bengal. (w.e.f. 09.09.2021 to 31.12.2021 i.e. 114 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000310/2021-2022 | 1498/B.Ar.D. | 07/09/2021 | 30/12/2021 | ALTAVISTA TECH SOLUTIONS | 14.05 | 0 | 0 | 0
65 | SOUTH 24 PARGANAS |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Supply and delivery of Support Services of Server Operating Systems, Annual Maintenance of Server & Network Hardware of Data Centre at Head Quarter for P.H.E. Department, Govt of West Bengal. (w.e.f. 09.09.2021 to 31.12.2021 i.e. 114 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000310/2021-2022 | 1498/B.Ar.D. | 07/09/2021 | 30/12/2021 | ALTAVISTA TECH SOLUTIONS | 14.05 | 0 | 0 | 0
66 | UTTAR DINAJPUR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Supply and delivery of Support Services of Server Operating Systems, Annual Maintenance of Server & Network Hardware of Data Centre at Head Quarter for P.H.E. Department, Govt of West Bengal. (w.e.f. 09.09.2021 to 31.12.2021 i.e. 114 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000310/2021-2022 | 1498/B.Ar.D. | 07/09/2021 | 30/12/2021 | ALTAVISTA TECH SOLUTIONS | 14.05 | 0 | 0 | 0
67 | ALIPURDUAR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Enhancement & Maintenance of Official Web Portal of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000312/2021-2022 | 1318/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.6 | 0 | 0 | 0
68 | BANKURA |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Enhancement & Maintenance of Official Web Portal of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000312/2021-2022 | 1318/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.6 | 0 | 0 | 0
69 | BIRBHUM |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Enhancement & Maintenance of Official Web Portal of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000312/2021-2022 | 1318/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.6 | 0 | 0 | 0
70 | COOCHBEHAR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Enhancement & Maintenance of Official Web Portal of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000312/2021-2022 | 1318/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.6 | 0 | 0 | 0
71 | DAKSHIN DINAJPUR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Enhancement & Maintenance of Official Web Portal of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000312/2021-2022 | 1318/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.6 | 0 | 0 | 0
72 | DARJEELING |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Enhancement & Maintenance of Official Web Portal of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000312/2021-2022 | 1318/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.6 | 0 | 0 | 0
73 | HOOGHLY |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Enhancement & Maintenance of Official Web Portal of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000312/2021-2022 | 1318/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.6 | 0 | 0 | 0
74 | HOWRAH |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Enhancement & Maintenance of Official Web Portal of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000312/2021-2022 | 1318/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.6 | 0 | 0 | 0
75 | JALPAIGURI |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Enhancement & Maintenance of Official Web Portal of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000312/2021-2022 | 1318/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.6 | 0 | 0 | 0
76 | JHARGRAM |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Enhancement & Maintenance of Official Web Portal of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000312/2021-2022 | 1318/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.6 | 0 | 0 | 0
77 | KALIMPONG |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Enhancement & Maintenance of Official Web Portal of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000312/2021-2022 | 1318/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.6 | 0 | 0 | 0
78 | MALDAH |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Enhancement & Maintenance of Official Web Portal of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000312/2021-2022 | 1318/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.6 | 0 | 0 | 0
79 | MURSHIDABAD |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Enhancement & Maintenance of Official Web Portal of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000312/2021-2022 | 1318/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.6 | 0 | 0 | 0
80 | NADIA |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Enhancement & Maintenance of Official Web Portal of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000312/2021-2022 | 1318/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.6 | 0 | 0 | 0
81 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Enhancement & Maintenance of Official Web Portal of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000312/2021-2022 | 1318/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.6 | 0 | 0 | 0
82 | PASCHIM BARDHAMAN |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Enhancement & Maintenance of Official Web Portal of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000312/2021-2022 | 1318/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.6 | 0 | 0 | 0
83 | PASCHIM MEDINIPUR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Enhancement & Maintenance of Official Web Portal of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000312/2021-2022 | 1318/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.6 | 0 | 0 | 0
84 | PURBA BARDHAMAN |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Enhancement & Maintenance of Official Web Portal of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000312/2021-2022 | 1318/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.6 | 0 | 0 | 0
85 | PURBA MEDINIPUR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Enhancement & Maintenance of Official Web Portal of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000312/2021-2022 | 1318/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.6 | 0 | 0 | 0
86 | PURULIA |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Enhancement & Maintenance of Official Web Portal of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000312/2021-2022 | 1318/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.6 | 0 | 0 | 0
87 | SOUTH 24 PARGANAS |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Enhancement & Maintenance of Official Web Portal of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000312/2021-2022 | 1318/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.6 | 0 | 0 | 0
88 | UTTAR DINAJPUR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Enhancement & Maintenance of Official Web Portal of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000312/2021-2022 | 1318/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.6 | 0 | 0 | 0
89 | ALIPURDUAR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Maintenance of SSO Container Application for multiple software applications of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000313/2021-2022 | 1319/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.59 | 0 | 0 | 0
90 | BANKURA |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Maintenance of SSO Container Application for multiple software applications of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000313/2021-2022 | 1319/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.59 | 0 | 0 | 0
91 | BIRBHUM |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Maintenance of SSO Container Application for multiple software applications of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000313/2021-2022 | 1319/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.59 | 0 | 0 | 0
92 | COOCHBEHAR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Maintenance of SSO Container Application for multiple software applications of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000313/2021-2022 | 1319/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.59 | 0 | 0 | 0
93 | DAKSHIN DINAJPUR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Maintenance of SSO Container Application for multiple software applications of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000313/2021-2022 | 1319/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.59 | 0 | 0 | 0
94 | DARJEELING |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Maintenance of SSO Container Application for multiple software applications of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000313/2021-2022 | 1319/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.59 | 0 | 0 | 0
95 | HOOGHLY |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Maintenance of SSO Container Application for multiple software applications of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000313/2021-2022 | 1319/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.59 | 0 | 0 | 0
96 | HOWRAH |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Maintenance of SSO Container Application for multiple software applications of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000313/2021-2022 | 1319/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.59 | 0 | 0 | 0
97 | JALPAIGURI |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Maintenance of SSO Container Application for multiple software applications of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000313/2021-2022 | 1319/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.59 | 0 | 0 | 0
98 | JHARGRAM |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Maintenance of SSO Container Application for multiple software applications of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000313/2021-2022 | 1319/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.59 | 0 | 0 | 0
99 | KALIMPONG |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Maintenance of SSO Container Application for multiple software applications of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000313/2021-2022 | 1319/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.59 | 0 | 0 | 0
100 | MALDAH |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Maintenance of SSO Container Application for multiple software applications of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000313/2021-2022 | 1319/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.59 | 0 | 0 | 0
101 | MURSHIDABAD |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Maintenance of SSO Container Application for multiple software applications of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000313/2021-2022 | 1319/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.59 | 0 | 0 | 0
102 | NADIA |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Maintenance of SSO Container Application for multiple software applications of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000313/2021-2022 | 1319/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.59 | 0 | 0 | 0
103 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Maintenance of SSO Container Application for multiple software applications of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000313/2021-2022 | 1319/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.59 | 0 | 0 | 0
104 | PASCHIM BARDHAMAN |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Maintenance of SSO Container Application for multiple software applications of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000313/2021-2022 | 1319/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.59 | 0 | 0 | 0
105 | PASCHIM MEDINIPUR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Maintenance of SSO Container Application for multiple software applications of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000313/2021-2022 | 1319/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.59 | 0 | 0 | 0
106 | PURBA BARDHAMAN |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Maintenance of SSO Container Application for multiple software applications of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000313/2021-2022 | 1319/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.59 | 0 | 0 | 0
107 | PURBA MEDINIPUR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Maintenance of SSO Container Application for multiple software applications of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000313/2021-2022 | 1319/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.59 | 0 | 0 | 0
108 | PURULIA |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Maintenance of SSO Container Application for multiple software applications of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000313/2021-2022 | 1319/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.59 | 0 | 0 | 0
109 | SOUTH 24 PARGANAS |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Maintenance of SSO Container Application for multiple software applications of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000313/2021-2022 | 1319/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.59 | 0 | 0 | 0
110 | UTTAR DINAJPUR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Maintenance of SSO Container Application for multiple software applications of Public Health Engineering Department, Govt. of W.B. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000313/2021-2022 | 1319/B.Ar.D. | 16/08/2021 | 28/12/2021 | UNICODE DIGITECH | 3.59 | 0 | 0 | 0
111 | ALIPURDUAR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Provide Comprehensive Maintenance work for upkeep of the LAN, WLAN, Networking Devices at WBPHED HQ for West Bengal Public Health Engineering Department. Govt. of WB. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000311/2021-2022 | 1317/B.Ar.D. | 16/08/2021 | 28/12/2021 | ALTAVISTA TECH SOLUTIONS | 3.66 | 0 | 0 | 0
112 | BANKURA |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Provide Comprehensive Maintenance work for upkeep of the LAN, WLAN, Networking Devices at WBPHED HQ for West Bengal Public Health Engineering Department. Govt. of WB. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000311/2021-2022 | 1317/B.Ar.D. | 16/08/2021 | 28/12/2021 | ALTAVISTA TECH SOLUTIONS | 3.66 | 0 | 0 | 0
113 | BIRBHUM |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Provide Comprehensive Maintenance work for upkeep of the LAN, WLAN, Networking Devices at WBPHED HQ for West Bengal Public Health Engineering Department. Govt. of WB. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000311/2021-2022 | 1317/B.Ar.D. | 16/08/2021 | 28/12/2021 | ALTAVISTA TECH SOLUTIONS | 3.66 | 0 | 0 | 0
114 | COOCHBEHAR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Provide Comprehensive Maintenance work for upkeep of the LAN, WLAN, Networking Devices at WBPHED HQ for West Bengal Public Health Engineering Department. Govt. of WB. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000311/2021-2022 | 1317/B.Ar.D. | 16/08/2021 | 28/12/2021 | ALTAVISTA TECH SOLUTIONS | 3.66 | 0 | 0 | 0
115 | DAKSHIN DINAJPUR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Provide Comprehensive Maintenance work for upkeep of the LAN, WLAN, Networking Devices at WBPHED HQ for West Bengal Public Health Engineering Department. Govt. of WB. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000311/2021-2022 | 1317/B.Ar.D. | 16/08/2021 | 28/12/2021 | ALTAVISTA TECH SOLUTIONS | 3.66 | 0 | 0 | 0
116 | DARJEELING |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Provide Comprehensive Maintenance work for upkeep of the LAN, WLAN, Networking Devices at WBPHED HQ for West Bengal Public Health Engineering Department. Govt. of WB. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000311/2021-2022 | 1317/B.Ar.D. | 16/08/2021 | 28/12/2021 | ALTAVISTA TECH SOLUTIONS | 3.66 | 0 | 0 | 0
117 | HOOGHLY |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Provide Comprehensive Maintenance work for upkeep of the LAN, WLAN, Networking Devices at WBPHED HQ for West Bengal Public Health Engineering Department. Govt. of WB. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000311/2021-2022 | 1317/B.Ar.D. | 16/08/2021 | 28/12/2021 | ALTAVISTA TECH SOLUTIONS | 3.66 | 0 | 0 | 0
118 | HOWRAH |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Provide Comprehensive Maintenance work for upkeep of the LAN, WLAN, Networking Devices at WBPHED HQ for West Bengal Public Health Engineering Department. Govt. of WB. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000311/2021-2022 | 1317/B.Ar.D. | 16/08/2021 | 28/12/2021 | ALTAVISTA TECH SOLUTIONS | 3.66 | 0 | 0 | 0
119 | JALPAIGURI |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Provide Comprehensive Maintenance work for upkeep of the LAN, WLAN, Networking Devices at WBPHED HQ for West Bengal Public Health Engineering Department. Govt. of WB. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000311/2021-2022 | 1317/B.Ar.D. | 16/08/2021 | 28/12/2021 | ALTAVISTA TECH SOLUTIONS | 3.66 | 0 | 0 | 0
120 | JHARGRAM |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Provide Comprehensive Maintenance work for upkeep of the LAN, WLAN, Networking Devices at WBPHED HQ for West Bengal Public Health Engineering Department. Govt. of WB. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000311/2021-2022 | 1317/B.Ar.D. | 16/08/2021 | 28/12/2021 | ALTAVISTA TECH SOLUTIONS | 3.66 | 0 | 0 | 0
121 | KALIMPONG |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Provide Comprehensive Maintenance work for upkeep of the LAN, WLAN, Networking Devices at WBPHED HQ for West Bengal Public Health Engineering Department. Govt. of WB. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000311/2021-2022 | 1317/B.Ar.D. | 16/08/2021 | 28/12/2021 | ALTAVISTA TECH SOLUTIONS | 3.66 | 0 | 0 | 0
122 | MALDAH |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Provide Comprehensive Maintenance work for upkeep of the LAN, WLAN, Networking Devices at WBPHED HQ for West Bengal Public Health Engineering Department. Govt. of WB. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000311/2021-2022 | 1317/B.Ar.D. | 16/08/2021 | 28/12/2021 | ALTAVISTA TECH SOLUTIONS | 3.66 | 0 | 0 | 0
123 | MURSHIDABAD |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Provide Comprehensive Maintenance work for upkeep of the LAN, WLAN, Networking Devices at WBPHED HQ for West Bengal Public Health Engineering Department. Govt. of WB. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000311/2021-2022 | 1317/B.Ar.D. | 16/08/2021 | 28/12/2021 | ALTAVISTA TECH SOLUTIONS | 3.66 | 0 | 0 | 0
124 | NADIA |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Provide Comprehensive Maintenance work for upkeep of the LAN, WLAN, Networking Devices at WBPHED HQ for West Bengal Public Health Engineering Department. Govt. of WB. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000311/2021-2022 | 1317/B.Ar.D. | 16/08/2021 | 28/12/2021 | ALTAVISTA TECH SOLUTIONS | 3.66 | 0 | 0 | 0
125 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Provide Comprehensive Maintenance work for upkeep of the LAN, WLAN, Networking Devices at WBPHED HQ for West Bengal Public Health Engineering Department. Govt. of WB. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000311/2021-2022 | 1317/B.Ar.D. | 16/08/2021 | 28/12/2021 | ALTAVISTA TECH SOLUTIONS | 3.66 | 0 | 0 | 0
126 | PASCHIM BARDHAMAN |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Provide Comprehensive Maintenance work for upkeep of the LAN, WLAN, Networking Devices at WBPHED HQ for West Bengal Public Health Engineering Department. Govt. of WB. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000311/2021-2022 | 1317/B.Ar.D. | 16/08/2021 | 28/12/2021 | ALTAVISTA TECH SOLUTIONS | 3.66 | 0 | 0 | 0
127 | PASCHIM MEDINIPUR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Provide Comprehensive Maintenance work for upkeep of the LAN, WLAN, Networking Devices at WBPHED HQ for West Bengal Public Health Engineering Department. Govt. of WB. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000311/2021-2022 | 1317/B.Ar.D. | 16/08/2021 | 28/12/2021 | ALTAVISTA TECH SOLUTIONS | 3.66 | 0 | 0 | 0
128 | PURBA BARDHAMAN |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Provide Comprehensive Maintenance work for upkeep of the LAN, WLAN, Networking Devices at WBPHED HQ for West Bengal Public Health Engineering Department. Govt. of WB. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000311/2021-2022 | 1317/B.Ar.D. | 16/08/2021 | 28/12/2021 | ALTAVISTA TECH SOLUTIONS | 3.66 | 0 | 0 | 0
129 | PURBA MEDINIPUR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Provide Comprehensive Maintenance work for upkeep of the LAN, WLAN, Networking Devices at WBPHED HQ for West Bengal Public Health Engineering Department. Govt. of WB. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000311/2021-2022 | 1317/B.Ar.D. | 16/08/2021 | 28/12/2021 | ALTAVISTA TECH SOLUTIONS | 3.66 | 0 | 0 | 0
130 | PURULIA |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Provide Comprehensive Maintenance work for upkeep of the LAN, WLAN, Networking Devices at WBPHED HQ for West Bengal Public Health Engineering Department. Govt. of WB. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000311/2021-2022 | 1317/B.Ar.D. | 16/08/2021 | 28/12/2021 | ALTAVISTA TECH SOLUTIONS | 3.66 | 0 | 0 | 0
131 | SOUTH 24 PARGANAS |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Provide Comprehensive Maintenance work for upkeep of the LAN, WLAN, Networking Devices at WBPHED HQ for West Bengal Public Health Engineering Department. Govt. of WB. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000311/2021-2022 | 1317/B.Ar.D. | 16/08/2021 | 28/12/2021 | ALTAVISTA TECH SOLUTIONS | 3.66 | 0 | 0 | 0
132 | UTTAR DINAJPUR |  | Barasat Arsenic Division | Support, Customization & Upkeepment of Hardware and Software Based Solutions and ITES Projects etc. under MIS & Computerization | SM/06473 | New | CONTINUATION ORDER FOR Provide Comprehensive Maintenance work for upkeep of the LAN, WLAN, Networking Devices at WBPHED HQ for West Bengal Public Health Engineering Department. Govt. of WB. (w.e.f. 19.08.2021 to 30.12.2021 i.e. 134 days) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000311/2021-2022 | 1317/B.Ar.D. | 16/08/2021 | 28/12/2021 | ALTAVISTA TECH SOLUTIONS | 3.66 | 0 | 0 | 0
Total | [13 empty] | 602.32 | 0 | 0