## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dimdima Tea Garden Area Piped Water Supply Scheme. | SM/06549 | New | Quotation for New service connection , Dim Dima T.G Z-II, T/W No. I. Application No. 4002574464 |  |  | VCH/001104/2020-2021 | 182/20-21 | 08/12/2020 | 08/12/2020 | WBSEDCL | 0.85 | 0 | 0 | 0
2 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dimdima Tea Garden Area Piped Water Supply Scheme. | SM/06549 | New | Quotation for New service connection , Dim Dima T.G Z-II, T/W No. II. Application No. 4002574470 |  |  | VCH/001693/2019-2020 |  | 04/02/2020 | 04/02/2020 | WBSEDCL | 0.85 | 0 | 0 | 0
3 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dimdima Tea Garden Area Piped Water Supply Scheme. | SM/06549 | New | Quotation for New service connection , Dim Dima T.G Z-II,T/W No. II. Application No. 4002574470 |  |  | VCH/001107/2020-2021 | 182/20-21 | 08/12/2020 | 08/12/2020 | WBSEDCL | 0.85 | 0 | 0 | 0
4 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dimdima Tea Garden Area Piped Water Supply Scheme. | SM/06549 | New | Quotation for New service connection , Dim Dima T.G Z-I, T/W No. I. Application No. 4002574458 |  |  | VCH/001105/2020-2021 | 182/20-21 | 08/12/2020 | 08/12/2020 | WBSEDCL | 0.85 | 0 | 0 | 0
5 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dimdima Tea Garden Area Piped Water Supply Scheme. | SM/06549 | New | Quotation for New service connection , Dim Dima T.G Z-I, T/W No. II. Application No. 4002574462 |  |  | VCH/001106/2020-2021 | 182/20-21 | 08/12/2020 | 08/12/2020 | WBSEDCL | 0.85 | 0 | 0 | 0
6 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dimdima Tea Garden Area Piped Water Supply Scheme. | SM/06549 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Zone-II Under Dim Dima T.G W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000203/2021-2022 | 813/NMD-II | 13/07/2021 | 13/07/2022 | DIPA CHHETRI | 2.97 | 0 | 0 | 0
7 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dimdima Tea Garden Area Piped Water Supply Scheme. | SM/06549 | New | Operation and Guarding of pumping machinery at pump house No. I , Zone-I under Dim Dima T.G W/S Scheme in the dist. of Alipurduar. |  |  | ORD/000243/2021-2022 | 814/NMD-II | 13/07/2021 | 13/07/2022 | M/S KUNDU CONSTRUCTION | 2.97 | 0 | 0 | 0
8 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dimdima Tea Garden Area Piped Water Supply Scheme. | SM/06549 | New | Operation and Guarding of Pumping machinery at Pump House No. II, ZONE - I under DIM DIMA W/S Scheme. In the dist. Of ALIPURDUAR |  |  | ORD/000513/2021-2022 | 820/NMD-II | 13/07/2021 | 13/07/2022 | M/S DE ENGINEERING CONCERN | 2.97 | 0 | 0 | 0
9 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dimdima Tea Garden Area Piped Water Supply Scheme. | SM/06549 | New | Yard lighting arrangement at pump House No.-I, Zone-II under Dim Dima Tea Garden Water supply scheme Under Northern Mechanical Division-II P.H.E Dte. |  |  | ORD/000641/2021-2022 | 1106/NMD-II | 20/09/2021 | 20/10/2021 | B.B CONCERNED | 3.18 | 3.18 | 100 | 0
10 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dimdima Tea Garden Area Piped Water Supply Scheme. | SM/06549 | New | Operation & guarding of the pumping machinery at Pump House No. II ,Zone- I, under DIM DIMA TG W/S Scheme, in the dist. Of Alipurduar P.H.E.,Dte. |  |  | ORD/000773/2021-2022 | 204/AMSD | 24/06/2021 | 24/07/2021 | M/S DE ENGINEERING CONCERN | 0.25 | 0 | 0 | 0
11 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dimdima Tea Garden Area Piped Water Supply Scheme. | SM/06549 | New | Yard lighting arrangement at pump House No.-I, Zone-I under Dim Dima Tea Garden Water supply scheme Under Northern Mechanical Division-II P.H.E Dte." |  |  | ORD/000642/2021-2022 | 1105/NMD-II | 20/09/2021 | 20/10/2021 | BONANZA ENTERPRISE | 3.17 | 3.17 | 100 | 0
12 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dimdima Tea Garden Area Piped Water Supply Scheme. | SM/06549 | New | Operation and Guarding of Pumping machinery at Pump House No. II, ZONE- II under DIM DIMA T.G W/S Scheme. In the dist. Of ALIPURDUAR |  |  | ORD/000512/2021-2022 | 819/NMD-II | 13/07/2021 | 13/07/2022 | M/S UTPAL CHAKRABORTY & CO. | 2.97 | 0 | 0 | 0
Total | [13 empty] | 22.71 | 6.34 | 27.94