## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-2) | SM/07065 | Retrofitting | Construction of Truss roof for office cum Godown Path way at KAIJALI BUSTY WSS under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000085/2022-2023 | 449/ALD | 13/05/2022 | 12/06/2022 | DAS ENTERPRISE | 4.79 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-2) | SM/07065 | Retrofitting | Providing House connection for KAIJALI BUSTY water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-III | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000210/2020-2021 | 1164/ALD | 15/12/2020 | 13/02/2021 | GHOSH & SAHA CONSTRUCTION | 19.93 | 4.39 | 22 | 68
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-2) | SM/07065 | Retrofitting | Restoration of pipe line for Turturi Khanda (Kaijali Busty Area), Culvert crossing and Laying Delivery line with DI and MS under Kaijali Busty TG WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000329/2021-2022 | 2202/ALD | 11/01/2022 | 12/03/2022 | TAPASH KUMAR BHOWMICK | 41.95 | 14.92 | 35.56 | 66
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-2) | SM/07065 | Retrofitting | Laying of distribution of HDPE/DI pipeline for TURTURI TG area, Kaijali Busty PWSS under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000480/2021-2022 | 2899/ALD | 08/03/2022 | 07/05/2022 | ASHOK SAPKOTA | 34.24 | 0 | 0 | 68
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-2) | SM/07065 | Retrofitting | Laying Delivary line with M.S FOR Connection of KAIJALI BUSTY WSS under Jainti TG Water Supply Scheme . | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000087/2022-2023 | 451/ALD | 13/05/2022 | 12/06/2022 | TAPASH KUMAR BHOWMICK | 4.94 | 0 | 0 | 66
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-2) | SM/07065 | Retrofitting | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Kaijali Basti Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000110/2022-2023 | 702/ALD | 08/06/2022 | 08/07/2022 | NARENDRA BHADANI. | 4.98 | 4.98 | 100 | 66
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Kaijali Basty Piped Water Supply Scheme (Phase-2) | SM/07065 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000004/2022-2023 | 396/ALD | 11/05/2022 | 11/05/2022 | Resource Division | 9.83 | 0 | 0 | 0
Total | [13 empty] | 120.66 | 24.29 | 20.13