## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Water Supply Scheme (Phase-2) | SM/07066 | Retrofitting | Construction of Boundary wall near head work site of Lankapara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000395/2021-2022 | 2309/ALD | 25/01/2022 | 11/03/2022 | ASHOK SAPKOTA | 4.78 | 3.04 | 63.58 | 98
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Water Supply Scheme (Phase-2) | SM/07066 | Retrofitting | Construction of Pump House with sanitary & plumbing arrangement near head work site of Lankapara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000396/2021-2022 | 2310/ALD | 25/01/2022 | 26/03/2022 | ASHOK SAPKOTA | 5.03 | 4.68 | 93.04 | 98
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Water Supply Scheme (Phase-2) | SM/07066 | Retrofitting | Laying of HDPE/DI pipe line at different area of flank of Lankapara road/village road and Lankapara Bazar Area under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000182/2020-2021 | 1007/ALD | 12/11/2020 | 11/01/2021 | MADHAB SAHA | 33.79 | 13.5 | 39.95 | 99
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Water Supply Scheme (Phase-2) | SM/07066 | Retrofitting | Laying of DI/MS/HDPE Distribution pipe line for the LANKAPARA WSS (TULSHIPARA TG) under Alipurduar Division, PHE Dte. Dist-Alipurduar. | Birpara A.E | Birpara Sub Division | ORD/000268/2020-2021 | 1280/ALD | 05/01/2021 | 06/03/2021 | UMWELT ENGINEER PVT. LTD. | 30.9 | 0 | 0 | 98
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Water Supply Scheme (Phase-2) | SM/07066 | Retrofitting | Sinking of 1no. Tube Well for replacement and another 1no. new Tube Well near factory line by ODEX-195 method of drilling at Lankapara Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000205/2021-2022 | 1345/ALD | 08/10/2021 | 07/11/2021 | SASANKA ROY | 33 | 32.32 | 97.93 | 96
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Water Supply Scheme (Phase-2) | SM/07066 | Retrofitting | Development of rig Bore TW by ODEX-165 method of drilling at Lankapara WSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000261/2021-2022 | 1608/ALD | 22/11/2021 | 12/12/2021 | DILIP MAHATO | 0.66 | 0.5 | 75.49 | 99
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Water Supply Scheme (Phase-2) | SM/07066 | Retrofitting | Construction of balance portion of boundary wall at CWR site under LANKAPARA (TULSHIPARA TG ) WSS under Alipurduar Division PHE Dte . | Birpara A.E | Birpara Sub Division | ORD/000084/2022-2023 | 448/ALD | 13/05/2022 | 12/06/2022 | TAPASH KUMAR BHOWMICK | 4.91 | 4.8 | 97.75 | 97
8 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Water Supply Scheme (Phase-2) | SM/07066 | Retrofitting | Sinking of Rig Bore Tube well by Odex-165 method of drilling and installation of Raising Main and laying of DI/MS/HDPE pipe line for the Tulshipara and Lankapara Water Supply Scheme. | Birpara A.E | Birpara Sub Division | ORD/000181/2020-2021 | 1006/ALD | 12/11/2020 | 11/01/2021 | UMWELT ENGINEER PVT. LTD. | 32.34 | 0 | 0 | 97
9 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Water Supply Scheme (Phase-2) | SM/07066 | Retrofitting | Bridge Crossing and Laying of DI/MS/HDPE Distribution pipe line for the LANKAPARA WSS under Alipurduar Division, PHE Dte. Dist-Alipurduar. | Birpara A.E | Alipurduar Sub Division,Birpara Sub Division | ORD/000270/2020-2021 | 1282/ALD | 05/01/2021 | 01/01/2023 | GHOSH & SAHA CONSTRUCTION | 23.75 | 4.66 | 19.63 | 100
10 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Water Supply Scheme (Phase-2) | SM/07066 | Retrofitting | Providing House connection at LANKAPARA TG (Part-A) PWSS under Alipuduar Division, P.H.E. Dte. | Birpara A.E | Alipurduar Sub Division,Birpara Sub Division | ORD/000364/2020-2021 | 1807/ALD | 22/02/2021 | 31/08/2023 | GHOSH & SAHA CONSTRUCTION | 41.88 | 10.17 | 24.29 | 50
Total | [13 empty] | 211.03 | 73.66 | 34.9