## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-1) | SM/07126 | Retrofitting | Providing House connection for BAROBISHA Zone-II water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-III | HQ-A.E | Alipurduar Sub Division | ORD/000207/2020-2021 | 1161/ALD | 15/12/2020 | 13/02/2021 | TAPAN CHANDA | 29.9 | 59.81 | 200 | 0
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-1) | SM/07126 | Retrofitting | Providing House connection for BAROBISHA ZONE-II piped water supply scheme under Alipuduar Division, P.H.E. Dte. Part-4 |  |  | ORD/000249/2020-2021 | 1249/ALD | 28/12/2020 | 26/02/2021 | TAPAN CHANDA | 39.91 | 79.82 | 200 | 0
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-1) | SM/07126 | Retrofitting | Laying of UPVC & DI (with pillar) pipeline for Barobisha Zone-III Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-A) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000170/2021-2022 | 1320/ALD | 05/10/2021 | 04/12/2021 | AKANSHA COMMERCIAL PRIVATE LTD. | 79.02 | 6.22 | 7.87 | 66
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-1) | SM/07126 | Retrofitting | Extension of Distribution pipe line (Barman Para and Beltala) with UPVC Connection of BAROBISA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000555/2021-2022 | 3082/ALD | 22/03/2022 | 21/05/2022 | AASHIRBAD ENTERPRISE | 13.46 | 6.83 | 50.73 | 70
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-1) | SM/07126 | Retrofitting | Construction of approach road & car parking area with paver block & chequered tiles at Jainty WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division | Alipurduar Sub Division,RWS Alipurduar - I Block | ORD/000331/2021-2022 | 2107/ALD | 05/01/2022 | 04/02/2022 | DAS ENTERPRISE | 5.02 | 0.87 | 17.41 | 77
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Barobisa Piped Water Supply Scheme (Zone-II, Phase-1) | SM/07126 | Retrofitting | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Barobisha PWSS (Part-II) Under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000474/2021-2022 | 2764/ALD | 25/02/2022 | 26/04/2022 | TAPAN CHANDA | 50.32 | 0.17 | 0.34 | 60
Total | [13 empty] | 217.63 | 153.73 | 70.64