## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jagijhora Barabak Piped Water Supply Scheme | SM/07129 | Retrofitting | Laying of DI/MS/HDPE pipe line and providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-II) |  |  | VCH/000944/2020-2021 | 571/20-21 | 26/03/2021 | 26/03/2021 | PRAMESH LAMA | 10 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jagijhora Barabak Piped Water Supply Scheme | SM/07129 | Retrofitting | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Alipurduar - I Block,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 25/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 17.04 | 3.39 | 100
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jagijhora Barabak Piped Water Supply Scheme | SM/07129 | Retrofitting | Providing House connection for JOGENDRAPUR water supply scheme at Falakata Block under Alipuduar Division, P.H.E. Dte. Part-III | HQ-A.E | RWS Kalchini Block | ORD/000217/2020-2021 | 1168/ALD | 15/12/2020 | 13/02/2021 | SASANKA ROY | 29.9 | 13.08 | 43.73 | 67
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jagijhora Barabak Piped Water Supply Scheme | SM/07129 | Retrofitting | Providing House connection for Jogijhora water supply scheme at Falakata Block under Alipuduar Division, P.H.E. Dte.(Part-I) | Birpara A.E | Birpara Sub Division | ORD/000286/2020-2021 | 1334/ALD | 11/01/2021 | 10/02/2021 | BHAGWATI BHUJEL | 4.98 | 9.96 | 200 | 0
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jagijhora Barabak Piped Water Supply Scheme | SM/07129 | Retrofitting | Construction of 300cum OHR for Augmentation of Jagijhora Barabak Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000414/2021-2022 | 2582/ALD | 17/02/2022 | 16/08/2022 | ASHIM KUMAR GHOSH | 63.76 | 11.26 | 17.66 | 43
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jagijhora Barabak Piped Water Supply Scheme | SM/07129 | Retrofitting | Laying of distribution of HDPE/DI pipeline for Jogijhora Barabak PWSS under Alipurduar Division, PHE DTE. | Birpara A.E | Alipurduar Sub Division,Birpara Sub Division | ORD/000477/2021-2022 | 2896/ALD | 08/03/2022 | 23/10/2024 | MS DEYS CONSTRUCTION | 56.01 | 0 | 0 | 100
Total | [13 empty] | 667.24 | 51.34 | 7.69