## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHUMCHIPARA T.G. Piped Water Supply Scheme | SM/07130 | Retrofitting | "Collectio of house hold details at prescribrd format through mobile app/Hard Copy including Geo-reference as directed by the E.I.C. and submission the same (soft copy) to P.H.E. Dte. (for the financial year 2022-2023 from 01/04/2022 onwards)" | Birpara A.E | Birpara Sub Division | ORD/000578/2021-2022 | 3223/ALD | 31/03/2022 | 31/03/2023 | DILIP MAHATO | 4.96 | 0 | 0 | 53.5
2 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHUMCHIPARA T.G. Piped Water Supply Scheme | SM/07130 | Retrofitting | Withdrawing & relaying & laying of pipeline and other misc. works for retrofitting of DHUMCHIPARA PWSS under Alipurduar Division PHED. | Birpara A.E | Birpara Sub Division | ORD/000084/2020-2021 | 688/ALD | 16/09/2020 | 14/01/2021 | MITHUN DAS | 24.86 | 0.51 | 2.05 | 37
3 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHUMCHIPARA T.G. Piped Water Supply Scheme | SM/07130 | Retrofitting | Construction of Pump House, Boundary Wall, and Tube well Boring by ODEX-195 method of drilling including Rising main for DHUMCHIPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000399/2021-2022 | 2390/ALD | 31/01/2022 | 01/05/2022 | DILIP MAHATO | 27.18 | 26.69 | 98.17 | 18
4 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHUMCHIPARA T.G. Piped Water Supply Scheme | SM/07130 | Retrofitting | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Alipurduar Sub Division,Birpara Sub Division,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000556/2021-2022 | 855/ALD | 31/08/2021 | 30/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 0 | 0 | 0
5 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHUMCHIPARA T.G. Piped Water Supply Scheme | SM/07130 | Retrofitting | Repairing of boundary wall with Gate and pump house at 2nd Tubewell site of Dhumchipara WSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000224/2022-2023 | 1114/ALD | 29/07/2022 | 28/08/2022 | KAMALESH ROY | 2.58 | 1.66 | 64.41 | 37
6 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHUMCHIPARA T.G. Piped Water Supply Scheme | SM/07130 | Retrofitting | Withdrawing and relaying and laying of UPVC/DI/MS/CI distribution pipeline and other misc. works for Dhumchipara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000481/2021-2022 | 2900/ALD | 08/03/2022 | 07/05/2022 | MITHUN DAS | 25.93 | 25.83 | 99.58 | 100
7 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHUMCHIPARA T.G. Piped Water Supply Scheme | SM/07130 | Retrofitting | Preparation of detailed Additional cost Requirement D.P.R. booklets in connection to various PWSS under Alipurduar-I and Alipurduar- II Block under Alipurduar Division P.H.E Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division |  | ORD/000185/2023-2024 | 1203/ALD | 07/08/2023 | 06/09/2023 | ANIK BHATTACHARJEE | 0.78 | 0.78 | 100 | 100
8 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHUMCHIPARA T.G. Piped Water Supply Scheme | SM/07130 | Retrofitting | Preparation of operation and maintenance DPR booklet in connection to 92 no's piped water supply scheme under Alipurduar Division P.H.E Dte | HQ-A.E | Alipurduar Sub Division | ORD/000184/2023-2024 | 1202/ALD | 07/08/2023 | 06/09/2023 | ANIK BHATTACHARJEE | 0.78 | 0.78 | 100 | 100
9 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHUMCHIPARA T.G. Piped Water Supply Scheme | SM/07130 | Retrofitting | Supply & delivery of diff. materials at Alipurduar Sub-divisional stack yard for special maintenance of P/line for Dhumchipara TG |  |  | ORD/000451/2018-2019 | 584/ALD | 01/10/2018 |  | DILIP MAHATO | 4.74 | 4.74 | 100 | 0
10 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DHUMCHIPARA T.G. Piped Water Supply Scheme | SM/07130 | Retrofitting | Construction of Pump House, Boundary Wall, laying distribution system and providing FHTC for BHUTNIRGHAT Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Birpara A.E | Alipurduar Sub Division | ORD/000379/2021-2022 | 2379/ALD | 31/01/2022 | 01/05/2022 | DILIP MAHATO | 92.34 | 8.37 | 9.07 | 98
Total | [13 empty] | 2774.82 | 69.35 | 2.5