## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-2) | SM/07132 | Retrofitting | Supply, delivery and Installation of split type Air Conditioner for Junior Engineer Section of Alipurduar, Sadar Sub-Division, P.H.E Dte. | Birpara A.E | Birpara Sub Division | ORD/000302/2022-2023 | 1732/ALD | 22/09/2022 | 29/09/2022 | M/S BADAL CHANDRA SAHA | 0.64 | 0.64 | 100 | 20
2 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-2) | SM/07132 | Retrofitting | Supply, delivery and Installation of split type Air Conditioner for Chamber of Assistant Engineer, Alipurduar, Sadar Sub-Division, P.H.E Dte. | Birpara A.E | Birpara Sub Division | ORD/000301/2022-2023 | 1731/ALD | 22/09/2022 | 29/09/2022 | M/S BADAL CHANDRA SAHA | 0.64 | 0.64 | 100 | 20
3 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-2) | SM/07132 | Retrofitting | Laying of balance DI/MS/HDPE pipeline for the Dalmore-Ramjhora WSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000324/2020-2021 | 1456/ALD | 25/01/2021 | 11/03/2021 | ASHIT KUMAR SINGHA | 21.28 | 0 | 0 | 59
4 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-2) | SM/07132 | Retrofitting | Retrofitting of pipeline for Ramjhora TG PWSS area at Madarihat-Birpara Block under Alipurduar Division, P.H.E. Dte. | Birpara A.E | Birpara Sub Division | ORD/000316/2020-2021 | 1447/ALD | 25/01/2021 | 11/03/2021 | ASHIT KUMAR SINGHA | 16.96 | 0 | 0 | 58
5 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-2) | SM/07132 | Retrofitting | Laying of HDPE pipe line for Dalmore Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000524/2021-2022 | 2996/ALD | 15/03/2022 | 14/05/2022 | MS DEYS CONSTRUCTION | 8.33 | 0 | 0 | 58
6 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-2) | SM/07132 | Retrofitting | Repairing bottom dome, conical, shell wall etc. of existing Dalmore 350 cum OHR including protective and Decorative Acrylic exterior paint of Birpara Sub-Division under Alipurduar Division, P.H.E.Dte. (SM/07132) | Birpara A.E | Birpara Sub Division,RWS Falakata Block | ORD/000508/2023-2024 | 826/ALD | 14/03/2024 | 12/06/2024 | BHAGWATI BHUJEL | 4.79 | 0 | 0 | 100
Total | [13 empty] | 52.64 | 1.27 | 2.42