## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-1) | SM/07133 | Retrofitting | Construction of Pump House with Sanitary & Plumbing arrangement at H/W Site (Old) of Dalmore Water supply scheme under Alipurduar Division. P.H.E. Dte. | Birpara A.E | Birpara Sub Division | ORD/000062/2020-2021 | 538/ALD | 20/08/2020 | 18/12/2020 | PRAPTI DUTTA | 4.75 | 8.4 | 177.02 | 0
2 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-1) | SM/07133 | Retrofitting | Laying of balance DI/MS/HDPE pipeline for the Dalmore-Ramjhora WSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000324/2020-2021 | 1456/ALD | 25/01/2021 | 11/03/2021 | ASHIT KUMAR SINGHA | 21.28 | 4.28 | 20.11 | 59
3 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-1) | SM/07133 | Retrofitting | Retrofitting of pipeline for Ramjhora TG PWSS area at Madarihat-Birpara Block under Alipurduar Division, P.H.E. Dte. | Birpara A.E | Birpara Sub Division | ORD/000316/2020-2021 | 1447/ALD | 25/01/2021 | 11/03/2021 | ASHIT KUMAR SINGHA | 16.96 | 3.58 | 21.09 | 58
4 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-1) | SM/07133 | Retrofitting | Retrofitting work of pipeline of Dalmore PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000198/2021-2022 | 971/ALD | 13/09/2021 | 13/10/2021 | MS DEYS CONSTRUCTION | 5.04 | 5.04 | 100 | 59
5 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-1) | SM/07133 | Retrofitting | Construction of Pump House with Sanitary & Plumbing arrangement at 2nd Pump House Site of Dalmore-Ramjhora WSS (Ramjhora Pump House no-2) under Alipurduar Division PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000094/2021-2022 | 893/ALD | 03/09/2021 | 02/11/2021 | PRAMESH LAMA | 4.96 | 4.97 | 100.09 | 60
6 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-1) | SM/07133 | Retrofitting | Construction of Pump House with Sanitary & Plumbing arrangement at Headwork Site of Dalmore-Ramjhora WSS (Ramjhora Pump House no-1) under Alipurduar Division PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000095/2021-2022 | 894/ALD | 03/09/2021 | 02/11/2021 | PRAMESH LAMA | 4.96 | 4.97 | 100.1 | 0
7 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-1) | SM/07133 | Retrofitting | Fuel bill for the month of August 2021 |  |  | VCH/000570/2021-2022 | 121/21-22/PFMS | 08/09/2021 | 08/09/2021 | SHIVAM SERVICE STATION | 0.22 | 0 | 0 | 0
8 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-1) | SM/07133 | Retrofitting | Fuel bill for the month of August 2021 |  |  | VCH/000567/2021-2022 | 117/21-22/PFMS | 08/09/2021 | 08/09/2021 | SHIVAM SERVICE STATION | 0.11 | 0 | 0 | 0
9 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-1) | SM/07133 | Retrofitting | Laying of HDPE pipe line for Dalmore Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000524/2021-2022 | 2996/ALD | 15/03/2022 | 14/05/2022 | MS DEYS CONSTRUCTION | 8.33 | 7.04 | 84.48 | 58
10 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara / Jalswapna including retrofitting of existing distribution system under DALMORE RAMJHORA T.G. Piped Water Supply Scheme (Phase-1) | SM/07133 | Retrofitting | Soil investigation work for proposed Over Head Reservoir, Construction of 150Cum OHR, Construction of Pump House and Boundary wall at both TW site, LDS as per departmental design & drawing for DALMORE & RAMJHORA TG PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000399/2026-2027 | 23/ALD | 06/04/2026 | 02/11/2026 | MS HOSSEN ELECTRICALS | 149.78 | 0 | 0 | 0
Total | [13 empty] | 216.41 | 38.28 | 17.69