## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dalimpur Piped Water Supply Scheme (Phase-1) | SM/07137 | Retrofitting | Laying of UPVC/DI/MS Distribution pipe line and FHTC in connection with Jaldhara Jal Sapna and other misc work for Dalimpur WSS under Birpara Sub-Division, Alipurduar Division, PHE Dte.(under Jateswar-I GP area) | Birpara A.E | Birpara Sub Division | ORD/000234/2020-2021 | 1179/ALD | 15/12/2020 | 13/02/2021 | NARAYAN CHANDRA SAHA | 45.66 | 10.38 | 22.74 | 0
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dalimpur Piped Water Supply Scheme (Phase-1) | SM/07137 | Retrofitting | Laying of UPVC/DI/MS Distribution pipe line and FHTC in connection with Jaldhara Jal Sapna and other misc work for Dalimpur WSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000232/2020-2021 | 1178/ALD | 15/12/2020 | 13/02/2021 | M/S PALIT ENTERPRISE | 45.48 | 28.89 | 63.53 | 86
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dalimpur Piped Water Supply Scheme (Phase-1) | SM/07137 | Retrofitting | Extension of pipeline and connection with main line by UPVC, GI, DI pipe and construction of valve chamberand others at Bhutnirghat WSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000065/2022-2023 | 342/ALD | 02/05/2022 | 16/06/2022 | DILIP MAHATO | 25.7 | 0.68 | 2.64 | 92
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dalimpur Piped Water Supply Scheme (Phase-1) | SM/07137 | Retrofitting | Extension of Distribution line with UPVC pipe line (From B.Ed College to Pulin Biswas House) under Dalimpur Water Supply Scheme under Alipurduar Division,PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000132/2020-2021 | 878/ALD | 14/10/2020 | 13/11/2020 | NARAYAN CHANDRA SAHA | 3.14 | 2.97 | 94.69 | 0
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dalimpur Piped Water Supply Scheme (Phase-1) | SM/07137 | Retrofitting | Extension of Distribution line with UPVC pipe line (From Pulin Biswas House to Bipul Islam House) under Dalimpur Water Supply Scheme under Alipurduar Division,PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000133/2020-2021 | 879/ALD | 14/10/2020 | 13/11/2020 | PARAMJYOTI ENTERPRISE | 3.14 | 2.97 | 94.69 | 0
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dalimpur Piped Water Supply Scheme (Phase-1) | SM/07137 | Retrofitting | Extension of Distribution line with UPVC pipe line (From Bhaben Biswas House to Ghughurertala Hridoy Barman's House) at Deodanga under Dalimpur Water Supply Scheme under Alipurduar Division,PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000174/2020-2021 | 918/ALD | 16/10/2020 | 15/11/2020 | PARAMJYOTI ENTERPRISE | 3.16 | 2.98 | 94.27 | 0
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dalimpur Piped Water Supply Scheme (Phase-1) | SM/07137 | Retrofitting | Providing House connection for DALIMPUR water supply scheme at FALAKATA Block under Alipuduar Division, P.H.E. Dte. | Birpara A.E | Birpara Sub Division | ORD/000154/2020-2021 | 866/ALD | 14/10/2020 | 13/11/2020 | SANJIT SAHA | 4.93 | 4.93 | 100 | 88
8 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dalimpur Piped Water Supply Scheme (Phase-1) | SM/07137 | Retrofitting | Providing House connection for Dalimpur water supply scheme at Falakata Block under Alipuduar Division, P.H.E. Dte.(Part-II) | Birpara A.E | Birpara Sub Division | ORD/000214/2020-2021 | 1134/ALD | 10/12/2020 | 09/01/2021 | PARAMJYOTI ENTERPRISE | 4.98 | 4.98 | 100 | 85
9 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dalimpur Piped Water Supply Scheme (Phase-1) | SM/07137 | Retrofitting | Preparation of Augmentation D.P.R after investigation For Dalimpur W/S scheme under Alipurduar Division. | Birpara A.E | Birpara Sub Division | ORD/000114/2021-2022 | 920/ALD | 06/09/2021 | 06/10/2021 | BHAGWATI BHUJEL | 2.18 | 2.18 | 100 | 0
10 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dalimpur Piped Water Supply Scheme (Phase-1) | SM/07137 | Retrofitting | Extension of Distribution line with UPVC pipe line (From Bamoner Bhangha Nagesh barman's House to Kashikanta Biswas House) near Bulet Club under Dalimpur Water Supply Scheme under Alipurduar Division,PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000175/2020-2021 | 919/ALD | 16/10/2020 | 15/11/2020 | NARAYAN CHANDRA SAHA & SONS | 3.16 | 3 | 94.68 | 0
Total | [13 empty] | 141.53 | 63.97 | 45.2