## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Piped Water Supply Scheme (Phase-1) | SM/07138 | Retrofitting | Laying of HDPE/DI pipe line at different area of flank of Lankapara road/village road and Lankapara Bazar Area under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000182/2020-2021 | 1007/ALD | 12/11/2020 | 11/01/2021 | MADHAB SAHA | 33.79 | 13.57 | 40.16 | 99
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Piped Water Supply Scheme (Phase-1) | SM/07138 | Retrofitting | Sinking of Rig Bore Tube well by Odex-165 method of drilling and installation of Raising Main and laying of DI/MS/HDPE pipe line for the Tulshipara and Lankapara Water Supply Scheme. | Birpara A.E | Birpara Sub Division | ORD/000181/2020-2021 | 1006/ALD | 12/11/2020 | 11/01/2021 | UMWELT ENGINEER PVT. LTD. | 32.34 | 3.86 | 11.94 | 97
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Piped Water Supply Scheme (Phase-1) | SM/07138 | Retrofitting | PROVIDING HOUSE CONNECTION FOR DIMDIMA Z-I PWSS AT MADARIHAT-BIRPARA BLOCK UNDER ALIPURDUAR DIVISION, PHE DTE. PART-2 | Birpara A.E | Alipurduar Sub Division | ORD/000194/2020-2021 | 1025/ALD | 18/11/2020 | 17/01/2021 | DILIP MAHATO | 28.87 | 22.95 | 79.47 | 0
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Piped Water Supply Scheme (Phase-1) | SM/07138 | Retrofitting | Laying of DI/MS/HDPE Distribution pipe line for the LANKAPARA WSS (TULSHIPARA TG) under Alipurduar Division, PHE Dte. Dist-Alipurduar. | Birpara A.E | Birpara Sub Division | ORD/000268/2020-2021 | 1280/ALD | 05/01/2021 | 06/03/2021 | UMWELT ENGINEER PVT. LTD. | 30.9 | 22.49 | 72.77 | 98
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Piped Water Supply Scheme (Phase-1) | SM/07138 | Retrofitting | Development of rig Bore TW by ODEX-165 method of drilling at Lankapara WSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000261/2021-2022 | 1608/ALD | 22/11/2021 | 12/12/2021 | DILIP MAHATO | 0.66 | 0 | 0 | 99
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Piped Water Supply Scheme (Phase-1) | SM/07138 | Retrofitting | Sinking of 1no. Tube Well for replacement and another 1no. new Tube Well near factory line by ODEX-195 method of drilling at Lankapara Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000205/2021-2022 | 1345/ALD | 08/10/2021 | 07/11/2021 | SASANKA ROY | 33 | 0 | 0 | 96
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Piped Water Supply Scheme (Phase-1) | SM/07138 | Retrofitting | Providing House connection for JAIGAON piped water supply scheme (Old scheme Area) under Alipuduar Division, P.H.E. Dte. Part-1 | HQ-A.E | RWS Kalchini Block | ORD/000317/2020-2021 | 1449/ALD | 25/01/2021 | 11/03/2021 | MAHENDRA CHHETRI | 43.86 | 7.27 | 16.58 | 67
8 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Lankapara Piped Water Supply Scheme (Phase-1) | SM/07138 | Retrofitting | Construction of balance portion of boundary wall at CWR site under LANKAPARA (TULSHIPARA TG ) WSS under Alipurduar Division PHE Dte . | Birpara A.E | Birpara Sub Division | ORD/000084/2022-2023 | 448/ALD | 13/05/2022 | 12/06/2022 | TAPASH KUMAR BHOWMICK | 4.91 | 0 | 0 | 97
Total | [13 empty] | 208.32 | 70.13 | 33.67