## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-1) | SM/07175 | Retrofitting | Providing House connection for Birpara water supply scheme at Alipurduar -I Block under Alipuduar Division, P.H.E. Dte. Part-II | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000203/2020-2021 | 1157/ALD | 15/12/2020 | 13/02/2021 | DAS CONSTRUCTION | 29.9 | 29.9 | 100 | 97
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-1) | SM/07175 | Retrofitting | Providing House connection for Birpara water supply scheme at Alipurduar -I Block under Alipuduar Division, P.H.E. Dte. |  |  | ORD/000099/2020-2021 | 720/ALD | 22/09/2020 | 22/10/2020 | KAMALESH ROY | 4.98 | 9.96 | 200 | 0
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-1) | SM/07175 | Retrofitting | Laying of Distribution Line (HDPE and DI) for retrofitting of FHTC for BIRPARA WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000360/2020-2021 | 1754/ALD | 19/02/2021 | 05/04/2021 | BILTU DAS | 47.98 | 4.42 | 9.21 | 61
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-1) | SM/07175 | Retrofitting | Repairing of office Quarter and construction of attached toilet for Assistant Engineer Chamber of Birpara Sub-Division Office under Alipurduar Division PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000284/2021-2022 | 1853/ALD | 13/12/2021 | 27/01/2022 | DAS ENTERPRISE | 4.91 | 4.75 | 96.6 | 97
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-1) | SM/07175 | Retrofitting | Repairing of damaged pipe line, arrangement of water supply pipe line on emergency basis and other works due to widening and strengthening of PWD road at Sonapur PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000269/2021-2022 | 1835/ALD | 10/12/2021 | 09/01/2022 | HARI CONSTRUCTION | 2.56 | 2.56 | 100 | 97
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-1) | SM/07175 | Retrofitting | Extension and replacement of damaged pipeline and providing FHTC at Alipurduar Birpara Bazar Chowpathi and surrounding area under Birpara PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000178/2021-2022 | 1308/ALD | 05/10/2021 | 04/12/2021 | DAS CONSTRUCTION | 43.41 | 13.05 | 30.07 | 99
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-1) | SM/07175 | Retrofitting | Laying of 90mm & 110 mm dia UPVC pipeline for Bholardabri Water Supply Scheme uner Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division | ORD/000331/2020-2021 | 1467/ALD | 25/01/2021 | 11/03/2021 | HARI CONSTRUCTION | 5.08 | 10.16 | 199.89 | 0
8 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-1) | SM/07175 | Retrofitting | Providing House Connection (FHTC) at Birpara (APD) WSS under Alipurduar Division, PHE Dte. Part-7 | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000342/2021-2022 | 2118/ALD | 05/01/2022 | 04/02/2022 | DAS CONSTRUCTION | 5 | 4.38 | 87.59 | 96
9 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-1) | SM/07175 | Retrofitting | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Alipurduar ITI College area under Birpara PWSS. Alipurduar-I Block under Alipurduar Division, PHE Dte | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000327/2021-2022 | 2200/ALD | 11/01/2022 | 12/03/2022 | DAS CONSTRUCTION | 42.69 | 0 | 0 | 98
10 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Birpara (APD) Piped Water Supply Scheme (Phase-1) | SM/07175 | Retrofitting | Providing House Connection (FHTC) at Birpara (APD) WSS under Alipurduar Division, PHE Dte.Part-6 | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000341/2021-2022 | 2117/ALD | 05/01/2022 | 04/02/2022 | DAS CONSTRUCTION | 5 | 5 | 100 | 96
Total | [13 empty] | 191.51 | 84.18 | 43.95