## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-1) | SM/07177 | Retrofitting | Providing House connection for SALSALABARI water supply scheme at Alipurduar -II Block underAlipuduar Division, P.H.E. Dte. Part-II |  |  | VCH/000945/2020-2021 | 572/20-21 | 26/03/2021 | 26/03/2021 | TAPASH KUMAR BHOWMICK | 14 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-1) | SM/07177 | Retrofitting | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under SALSALABARI PWSS, Block- Alipurduar-II, Dist-Alipurduar. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000267/2020-2021 | 1279/ALD | 05/01/2021 | 06/03/2021 | MATRI ENTERPRISE | 45.43 | 30.3 | 66.71 | 97
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-1) | SM/07177 | Retrofitting | Providing House connection for Putimari water supply scheme at Alipurduar-II Block under Alipuduar Division, P.H.E. Dte. |  |  | ORD/000104/2020-2021 | 725/ALD | 22/09/2020 | 22/10/2020 | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 5.02 | 10.04 | 200 | 0
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-1) | SM/07177 | Retrofitting | Providing House connection for SALSALABARI water supply scheme at ALIPURDUAR-II Block under Alipuduar Division, P.H.E. Dte. |  |  | ORD/000166/2020-2021 | 910/ALD | 16/10/2020 | 15/11/2020 | M/S BHOWMICK CONSTRUCTION | 4.96 | 9.91 | 200 | 0
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-1) | SM/07177 | Retrofitting | Providing House connection for Jashodanga water supply scheme at Alipurduar -II Block under Alipuduar Division, P.H.E. Dte. Part-II | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000205/2020-2021 | 1159/ALD | 15/12/2020 | 13/02/2021 | TAPASH KUMAR BHOWMICK | 29.89 | 25.43 | 85.07 | 98
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-1) | SM/07177 | Retrofitting | Providing House connection for Purba Chepani water supply scheme at Alipurduar -II Block under Alipuduar Division, P.H.E. Dte.(Part-IV |  |  | ORD/000212/2020-2021 | 1132/ALD | 10/12/2020 | 09/01/2021 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 4.93 | 2.88 | 58.31 | 0
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-1) | SM/07177 | Retrofitting | Construction of Boundary Wall at Dalda Bari of Jaigaon WSS, Zone-II under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000040/2021-2022 | 551/ALD | 14/07/2021 | 28/08/2021 | TAPASH DAS | 4.9 | 0 | 0.06 | 0
8 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Salsalabari Piped Water Supply Scheme (Phase-1) | SM/07177 | Retrofitting | Preparation of Augmentation D.P.R after investigation For Jateswar W/S scheme under Alipurduar Division. | Birpara A.E | Birpara Sub Division | ORD/000111/2021-2022 | 914/ALD | 06/09/2021 | 06/10/2021 | BHAGWATI BHUJEL | 2.31 | 0.01 | 0.23 | 0
Total | [13 empty] | 111.44 | 78.57 | 70.51