## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-2) | SM/07179 | Retrofitting | Providing House connection for Munshipara piped water supply scheme at Alipurduar-I Block under Alipuduar Division, P.H.E. Dte.Part-II | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000204/2020-2021 | 1158/ALD | 15/12/2020 | 13/02/2021 | TAPASH DAS | 19.93 | 0 | 0 | 82
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-2) | SM/07179 | Retrofitting | Providing FHTC and other allied works at Munshipara WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000161/2021-2022 | 1303/ALD | 05/10/2021 | 04/12/2021 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 44.94 | 31.33 | 69.72 | 82
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-2) | SM/07179 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Munshipara WSS under Alipurduar Division, PHE Dte. Part-5 | Alipurduar RWS | RWS Alipurduar - I Block,RWS Madarihat - Birpara Block | ORD/000278/2021-2022 | 1845/ALD | 10/12/2021 | 09/01/2022 | RATAN DUTTA | 4.35 | 2.57 | 59.2 | 82
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-2) | SM/07179 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Munshipara WSS under Alipurduar Division, PHE Dte. Part-6 | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000279/2021-2022 | 1846/ALD | 10/12/2021 | 09/01/2022 | AASHIRBAD ENTERPRISE | 4.34 | 0 | 0 | 80
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-2) | SM/07179 | Retrofitting | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of DIMA TG Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar RWS,HQ-A.E | RWS Alipurduar - I Block,RWS Kalchini Block | ORD/000293/2021-2022 | 1991/ALD | 27/12/2021 | 27/03/2022 | GOBINDA BAGCHI | 20.87 | 0 | 0 | 72
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-2) | SM/07179 | Retrofitting | Laying of DI/UPVC pipeline along with PMGSY Road and other misc. works related to Munshipara PWSS under Alipurduar Division PHE DTE. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000187/2020-2021 | 1012/ALD | 12/11/2020 | 11/01/2021 | TAPASH DAS | 35.88 | 8.78 | 24.48 | 83
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Munshipara Piped Water Supply Scheme (Phase-2) | SM/07179 | Retrofitting | Laying Distribution line of UPVC and DI with providing FHTC Connection for the Salkumar and Munshipara Water Supply Scheme Area under Alipurduar Division, PHE Dte. | Alipurduar RWS,Birpara A.E | Birpara Sub Division,RWS Alipurduar - I Block,RWS Madarihat - Birpara Block | ORD/000196/2021-2022 | 1317/ALD | 05/10/2021 | 11/05/2026 | DILIP MAHATO | 58.07 | 0 | 0 | 85
Total | [13 empty] | 188.39 | 42.69 | 22.66