## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Totopara Piped Water Supply Scheme | SM/07180 | Retrofitting | Entry of data for house Connection (JJM) of PWSS in website under Alipurduar division, PHE Dte. (Part-B) | HQ-A.E |  | ORD/000516/2020-2021 | 845/ALD | 13/10/2020 | 12/12/2020 | TAPASH KUMAR BHOWMICK | 0.96 | 1.92 | 200 | 0
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Totopara Piped Water Supply Scheme | SM/07180 | Retrofitting | Entry of data for house Connection (JJM) of PWSS in website under Alipurduar division, PHE Dte. (Part-C) | HQ-A.E |  | ORD/000518/2020-2021 | 1092/ALD | 02/12/2020 | 31/01/2021 | HARIDAS GHOSH | 0.96 | 1.92 | 200 | 0
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Totopara Piped Water Supply Scheme | SM/07180 | Retrofitting | Collectio of house hold details at prescribrd format through mobile app/Hard Copy including Geo-reference as directed by the E.I.C. and submission the same to PHE Dte. in soft copy.(Part-B) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000515/2020-2021 | 844/ALD | 13/10/2020 | 12/12/2020 | TAPASH KUMAR BHOWMICK | 0.98 | 1.96 | 200 | 0
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Totopara Piped Water Supply Scheme | SM/07180 | Retrofitting | Collectio of house hold details at prescribrd format through mobile app/Hard Copy including Geo-reference as directed by the E.I.C. and submission the same to PHE Dte. in soft copy.(Part-C) | Alipurduar Sadar Sub Division |  | ORD/000517/2020-2021 | 1091/ALD | 02/12/2020 | 31/01/2021 | HARIDAS GHOSH | 0.98 | 1.96 | 200 | 0
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Totopara Piped Water Supply Scheme | SM/07180 | Retrofitting | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) (Preferably TUV) for Assistant Engineer, Alipurduar Sadar Sub-Division, P.H.E. Dte.(from 01.01.2022 to 31.12.2022) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000306/2021-2022 | 2013/ALD | 29/12/2021 | 29/12/2022 | MATRI ENTERPRISE | 1.76 | 0 | 0 | 0
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Totopara Piped Water Supply Scheme | SM/07180 | Retrofitting | Providing FHTC from existing distribution system as per specification for TOTOPARA PWSS under madarihat - Birpara Block under Alipurduar Division PHE Dte. | HQ-A.E | JUNIOR ENGINEER | ORD/000044/2025-2026 | 669/ALD | 21/05/2025 | 19/08/2025 | DULAL DAS | 23.27 | 0 | 0 | 15
Total | [13 empty] | 28.92 | 7.76 | 26.84