## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Loknathpur and Amp Adj. Mouza Piped Water Supply Scheme (Phase-2) | SM/07183 | Retrofitting | Retrofitting of pipeline etc. for the 'Jal Sapna' programme (FHTC for every house hold) under Loknathpur PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000368/2021-2022 | 2296/ALD | 24/01/2022 | 25/03/2022 | GOUTAM KUMAR DAS | 45.8 | 16.58 | 36.19 | 93.5
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Loknathpur and Amp Adj. Mouza Piped Water Supply Scheme (Phase-2) | SM/07183 | Retrofitting | Laying of distribution pipeline with DI and UPVC pipes for interconnection of Dhaolajhora PWSS with Loknathpur PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000540/2021-2022 | 3192/ALD | 28/03/2022 | 27/05/2022 | GOUTAM KUMAR DAS | 49.89 | 0 | 0 | 81
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Loknathpur and Amp Adj. Mouza Piped Water Supply Scheme (Phase-2) | SM/07183 | Retrofitting | Restoration of pipe line by providing steel piles at Turturi River for LOKNATHPUR Water Supply Scheme Under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division |  | ORD/000088/2020-2021 | 692/ALD | 16/09/2020 | 14/01/2021 | MATARA CONSTRUCTION CO | 6.04 | 0 | 0 | 100
Total | [13 empty] | 101.73 | 16.58 | 16.29