## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) | SM/07186 | Retrofitting | Construction of Approach road for 2nd TWS & others misc work of Radharani WSS under Alipurduar Division PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000106/2021-2022 | 904/ALD | 03/09/2021 | 03/10/2021 | SOUVIK ROY PALADHI | 4.98 | 0 | 0 | 86
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) | SM/07186 | Retrofitting | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of DIMA TG Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar RWS,HQ-A.E | RWS Alipurduar - I Block,RWS Kalchini Block | ORD/000293/2021-2022 | 1991/ALD | 27/12/2021 | 27/03/2022 | GOBINDA BAGCHI | 20.87 | 0 | 0 | 72
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) | SM/07186 | Retrofitting | Laying HDPE pipe , Road crossing and other misc woks related to Radharani WSS under Alipurduar Division PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000272/2021-2022 | 1838/ALD | 10/12/2021 | 24/01/2022 | UMWELT ENGINEER PVT. LTD. | 3.01 | 0 | 0 | 91
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) | SM/07186 | Retrofitting | Providing FHTC at surrounding area of Radharani Piped Water Supply Scheme Under Alipurduar Division, PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000476/2021-2022 | 2762/ALD | 25/02/2022 | 26/04/2022 | SOUVIK ROY PALADHI | 34.95 | 0 | 0 | 92
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) | SM/07186 | Retrofitting | PROVIDING HOUSE CONNECTION FOR RADHARANI PWSS AT KALCHINI BLOCK UNDER ALIPURDUAR DIVISION, PHE DTE. PART-2 | HQ-A.E | RWS Kalchini Block | ORD/000197/2020-2021 | 1028/ALD | 18/11/2020 | 17/01/2021 | UMWELT ENGINEER PVT. LTD. | 37.24 | 0 | 0 | 91
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) | SM/07186 | Retrofitting | Balance work of OHR Construction of PHouse B/Wall Godown & ODEX-165 Tubewell incl. laying of DI/HDPE Pipe for Nayabasti SSB Camp at RADHARANI PWSS under Alipurduar Division PHED. | HQ-A.E | RWS Kalchini Block | ORD/000076/2020-2021 | 627/ALD | 03/09/2020 | 01/01/2021 | UMWELT ENGINEER PVT. LTD. | 65.53 | 0 | 0 | 92
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) | SM/07186 | Retrofitting | PROVIDING HOUSE CONNECTION FOR RADHARANI PWSS AT KALCHINI BLOCK UNDER ALIPURDUAR DIVISION, PHE DTE. PART-1 | HQ-A.E | RWS Kalchini Block | ORD/000196/2020-2021 | 1027/ALD | 18/11/2020 | 17/01/2021 | UMWELT ENGINEER PVT. LTD. | 37.24 | 0 | 0 | 92
8 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) | SM/07186 | Retrofitting | Balance work of office cum Godown at Radharani WSS under Alipurduar Division PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000273/2021-2022 | 1839/ALD | 10/12/2021 | 08/02/2022 | UMWELT ENGINEER PVT. LTD. | 4.97 | 0 | 0 | 92
9 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) | SM/07186 | Retrofitting | Balance work of construction of RADHARANI GODOWN cum REST SHED at RADHARANI WSS under Alipurduar Division , PHE Dte ( Part - A) | HQ-A.E | RWS Kalchini Block | ORD/000090/2022-2023 | 454/ALD | 13/05/2022 | 12/06/2022 | BHAGWATI BHUJEL | 5.02 | 0 | 0 | 92
10 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) | SM/07186 | Retrofitting | Construction of Approach Road with paver Block at RADHARANI WSS under Alipurduar Division , PHE Dte | HQ-A.E | RWS Kalchini Block | ORD/000091/2022-2023 | 455/ALD | 13/05/2022 | 12/06/2022 | BHAGWATI BHUJEL | 4.96 | 0 | 0 | 92
11 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) | SM/07186 | Retrofitting | Plinth protection of office cum GODOWN surface dressing & land development (H/W) at RADHARANI WSS under Alipurduar Division , PHE Dte | HQ-A.E | RWS Kalchini Block | ORD/000093/2022-2023 | 457/ALD | 13/05/2022 | 12/06/2022 | DILIP MAHATO | 4.39 | 0 | 0 | 82
12 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) | SM/07186 | Retrofitting | Balance work of Radharani Godown cum rest shed under Radharani WSS under Alipurduar Division, PHE Dte. (Part-B) | HQ-A.E | RWS Kalchini Block | ORD/000186/2022-2023 | 1020/ALD | 21/07/2022 | 20/08/2022 | ASHOK PRADHAN | 2.82 | 0 | 0 | 89
13 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) | SM/07186 | Retrofitting | Laying of HDPE pipe line for Bijaynagar Busty Area under Radharani Water Supply Scheme, Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000328/2021-2022 | 2201/ALD | 11/01/2022 | 12/03/2022 | SOUVIK ROY PALADHI | 41.96 | 0 | 0 | 92
14 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Radharani T.G Piped Water Supply Scheme (Phase-2) | SM/07186 | Retrofitting | Construction of Pump House, Boundary wall, Tube well boring (ODEX- 165 Method) Rising main of 4th T/W site of Radharani TG WSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000298/2022-2023 | 1689/ALD | 20/09/2022 | 18/01/2023 | BHAGWATI BHUJEL | 20.53 | 0 | 0 | 100
Total | [13 empty] | 288.48 | 0 | 0