## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-1) | SM/07187 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Banchukamari WSS under Alipurduar Division, PHE Dte. Part-4 | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000277/2021-2022 | 1844/ALD | 10/12/2021 | 09/01/2022 | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 5.04 | 0 | 0 | 87
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-1) | SM/07187 | Retrofitting | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Banchukamari PWSS. Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000378/2021-2022 | 2378/ALD | 31/01/2022 | 01/04/2022 | SHIBA ENTERPRISE | 51.82 | 0 | 0 | 87
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-1) | SM/07187 | Retrofitting | Providing House connection for Banchukamari piped water supply scheme at Alipurduar -I Block under Alipuduar Division, P.H.E. Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000100/2020-2021 | 721/ALD | 22/09/2020 | 22/10/2020 | DAS CONSTRUCTION | 4.99 | 4.99 | 100 | 0
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-1) | SM/07187 | Retrofitting | Providing House connection for BHOLARDABRI PWSS under Alipuduar Division, P.H.E. Dte. |  |  | ORD/000371/2020-2021 | 1767/ALD | 19/02/2021 | 20/04/2021 | HARIDAS GHOSH | 10.03 | 10.03 | 100 | 0
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-1) | SM/07187 | Retrofitting | Providing House connection for BHOLARDABRI water supply scheme at ALIPURDUAR-I Block under Alipuduar Division, P.H.E. Dte.(Part-2) |  |  | ORD/000321/2020-2021 | 1462/ALD | 25/01/2021 | 24/02/2021 | HARI CONSTRUCTION | 5.01 | 5.01 | 100 | 0
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-1) | SM/07187 | Retrofitting | Providing House connection for KALCHINI water supply scheme at KALCHINI Block under Alipuduar Division, P.H.E. Dte.(Part-3) | HQ-A.E | RWS Kalchini Block | ORD/000327/2020-2021 | 1463/ALD | 25/01/2021 | 24/02/2021 | HARI CONSTRUCTION | 4.98 | 2.83 | 56.8 | 97
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-1) | SM/07187 | Retrofitting | Providing House connection for BHOLARDABRI WSS at Alipurduar-II Block under Alipurduar Division, PHE Dte. (Part-5) | Alipurduar RWS | Alipurduar Sub Division | ORD/000400/2020-2021 | 1586/ALD | 10/02/2021 | 11/04/2021 | HARIDAS GHOSH | 4.98 | 4.98 | 100 | 0
8 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-1) | SM/07187 | Retrofitting | Providing House connection for BHOLARDABRI WSS at Alipurduar-II Block under Alipurduar Division, PHE Dte. (Part-4) | Alipurduar RWS | Alipurduar Sub Division | ORD/000399/2020-2021 | 1585/ALD | 10/02/2021 | 11/04/2021 | HARIDAS GHOSH | 4.98 | 4.98 | 100 | 0
9 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Banchukamari Piped Water Supply Scheme (Phase-1) | SM/07187 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Banchukamari WSS under Alipurduar Division, PHE Dte. Part-3 | Alipurduar RWS,HQ-A.E | Birpara Sub Division,RWS Alipurduar - I Block | ORD/000280/2021-2022 | 1843/ALD | 10/12/2021 | 01/11/2025 | PROJIT HALDER | 5.02 | 0 | 0 | 87
Total | [13 empty] | 96.87 | 32.83 | 33.89