## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dhaolajhora T.G Piped Water Supply Scheme | SM/07191 | Retrofitting | Laying of distribution pipeline with DI and UPVC pipes for interconnection of Dhaolajhora PWSS with Loknathpur PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000540/2021-2022 | 3192/ALD | 28/03/2022 | 27/05/2022 | GOUTAM KUMAR DAS | 49.89 | 1.8 | 3.61 | 81
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dhaolajhora T.G Piped Water Supply Scheme | SM/07191 | Retrofitting | Repairing of old UPVC pipe line , FHTC and other misc. work related to DHAOLAJHORA PWSS Alipurduar - II Block under Alipurduar Division , PHE Dte | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000071/2022-2023 | 436/ALD | 13/05/2022 | 12/06/2022 | MATARA CONSTRUCTION CO | 3.3 | 3.29 | 99.67 | 26.5
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Dhaolajhora T.G Piped Water Supply Scheme | SM/07191 | Retrofitting | Laying of rising main line with HDPE PN10, horizontal boring by HDD method , bridge and culvert crossing, left out portion of household connection with HDPE pipe, providing balance FHTC, construction of pathway, surface drain and chatal, installation of paver block, land development along with the other allied works at DHAOLAJHORA (SM/07191) 3rd TW site PWSS of Alipurduar Sadar Sub-Division under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000205/2024-2025 | 1954/ALD | 02/07/2024 | 30/09/2024 | CHANDAN KIRTONIA | 33.15 | 0 | 0 | 0
Total | [13 empty] | 86.35 | 5.09 | 5.9