## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme | SM/07192 | Retrofitting | Fuel bill for the month of August 2021 |  |  | VCH/000570/2021-2022 | 121/21-22/PFMS | 08/09/2021 | 08/09/2021 | SHIVAM SERVICE STATION | 0.22 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme | SM/07192 | Retrofitting | Providing House connection for Munshipara piped water supply scheme at Alipurduar -I Block under Alipuduar Division, P.H.E. Dte. |  |  | ORD/000101/2020-2021 | 722/ALD | 22/09/2020 | 22/10/2020 | TAPASH DAS | 4.98 | 9.97 | 200 | 0
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme | SM/07192 | Retrofitting | Construction of Soak well, Fencing and other works at Madhu TG PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | Birpara Sub Division | ORD/000039/2020-2021 | 516/ALD | 20/08/2020 | 19/10/2020 | TAPASH KUMAR BHOWMICK | 3.91 | 7.82 | 200.07 | 0
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme | SM/07192 | Retrofitting | Construction of Fire hydrant, parking area for water collecting vehicles, surface drain and other miscellaneous works for Madhu T.G. P/W/S/S, Under Alipurduar Division P.H.E. Dte. | HQ-A.E | Birpara Sub Division | ORD/000051/2020-2021 | 530/ALD | 20/08/2020 | 19/10/2020 | TAPASH KUMAR BHOWMICK | 5 | 10 | 199.93 | 0
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme | SM/07192 | Retrofitting | Withdrawing and relaying and laying of UPVC/DI/MS/CI Distribution pipe line and other misc. work for retrofitting of Mujnai PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000144/2020-2021 | 943/ALD | 19/10/2020 | 18/12/2020 | VEDATRAYEE AND CO | 29.81 | 57.1 | 191.54 | 92
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme | SM/07192 | Retrofitting | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under PURBA CHEPANI PWSS, Block- Alipurduar-II, Dist-Alipurduar. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000269/2020-2021 | 1281/ALD | 05/01/2021 | 06/03/2021 | MATRI ENTERPRISE | 37.84 | 2.8 | 7.4 | 94
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Madhu T.G Piped Water Supply Scheme | SM/07192 | Retrofitting | Extension of pipeline to Bharnabari TG area under Hasimara PWSS for providing at Kalchini Block under Alipurduar Division, P.H.E. Dte.(Part-B) |  |  | ORD/000185/2020-2021 | 1010/ALD | 12/11/2020 | 11/01/2021 | ASHIT KUMAR SINGHA | 39.34 | 49.96 | 126.98 | 0
Total | [13 empty] | 121.1 | 137.64 | 113.66