## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti Piped Water Supply Scheme | SM/07193 | Retrofitting | Extension of pipeline for Jainti TG including connection from Reservoir-2 under Jainti TG Water Supply Scheme (Part-A). | Alipurduar Sadar Sub Division,HQ-A.E | Alipurduar Sub Division,RWS Kalchini Block | ORD/000123/2020-2021 | 795/ALD | 01/10/2020 | 30/11/2020 | CALCON CONSTRUCTIONS | 40.62 | 0 | 0 | 90
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti Piped Water Supply Scheme | SM/07193 | Retrofitting | Providing House connection for JAYANTI water supply scheme at KALCHINI Block under Alipuduar Division, P.H.E. Dte.(PART-2) | HQ-A.E | Birpara Sub Division | ORD/000172/2020-2021 | 916/ALD | 16/10/2020 | 15/11/2020 | M/S BHOWMICK CONSTRUCTION | 4.95 | 9.9 | 200 | 0
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti Piped Water Supply Scheme | SM/07193 | Retrofitting | Providing House connection for Bhutia Basty and Jayanti water supply scheme at Kalchini Block under Alipuduar Division, P.H.E. Dte | HQ-A.E | Birpara Sub Division | ORD/000103/2020-2021 | 724/ALD | 22/09/2020 | 22/10/2020 | M/S BHOWMICK CONSTRUCTION | 4.99 | 9.99 | 200 | 0
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti Piped Water Supply Scheme | SM/07193 | Retrofitting | Laying balance portion pipeline and providing house connection at Jayanti Water Supply Scheme and Bhutiya Busty Area under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000202/2021-2022 | 975/ALD | 13/09/2021 | 13/10/2021 | GHOSH & SAHA CONSTRUCTION | 5.04 | 0 | 0 | 54
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti Piped Water Supply Scheme | SM/07193 | Retrofitting | Extension pipeline (HDPE) for providing FHTC at 28th and 29th mile busty area under Jainti Water Supply Scheme, Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,HQ-A.E | Alipurduar Sub Division,RWS Kalchini Block | ORD/000224/2021-2022 | 1576/ALD | 22/11/2021 | 21/01/2022 | DEBAJYOTI SUTRADHAR | 25.75 | 17.07 | 66.28 | 69
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Jayanti Piped Water Supply Scheme | SM/07193 | Retrofitting | Laying of DI/MS/HDPE pipe line and providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-II) |  |  | VCH/000944/2020-2021 | 571/20-21 | 26/03/2021 | 26/03/2021 | PRAMESH LAMA | 10 | 0 | 0 | 0
Total | [13 empty] | 91.36 | 36.96 | 40.46