## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Rahimabad T.G Piped Water Supply Scheme | SM/07196 | Retrofitting | Providing house connection from Rahimabad Water Supply Scheme (Specially for School & FHTC) under Alipurduar Division P.H.E. Dte.Part-4 | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000091/2021-2022 | 890/ALD | 03/09/2021 | 03/10/2021 | SOUVIK ROY PALADHI | 4.3 | 0 | 0 | 71
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Rahimabad T.G Piped Water Supply Scheme | SM/07196 | Retrofitting | LAYING DISTRIBUTION LINE FOR RETROFITTING OF FHTC AT KHASRU LINE UNDER RAHIMABAD TG PWSS UNDER ALIPURDUAR DIVISION, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000032/2021-2022 | 580/ALD | 15/07/2021 | 14/08/2021 | M/S BHOWMICK CONSTRUCTION | 12.75 | 0 | 0 | 71
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Rahimabad T.G Piped Water Supply Scheme | SM/07196 | Retrofitting | Construction of pump house, Boundary Wall, Tube well Boring (ODEX-165 method), rising main of 3rd TW site of Rahimabad WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000347/2022-2023 | 2493/ALD | 13/12/2022 | 12/04/2023 | DULAL DAS | 23.52 | 0 | 0 | 27
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Rahimabad T.G Piped Water Supply Scheme | SM/07196 | Retrofitting | Providing house connection from Rahimabad Water Supply Scheme (Specially for School & FHTC) under Alipurduar Division P.H.E. Dte.Part-3 | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000090/2021-2022 | 889/ALD | 03/09/2021 | 03/10/2021 | POLY CONSTRUCTION | 4.3 | 4.3 | 100 | 0
Total | [13 empty] | 44.87 | 4.3 | 9.58