## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Makrapara T.G Piped Water Supply Scheme | SM/07199 | Retrofitting | Fuel bill for the month of August 2021 |  |  | VCH/000568/2021-2022 | 118/21-22/PFMS | 08/09/2021 | 08/09/2021 | SHIVAM SERVICE STATION | 0.21 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Makrapara T.G Piped Water Supply Scheme | SM/07199 | Retrofitting | Laying of HDPE / DI Pipeline at different area of MAKRAPARA PWSS under Alipurduar Division PHED. | Birpara A.E | Birpara Sub Division | ORD/000070/2020-2021 | 624/ALD | 03/09/2020 | 01/01/2021 | DILIP MAHATO | 14.63 | 4.22 | 28.86 | 84
3 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Makrapara T.G Piped Water Supply Scheme | SM/07199 | Retrofitting | Laying of balance DI/MS/HDPE pipeline for Makrapara WSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000325/2020-2021 | 1457/ALD | 25/01/2021 | 11/03/2021 | DILIP MAHATO | 13.65 | 0 | 0 | 85
4 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Makrapara T.G Piped Water Supply Scheme | SM/07199 | Retrofitting | Laying of distribution of HDPE pipeline and providing FHTC for Garochira area, Makrapara PWSS under Alipurduar Division, PHE DTE. | Birpara A.E | Birpara Sub Division,JUNIOR ENGINEER,RWS Falakata Block | ORD/000478/2021-2022 | 2897/ALD | 08/03/2022 | 07/05/2022 | DILIP MAHATO | 33.9 | 0 | 0 | 42
5 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Makrapara T.G Piped Water Supply Scheme | SM/07199 | Retrofitting | Water supply for Makrapara Kali Mandir at Makarapara within Birpara Sub-Division under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000558/2021-2022 | 3216/ALD | 30/03/2022 | 14/05/2022 | RATAN DUTTA | 4.4 | 0 | 0 | 0
6 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Makrapara T.G Piped Water Supply Scheme | SM/07199 | Retrofitting | Laying of HDPE pipeline near existing PH No-01 village for the Makrapara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000554/2021-2022 | 3046/ALD | 21/03/2022 | 20/04/2022 | DILIP MAHATO | 4.95 | 0 | 0 | 42
7 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Makrapara T.G Piped Water Supply Scheme | SM/07199 | Retrofitting | Construction of Pump House, Boundary Wall, and Tube well Boring by ODEX-195 method of drilling including Rising main for MAKRAPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Birpara A.E | Alipurduar Sub Division | ORD/000398/2021-2022 | 2389/ALD | 31/01/2022 | 01/05/2022 | INDRAYOODH BHOWAL | 27.18 | 0 | 0 | 0
8 | ALIPURDUAR |  | Alipurduar Division | F.H.T.C Under Jaldhara/Jalswapna including retrofitting of existing distribution System under the command area of Makrapara T.G Piped Water Supply Scheme | SM/07199 | Retrofitting | Construction of Balance boundary wall at CWR under Makrapara WSS under Alipurduar Division PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000093/2021-2022 | 892/ALD | 03/09/2021 | 18/10/2021 | DILIP MAHATO | 4.76 | 0 | 0 | 0
Total | [13 empty] | 103.69 | 4.22 | 4.07