## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Laying of Distribution Line (by using metal Pipes) of Zone-I for JDA (Jaigaon Development Authority) Area Water Supply Scheme under Alipurduar District. | HQ-A.E | RWS Kalchini Block | ORD/000118/2020-2021 | 789/ALD | 01/10/2020 | 28/02/2021 | M/S SSB CONSTRUCTION CO. | 185.6 | 22.05 | 11.88 | 65
2 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing House connection for FALAKATA AUG. piped water supply scheme (Falakata-Birpara Road) under Alipuduar Division, P.H.E. Dte. Part-3 | HQ-A.E | RWS Kalchini Block | ORD/000266/2020-2021 | 1257/ALD | 28/12/2020 | 26/02/2021 | BILTU DAS | 43.41 | 33.23 | 76.55 | 70
3 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing House connection for FALAKATA AUG. piped water supply scheme (Barodoba Area) under Alipuduar Division, P.H.E. Dte. Part-1 | HQ-A.E | RWS Kalchini Block | ORD/000263/2020-2021 | 1254/ALD | 28/12/2020 | 26/02/2021 | HARIDAS GHOSH | 43.86 | 74.64 | 170.18 | 66
4 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Sinking of Big Dia T/Well P/House B/Wall & Rising Main of 3rd T/Well Site at FALAKATA Aug. PWSS under Alipurduar Division PHED. | HQ-A.E | RWS Kalchini Block | ORD/000083/2020-2021 | 655/ALD | 08/09/2020 | 06/01/2021 | BILTU DAS | 22.65 | 0 | 0 | 82
5 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing House connection for FALAKATA AUG. piped water supply (Masalapatty area, left side of NH)under Alipuduar Division, P.H.E. Dte. Part-6 | HQ-A.E | RWS Kalchini Block | ORD/000252/2020-2021 | 1252/ALD | 28/12/2020 | 26/02/2021 | SOUVIK ROY PALADHI | 30.05 | 57.06 | 189.87 | 60
6 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing House connection for FALAKATA AUG. piped water supply scheme (Falakata-Dhupguri Road) under Alipuduar Division, P.H.E. Dte. Part-4 | HQ-A.E | RWS Kalchini Block | ORD/000246/2020-2021 | 1246/ALD | 28/12/2020 | 26/02/2021 | TAPASH KUMAR BHOWMICK | 30.04 | 54.27 | 180.67 | 67
7 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing House connection for JOGENDRAPUR water supply scheme at Falakata Block under Alipuduar Division, P.H.E. Dte. Part-III | HQ-A.E | RWS Kalchini Block | ORD/000217/2020-2021 | 1168/ALD | 15/12/2020 | 13/02/2021 | SASANKA ROY | 29.9 | 23.36 | 78.13 | 67
8 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing House connection for FALAKATA AUG. piped water supply scheme (Subhaspally area, right side of NH) under Alipuduar Division, P.H.E. Dte. Part-5 | Alipurduar Sadar Sub Division,HQ-A.E | RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000248/2020-2021 | 1248/ALD | 28/12/2020 | 26/02/2021 | BILTU DAS | 29.59 | 29.5 | 99.69 | 82
9 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing House connection for FALAKATA AUG. piped water supply scheme (College Para Area) under Alipuduar Division, P.H.E. Dte. Part-2 | HQ-A.E | RWS Kalchini Block | ORD/000265/2020-2021 | 1256/ALD | 28/12/2020 | 26/02/2021 | BILTU DAS | 43.41 | 78.8 | 181.55 | 62
10 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Loop Connention between West Falakata & Barodoba area via Mujnai River Bridge incl interconnection with the existing BHUTNIRGHAT PWSS under FALAKATA Aug. PWSS under Alipurduar Division PHED. | HQ-A.E | RWS Kalchini Block | ORD/000072/2020-2021 | 626/ALD | 03/09/2020 | 01/01/2021 | GOUTAM KUMAR DAS | 26.08 | 0 | 0 | 83
11 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing House connection for BHUTNIRGHAT water supply scheme at FALAKATA Block under Alipuduar Division, P.H.E. Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000153/2020-2021 | 865/ALD | 14/10/2020 | 13/11/2020 | GOUTAM KUMAR DAS | 4.98 | 3.68 | 73.9 | 0
12 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Constrcution of Pump House with Sanitary & Plumbing arrangement at 2nd Site (Old) of Dalmore Water supply scheme under Alipurduar Division. P.H.E. Dte. | Birpara A.E | Birpara Sub Division | ORD/000061/2020-2021 | 537/ALD | 20/08/2020 | 18/12/2020 | M/S MONORAMA ENTERPRISE | 4.75 | 8.4 | 177.02 | 0
13 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing House connection for BHUTNIRGHAT water supply scheme at FALAKATA Block under Alipuduar Division, P.H.E. Dte.(PART-2) | Birpara A.E | Alipurduar Sub Division | ORD/000161/2020-2021 | 905/ALD | 16/10/2020 | 15/11/2020 | GOUTAM KUMAR DAS | 4.98 | 9.97 | 200 | 0
14 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing House connection for BANGSHIDHARPUR piped water supply scheme under Alipuduar Division, P.H.E. Dte. Part-1 | Birpara A.E |  | ORD/000247/2020-2021 | 1247/ALD | 28/12/2020 | 26/02/2021 | MESSRS R N TRADERS | 40.06 | 40.06 | 100 | 0
15 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing House connection for BHUTNIRGHAT water supply scheme at Falakata Block under Alipuduar Division, P.H.E. Dte. Part-III | Birpara A.E | Alipurduar Sub Division | ORD/000216/2020-2021 | 1167/ALD | 15/12/2020 | 13/02/2021 | GOUTAM KUMAR DAS | 19.91 | 39.83 | 200 | 0
16 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing House connection for SOUTH FALAKATA AREA, FALAKATA AUG. PWSS ZONE-III under Alipuduar Division, P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000368/2020-2021 | 1761/ALD | 19/02/2021 | 20/04/2021 | HARIDAS GHOSH | 40.13 | 20.44 | 50.92 | 66
17 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing House connection for MADARI ROAD/ PARANGERPAR, FALAKATA AUG. PWSS ZONE-I under Alipuduar Division, P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000365/2020-2021 | 1758/ALD | 19/02/2021 | 20/04/2021 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 39.97 | 48.77 | 122 | 63
18 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing House connection for JAIGAON piped water supply scheme (Old scheme Area) under Alipuduar Division, P.H.E. Dte. Part-2 | HQ-A.E | RWS Kalchini Block | ORD/000318/2020-2021 | 1451/ALD | 25/01/2021 | 11/03/2021 | AQUEDUCT PLASTICS PVT. LTD. | 43.86 | 30 | 68.4 | 90
19 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing Functional Household Tap connection (FHTC) in connection with Jaldhara Jal Sapno for Jogendrapur PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000301/2020-2021 | 1381/ALD | 19/01/2021 | 05/03/2021 | ASSOCIATE CONSTRUCTION COMPANY | 15.78 | 14.66 | 92.93 | 67
20 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Extension and replacement of damaged pipeline including new FHTC under Dakshin Chakoakhati mouza (Sonapur area) at Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS,HQ-A.E | RWS Alipurduar - I Block,RWS Kalchini Block | ORD/000079/2021-2022 | 877/ALD | 03/09/2021 | 02/11/2021 | M/S STAR INDIA CONSTRUCTION | 33.42 | 0 | 0 | 73
21 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Replacement of old existing AC pipeline with UPVC pipe and providing FHTC in connection with Jaldhara/Jal Sapna for Augmentation of Falakata WSS under Alipurduar Division, PHE Dte.( Subhaspally and adjacent area.) | HQ-A.E | RWS Kalchini Block | ORD/000186/2021-2022 | 1314/ALD | 05/10/2021 | 04/12/2021 | SOUVIK ROY PALADHI | 41.3 | 26.04 | 63.07 | 67
22 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing House connection for TORSA TG AREA, JAIGAON DEVLOPMENT AREA ZONE-3B under Alipuduar Division, P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000726/2020-2021 | 1764/ALD | 19/02/2021 | 20/04/2021 | AQUEDUCT PLASTICS PVT. LTD. | 40.17 | 0 | 0 | 67
23 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Road crossing (by NP3 Hume pipe) at Dhupguri Road under under Zone-II of augmentation of Falakata WSS due to widening of PWD Road under Alipurduar Division, PHE Dte. (3 nos) | HQ-A.E | RWS Kalchini Block | ORD/000270/2021-2022 | 1836/ALD | 10/12/2021 | 24/01/2022 | SASANKA ROY | 2.49 | 2.49 | 100 | 67
24 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing House connection for RABINDRANAGAR, FALAKATA AUG. PWSS ZONE-III under Alipuduar Division, P.H.E. Dte. | Birpara A.E | Alipurduar Sub Division,RWS Falakata Block | ORD/000366/2020-2021 | 1759/ALD | 19/02/2021 | 01/10/2024 | BILTU DAS | 39.46 | 30.3 | 76.8 | 86
25 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing House connection for existing PWSS, JAIGAON DEVLOPMENT AREA ZONE- 1 and 2 under Alipurduar Division, P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000382/2020-2021 | 1765/ALD | 19/02/2021 | 20/04/2021 | MAHENDRA CHHETRI | 40.23 | 40.23 | 100 | 63
26 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing House connection for JAIGAON piped water supply scheme (Old scheme Area) under Alipuduar Division, P.H.E. Dte. Part-1 | HQ-A.E | RWS Kalchini Block | ORD/000317/2020-2021 | 1449/ALD | 25/01/2021 | 11/03/2021 | MAHENDRA CHHETRI | 43.86 | 33.73 | 76.91 | 67
27 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing House connection for DESHBANDHUPARA, FALAKATA AUG. PWSS ZONE-III under Alipurduar Division, P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000367/2020-2021 | 1760/ALD | 19/02/2021 | 20/04/2021 | ASHIT KUMAR SINGHA | 40.25 | 40.25 | 100 | 65
28 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Gap filling by UPVC/DI pipe at Parangerpar (near rail gate) of Augmenttion of Falakata WSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000257/2021-2022 | 1604/ALD | 22/11/2021 | 22/12/2021 | ASSOCIATE CONSTRUCTION COMPANY | 4.98 | 5 | 100.34 | 61
29 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Gap filling by UPVC pipe at different zone of Falakata water supply scheme under Alipurduar Division, PHE Dte. Part-4 | HQ-A.E | RWS Kalchini Block | ORD/000396/2020-2021 | 1582/ALD | 10/02/2021 | 11/04/2021 | SWAPAN SAHA | 5.01 | 5.06 | 100.83 | 64
30 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Laying of CI/DI/MS Pipe for Rising and delivery line, cons. Of valve chamber and other allied works for Zone-II and III at JDA (Jaigaon Development Authority) Area Water Supply Scheme under Alipurduar District. | HQ-A.E | RWS Kalchini Block | ORD/000229/2021-2022 | 1572/ALD | 22/11/2021 | 21/01/2022 | DILIP MAHATO | 26.46 | 0 | 0 | 66
31 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Gap filling by UPVC pipe at different zone of Falakata water supply scheme under Alipurduar Division, PHE Dte. Part-5 | HQ-A.E | RWS Kalchini Block | ORD/000397/2020-2021 | 1583/ALD | 10/02/2021 | 11/04/2021 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 5.01 | 5.01 | 100 | 67
32 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Replacement of old existing AC pipeline with UPVC pipe and providing FHTC in connection with Jaldhara/Jal Sapna for Augmentation of Falakata WSS under Alipurduar Division, PHE Dte.( Masterpara, BDO Office and adjacent area.) | HQ-A.E | RWS Kalchini Block | ORD/000083/2021-2022 | 979/ALD | 13/09/2021 | 12/11/2021 | MESSRS R N TRADERS | 40.51 | 38.36 | 94.7 | 67
33 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Construction of gasious chlorine room for Zone-VB of JDA water supply scheme Alipurduar Division PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000285/2020-2021 | 1333/ALD | 11/01/2021 | 11/04/2021 | MAHENDRA CHHETRI | 5 | 0 | 0 | 65
34 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Extension and replacement of damaged pipeline including new FHTC under Dakshin Chakoakhati mouza (Simlabari area) at Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS,HQ-A.E | RWS Alipurduar - I Block,RWS Kalchini Block | ORD/000078/2021-2022 | 876/ALD | 03/09/2021 | 02/11/2021 | M/S AMIT KUMAR GUPTA | 35.43 | 3.03 | 8.55 | 75
35 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Gap filling by UPVC/DI pipe and bridge crossing near Hat Khola Bazar Area for Augmenttion of Falakata WSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000256/2021-2022 | 1603/ALD | 22/11/2021 | 22/12/2021 | NARENDRA BHADANI. | 5 | 4.82 | 96.55 | 67
36 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Laying of CI/DI/MS Pipe for delivery line, cons. of RCC Pillar with ISMB and balance part of boundary wall of CWR Project Area and earth filling at River Bed site of JDA (JAIGAON DEVELOPMENT AUTHORITY) Area Water Supply Scheme under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000013/2021-2022 | 405/ALD | 17/06/2021 | 17/07/2021 | DILIP MAHATO | 49.78 | 4 | 8.04 | 67
37 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Withdrawing and relaying and laying of UPVC/DI/MS/CI Distribution pipe line and other misc. work for interconnection between Jogendrapur and Augmentation of Falakata PWSS under Alipurduar Division, PHE Dte.(Part-II) | Birpara A.E | Birpara Sub Division | ORD/000302/2020-2021 | 1382/ALD | 19/01/2021 | 05/03/2021 | SASANKA ROY | 15.06 | 15.06 | 100 | 100
38 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Construction of gasious chlorine room for Zone-IV of JDA water supply scheme Alipurduar Division PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000281/2020-2021 | 1331/ALD | 11/01/2021 | 11/04/2021 | MAHENDRA CHHETRI | 5 | 0 | 0 | 60
39 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Repairing of drainage system & painting of office cum Godown building at Head Work site of Falakata WSS (OLD) under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000267/2021-2022 | 1832/ALD | 10/12/2021 | 08/02/2022 | NARENDRA BHADANI. | 4.47 | 4.36 | 97.45 | 63
40 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Construction of gasious chlorine room for Zone-IIIB of JDA water supply scheme Alipurduar Division PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000280/2020-2021 | 1330/ALD | 11/01/2021 | 11/04/2021 | MAHENDRA CHHETRI | 5 | 0 | 0 | 67
41 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under BAKLA PWSS, Block- Alipurduar-II, Dist-Alipurduar. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000271/2020-2021 | 1283/ALD | 05/01/2021 | 06/03/2021 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 45.19 | 0.45 | 0.99 | 74
42 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing House connection for JAIGAON DEVLOPMENT AREA ZONE-5B under Alipurduar Division, P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000380/2020-2021 | 1763ALD | 19/02/2021 | 20/04/2021 | AQUEDUCT PLASTICS PVT. LTD. | 40.17 | 40.17 | 100 | 0
43 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Preparation of Agumentation D.P.R after investigation For Kumargram W/Sscheme under Alipurduar Division. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000109/2021-2022 | 912/ALD | 06/09/2021 | 06/10/2021 | BHAGWATI BHUJEL | 2.77 | 2.58 | 93.28 | 0
44 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | PROVIDING FHTC IN CONNECTION WITH JALDHARA JAL SAPNA FOR AUGMENTATION OF FALAKATA WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION, PHE DTE. (COMMAND AREA : OLD OHR) | Birpara A.E | Alipurduar Sub Division | ORD/000031/2021-2022 | 579/ALD | 15/07/2021 | 29/08/2021 | NARENDRA BHADANI. | 21.24 | 35.05 | 165.02 | 0
45 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing House connection for DALSINGPARA, JAIGAON DEVLOPMENT AREA ZONE-5A under Alipurduar Division, P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000379/2020-2021 | 1762ALD | 19/02/2021 | 20/04/2021 | AQUEDUCT PLASTICS PVT. LTD. | 40.17 | 40.17 | 100 | 0
46 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Fuel bill for the month of August 2021 |  |  | VCH/000569/2021-2022 | 120/21-22/PFMS | 08/09/2021 | 08/09/2021 | SHIVAM SERVICE STATION | 0.18 | 0 | 0 | 0
47 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Fuel bill for the month of August 2021 |  |  | VCH/000571/2021-2022 | 122/21-22/PFMS | 08/09/2021 | 08/09/2021 | SHIVAM SERVICE STATION | 0.22 | 0 | 0 | 0
48 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna ( for public/Govt. organisations etc. ) at JDA WSS (Zone-II) under Alipurduar Division, PHE Dte. Part-3 | HQ-A.E | RWS Kalchini Block | ORD/000344/2021-2022 | 2137/ALD | 06/01/2022 | 05/02/2022 | D. K. & SONS | 5.02 | 0 | 0 | 65
49 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Laying of different dia. Of HDPE pipeline inclu. Providing FHTC and other works at JDA PWSS Zone-5A and 5B under JDA PWSS, Kalchini Block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000374/2021-2022 | 2374/ALD | 31/01/2022 | 01/04/2022 | AQUEDUCT PLASTICS PVT. LTD. | 52.63 | 0 | 0 | 80
50 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Laying of different dia. Of HDPE pipeline inclu. Providing FHTC and other works at JDA PWSS Zone-IV under JDA PWSS, Kalchini Block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000373/2021-2022 | 2373/ALD | 31/01/2022 | 01/04/2022 | AQUEDUCT PLASTICS PVT. LTD. | 55.55 | 1.23 | 2.21 | 71
51 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Laying of water Supply pipeline due to widening of Road at industrial park by JDA (Jaigaon Development Authority Area) at Jaigaon Zone-2 WSS under Alipurduar District. | HQ-A.E |  | ORD/000225/2022-2023 | 1115/ALD | 29/07/2022 | 28/08/2022 | D. K. & SONS | 4.84 | 0 | 0 | 0
52 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Laying of UPVC/DI/MS/CI Distribution line for gap filling and FHTC Connection in ward no. 03, 04, 07, 08, 11, 15 location of augmentation of Falakata PWSS (Zone-I AND Zone-III) under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000327/2022-2023 | 2236/ALD/ | 21/11/2022 | 20/01/2023 | NARENDRA BHADANI. | 33.38 | 33.37 | 99.98 | 0
53 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna ( for public/Govt. organisations etc. ) at JDA WSS (Zone-II) under Alipurduar Division, PHE Dte. Part-2 | HQ-A.E | RWS Kalchini Block | ORD/000343/2021-2022 | 2136/ALD | 06/01/2022 | 05/02/2022 | D. K. & SONS | 5.02 | 0 | 0 | 67
54 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Laying of DI pipe line for discharge of washed out water from Tube well No. 1 within Falakata PWSS(Existing) under Alipurduar Division PHED. | HQ-A.E | RWS Kalchini Block | ORD/000404/2021-2022 | 57/PHE-Brp | 03/02/2022 | 05/03/2022 | KANKAN SARKAR | 0.22 | 0 | 0 | 67
55 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Gap filling and culvert crossing along the main road at Zone-II and Zone-I by MS, DI Pipe and other allied works at JDA WSS under Alipurduar Division, PHE Dte | HQ-A.E | RWS Kalchini Block | ORD/000064/2022-2023 | 341/ALD | 02/05/2022 | 16/06/2022 | DILIP MAHATO | 10.82 | 0 | 0 | 63
56 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Installation of 125mm X 80mm X 90 mtr. Deep Tube Well (Mark-II TW) for fresh drinking water sources(with provision of lowering of sub-merssible pump) by ODEX-115 method of Drilling at Truck Stand of Jaigaon PS (East side) within Alipurduar District under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000565/2021-2022 | 3139/ALD | 25/03/2022 | 14/04/2022 | MAHENDRA CHHETRI | 3.32 | 0 | 0 | 67
57 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Construction of roof truss, field development and other allied works at Headwork site of Old Jaigaon WSS under Alipurduar Division, PHE Dte. | Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Kalchini Block | ORD/000393/2021-2022 | 2307/ALD | 25/01/2022 | 24/02/2022 | DILIP MAHATO | 4.17 | 4.14 | 99.16 | 75
58 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Construction of Boundary wall 2nd TW site of Jaigaon PWSS (near Hanuman Mandir) under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000571/2021-2022 | 3144/ALD | 25/03/2022 | 09/05/2022 | D. K. & SONS | 4.75 | 0 | 0 | 62
59 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Preparation of DPR after investigation for Tasti Tea Garden, Dalgaon Tea Garden and Dalmoney Tea Garden Piped Water Supply Scheme under Falakata Block, Alipurduar Division, PHE Dte. | Birpara A.E |  | ORD/000251/2022-2023 | 1392/ALD | 29/08/2022 | 28/09/2022 | M/S SOBHA AND CO | 6.51 | 6.51 | 100 | 100
60 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Construction of pathway with paver block and repairing of old H/W site's Guest House of Jaigaon WSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000570/2021-2022 | 3143/ALD | 25/03/2022 | 24/04/2022 | D. K. & SONS | 4.86 | 0 | 0 | 67
61 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Carrying of AC pipe and DI pipe and specials from Bhutnirghat PWSS to Falakata Stackyard due to widening PWD Road under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000218/2022-2023 | 1108/ALD | 29/07/2022 | 28/08/2022 | SASANKA ROY | 0.92 | 0.92 | 100 | 67
62 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna ( for public/Govt. organisations etc. ) at JDA WSS (Zone-1) under Alipurduar Division, PHE Dte. Part-3 | HQ-A.E | RWS Kalchini Block | ORD/000353/2021-2022 | 2152/ALD | 06/01/2022 | 05/02/2022 | D. K. & SONS | 5.02 | 0 | 0 | 61
63 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Laying of UPVC/DI/MS/CI Distribution pipe line for Gap filling and FHTC connection at different location of AUG. of Falakata PWSS (ZONE -II & III) under Alipurduar Division , PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000074/2022-2023 | 439/ALD | 13/05/2022 | 12/06/2022 | SASANKA ROY | 4.73 | 4.75 | 100.37 | 66
64 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna ( for AWC and school & others) at JDA WSS (Zone-1) under Alipurduar Division, PHE Dte. Part-2 | HQ-A.E | RWS Kalchini Block | ORD/000371/2021-2022 | 2153/ALD | 06/01/2022 | 05/02/2022 | MAHENDRA CHHETRI | 5.02 | 0 | 0 | 66
65 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Laying of UPVC/DI/MS/CI Distribution pipe line for Gap filling and FHTC connection at different location of AUG. of Falakata PWSS (ZONE - I & III) under Alipurduar Division , PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000089/2022-2023 | 453/ALD | 13/05/2022 | 12/06/2022 | NARENDRA BHADANI. | 5.05 | 5.04 | 99.81 | 65
66 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Laying of HDPE pipeline including Providing FHTC at Jaigaon Development Area Zone-II from Krishna Pradhan house to Geeta Chhetri house within Kalchini Block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000196/2022-2023 | 1222/ALD | 10/08/2022 | 09/10/2022 | MAHENDRA CHHETRI | 36.35 | 0 | 0 | 67
67 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Repairing of old UPVC pipe line , FHTC and other misc. work related to FALAKATA PWSS FALAKATA Block under Alipurduar Division , PHE Dte | HQ-A.E | RWS Kalchini Block | ORD/000072/2022-2023 | 437/ALD | 13/05/2022 | 12/06/2022 | NARENDRA BHADANI. | 4.66 | 3.81 | 81.86 | 66
68 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna ( for AWC, school & public/Govt. organisations etc. ) at JDA WSS (Existing) under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000372/2021-2022 | 2154/ALD | 06/01/2022 | 05/02/2022 | MAHENDRA CHHETRI | 5.02 | 0 | 0 | 62
69 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Laying of CI/ DI, HDPE pipe including valve chamber and other misc. works at JDA PWSS ZONE-II under JDA PWSS, Kalchini Block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000500/2021-2022 | 3005/ALD | 15/03/2022 | 14/04/2022 | DILIP MAHATO | 30.59 | 0 | 0 | 60
70 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Installation of rising main with CI/DI pipeline and others misc. works for augmentation of Falakata PWSS (For Old OHR) under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000096/2022-2023 | 460/ALD | 13/05/2022 | 12/06/2022 | ASSOCIATE CONSTRUCTION COMPANY | 5.02 | 5.02 | 100 | 100
71 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Installation of 125mm X 80mm X 90 mtr. Deep Tube Well (Mark-II TW) for fresh drinking water sources(with provision of lowering of sub-merssible pump) by ODEX-115 method of Drilling at Truck Stand of Jaigaon PS (West side) within Alipurduar District under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000566/2021-2022 | 3140/ALD | 25/03/2022 | 14/04/2022 | D. K. & SONS | 3.32 | 0 | 0 | 61
72 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000018/2022-2023 | 917/ALD | 07/07/2022 | 07/07/2022 | Resource Division | 61.6 | 0 | 0 | 0
73 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Remaining portion of pipeline of JDA Zone-I & Zone-II and special Road repairing of Zone-I and II and Zone-4B, providing pipeline and FHTC of Ramgaon. | HQ-A.E | RWS Kalchini Block | ORD/000570/2022-2023 | 3623/ALD | 30/03/2023 | 17/06/2025 | D. K. & SONS | 54.46 | 11.23 | 20.61 | 96
74 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara/Jal Sapna including retrofitting of existing distribution system under the command area of Jaigaon & Falakata water supply scheme. | SM/08080 | Retrofitting | Preparation of detailed Additional cost Requirement D.P.R. booklets in connection to various PWSS under Block Faakata & Madarihat Block under Alipurduar Division P.H.E Dte. | Birpara A.E |  | ORD/000187/2023-2024 | 1205/ALD | 07/08/2023 | 06/09/2023 | ANIK BHATTACHARJEE | 0.78 | 0.78 | 100 | 100
Total | [13 empty] | 1750.45 | 1041.68 | 59.51