## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Alipurduar Division | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. | SM/08580 | New | CONS. OF RESERVOIR (100M3), BOUNDARY WALL (80 m), PUMPHOUSE( 1.Nos) ,TUBEWELL (2 Nos.), RISING MAIN AND DISTRIBUTION LINE FOR MUJNAI T.G (All Other Division & Line 475 unit) CHA SUNDARAI WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION PHE DTE. | Birpara A.E | Alipurduar Sub Division | ORD/000388/2020-2021 | 1947/ALD | 25/02/2021 | 18/05/2023 | BILTU DAS | 113.04 | 82.72 | 73.18 | 80
2 | ALIPURDUAR | Madarihat | Alipurduar Division | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. | SM/08580 | New | CONS. OF BOUNDARY WALL (80 m), PUMPHOUSE( 1.Nos) ,TUBEWELL (2 Nos.), RISING MAIN AND DISTRIBUTION LINE FOR MUJNAI T.G (All Other Division & Line 60 unit) CHA SUNDARI WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION PHE DTE. | Birpara A.E | Alipurduar Sub Division | ORD/000387/2020-2021 | 1946/ALD | 25/02/2021 | 15/06/2023 | GHOSH & SAHA CONSTRUCTION | 36.68 | 22.66 | 61.79 | 100
3 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. | SM/08580 | New | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Mujnai T.G Water Supply scheme T/W No. III under NMD-II,PHE Dte Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000810/2021-2022 | 193/NMD-II | 24/02/2022 | 26/03/2022 | RIPON DAS | 6.83 | 6.83 | 100 | 100
4 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. | SM/08580 | New | Supply, delivery of Electro mechanical components at Mujnai T.G Water Supply Scheme in the dist of ALIPURDUAR under NMD-II PHE Dte Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000871/2021-2022 | 332/NMD-II | 14/03/2022 | 13/04/2022 | SARKAR ELECTRIC | 11.5 | 11.5 | 100 | 27
5 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. | SM/08580 | New | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Mujnai T.G Water Supply scheme T/W No.IV under NMD-II,PHE Dte Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000808/2021-2022 | 191/NMD-II | 24/02/2022 | 26/03/2022 | SUMON ELECTRICAL | 6.86 | 6.86 | 100 | 28
6 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. | SM/08580 | New | Supply, delivery & installation of 10 KVA, Servo Motor operated Copper wound line voltage stabilizer of Mujnai T.G Water Supply Scheme TW No.-III under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000822/2021-2022 | 186/NMD-II | 23/02/2022 | 25/03/2022 | ASHWIRBAD WOOD CRAFT | 1.82 | 1.33 | 72.86 | 27
7 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. | SM/08580 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MUJNAI TG Under CHAA SUNDARI water supply scheme, TW no V under Jal Jeevan Mission under NMD-II, PHE Dte. APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000717/2022-2023 | 2106/NMD-II | 29/12/2022 | 28/01/2023 | MUSTAFI CONCERN | 9.39 | 9.39 | 100 | 28
8 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. | SM/08580 | New | Supply, delivery & installation of 10 KVA, Servo Motor operated Copper wound line voltage stabilizer of Mujnai T.G Water Supply Scheme TW No.-IV under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000786/2021-2022 | 169/NMD-II | 22/02/2022 | 24/03/2022 | WILFUL UNEMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 1.81 | 1.81 | 100 | 28
9 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. | SM/08580 | New | Quotation for new service connection at MUJNAI T.G . P/H no. V, Application no.4002997419 |  |  | VCH/001462/2022-2023 | BP-84/22-23 | 04/11/2022 | 04/11/2022 | WBSEDCL | 1.06 | 0 | 0 | 0
10 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. | SM/08580 | New | Quotation for new service connection at Mujnai TG P/H No-V |  |  | VCH/001441/2022-2023 |  | 02/11/2022 | 02/11/2022 | WBSEDCL | 1.06 | 0 | 0 | 0
11 | ALIPURDUAR | Madarihat | Alipurduar Division | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. | SM/08580 | New | Supply and installation of sign board for different Cha Sundori projects under Madarihat -Birpara Block under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar RWS,Birpara Sub Division | ORD/000397/2023-2024 | 208/ALD | 16/01/2024 | 15/02/2024 | KOUSHIK BHOWMICK | 1.09 | 1.09 | 99.38 | 100
12 | ALIPURDUAR | Madarihat | Alipurduar Division | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. | SM/08580 | New | Cons. of 100 cum OHR,BOUNDARY WALL, PUMP HOUSE, TUBE, RISING MAIN FOR Mouza-MUJNAI TEA GARDEN(JL NO.39,RL Plot No.121,129 &155) 410 unit CHA SUNDARI WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION, PHE DTE. of North Bengal Circle-I, PHE Dte. | Birpara A.E | Alipurduar Sub Division,Birpara Sub Division | ORD/000455/2023-2024 | 436/ALD | 07/02/2024 | 28/11/2025 | MITHUN DAS | 108.05 | 47.88 | 44.31 | 80
13 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. | SM/08580 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Mujnai Water Supply Scheme (Chha Sundari) TW No.-VI under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000504/2024-2025 | 2634/NMD-II | 05/12/2024 | 04/07/2025 | MITRA ENTERPRISE | 10.74 | 0 | 0 | 100
14 | ALIPURDUAR | Madarihat | Alipurduar Division | Supply of potable drinking water to Mujnai Tea Garden in relation with Chaa Sundari Project. | SM/08580 | New | New service connection charges for Mujnai Cha Sundori PH NO-VI under NMD-II |  |  | BILL/00392/2024-2025 | 20249706 | 02/12/2024 | 02/12/2024 | WBSEDCL | 8.09 | 0 | 0 | 0
Total | [13 empty] | 318.02 | 192.06 | 60.39