## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme | SM/08884 | Retrofitting | Extension of pipeline to Bharnabari TG area under Hasimara PWSS for providing at Kalchini Block under Alipurduar Division, P.H.E. Dte.(Part-A) | HQ-A.E | RWS Kalchini Block | ORD/000122/2020-2021 | 794/ALD | 01/10/2020 | 30/11/2020 | TAPASH KUMAR BHOWMICK | 40.85 | 17.5 | 42.84 | 98
2 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme | SM/08884 | Retrofitting | Providing House connection for BAROBISHA ZONE- III water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division,HQ-A.E | Alipurduar Sub Division,RWS Alipurduar - I Block,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000148/2020-2021 | 860/ALD | 14/10/2020 | 13/11/2020 | AKANSHA COMMERCIAL PRIVATE LTD. | 4.98 | 2.15 | 43.21 | 79
3 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme | SM/08884 | Retrofitting | Providing FHTC for Bharnobari / Santali TG area including supply of CI materials and other misc. works under Alipurduar Division, P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000073/2021-2022 | 880/ALD | 03/09/2021 | 02/11/2021 | SOUVIK ROY PALADHI | 30.69 | 19.4 | 63.23 | 95
4 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme | SM/08884 | Retrofitting | Laying Distribution line of UPVC and DI with providing FHTC Connection for the Salkumar Water Supply Scheme Area under Alipurduar Division, PHE Dte. | Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Kalchini Block | ORD/000197/2021-2022 | 1318/ALD | 05/10/2021 | 04/12/2021 | TAPASH KUMAR BHOWMICK | 35.38 | 5.13 | 14.49 | 85
5 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme | SM/08884 | Retrofitting | Construction of Culvert at Hasimara WSS Head Work Site within Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000264/2021-2022 | 1597/ALD | 22/11/2021 | 06/01/2022 | ALATYA CONSTRUCTION & CO. | 4.92 | 4.54 | 92.27 | 98
6 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme | SM/08884 | Retrofitting | PROVIDNG HOUSE CONNECTION FOR BHARNOBARI TG AREA NEAR DALSINGPARA AT KALCHINI BLOCK UNDER ALIPURDUAR DIVISION, PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000034/2021-2022 | 582/ALD | 15/07/2021 | 14/08/2021 | M/S BHOWMICK CONSTRUCTION | 20.03 | 20.03 | 100 | 96
7 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme | SM/08884 | Retrofitting | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Alipurduar - I Block,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 25/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 50 | 9.95 | 100
8 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme | SM/08884 | Retrofitting | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of HASIMARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000294/2021-2022 | 1992/ALD | 27/12/2021 | 27/03/2022 | MAHENDRA CHHETRI | 42.03 | 42.02 | 99.99 | 49
9 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme | SM/08884 | Retrofitting | Providing House connection for KALCHINI water supply scheme at KALCHINI Block under Alipuduar Division, P.H.E. Dte.(Part-3) | HQ-A.E | RWS Kalchini Block | ORD/000327/2020-2021 | 1463/ALD | 25/01/2021 | 24/02/2021 | HARI CONSTRUCTION | 4.98 | 2.15 | 43.2 | 97
10 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme | SM/08884 | Retrofitting | Laying of HDPE pipeline for Malangi Tea Garden Area within Hasimara Water Supply Scheme under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000375/2021-2022 | 2375/ALD | 31/01/2022 | 01/04/2022 | MADHAB SAHA | 74.82 | 69.57 | 92.99 | 94
11 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme | SM/08884 | Retrofitting | Laying of HDPE pipeline for New Hasimara Area within Hasimara Water Supply Scheme under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block,RWS Kumargram Block | ORD/000376/2021-2022 | 2376/ALD | 31/01/2022 | 01/04/2022 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 73.83 | 58.99 | 79.9 | 99
12 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme | SM/08884 | Retrofitting | Providing FHTC at Southern side of Hasimara Piped Water Supply Scheme Under Alipurduar Division, PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000466/2021-2022 | 2811/ALD | 28/02/2022 | 29/04/2022 | MAHENDRA CHHETRI | 34.74 | 31.27 | 90 | 91
13 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme | SM/08884 | Retrofitting | Extension of pipeline from Malangi TW to Bharnobari TG area (booster line) under Hasimara PWSS at Kalchini Block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000025/2022-2023 | 20/ALD | 01/04/2022 | 31/05/2022 | AASHIRBAD ENTERPRISE | 14.64 | 11.92 | 81.39 | 50
14 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme | SM/08884 | Retrofitting | Extension of pipeline from Santali TG connection line to upper line of Madhu TG area (booster line) under Hasimara TG PWSS at Kalchini Block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000024/2022-2023 | 19/ALD | 01/04/2022 | 31/05/2022 | AASHIRBAD ENTERPRISE | 12.61 | 8.47 | 67.18 | 49
15 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme | SM/08884 | Retrofitting | Construction of valve chamber, dismantling concrete road and other misc works at Malangi TG area within Hasimara W/S/S under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000077/2022-2023 | 442/ALD | 13/05/2022 | 12/06/2022 | MADHAB SAHA | 4.9 | 4.55 | 93.01 | 49
16 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme | SM/08884 | Retrofitting | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Hasimara Water Supply Scheme under Alipurduar Division P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000111/2022-2023 | 703/ALD | 08/06/2022 | 08/07/2022 | MADHAB SAHA | 4.84 | 4.84 | 100 | 50
17 | ALIPURDUAR |  | Alipurduar Division | FHTC under Jaldhara Jalswapna Including Retrofitting of existing distribution system under the command area of HASIMARA Water Supply Scheme | SM/08884 | Retrofitting | Providing FHTC at Northern side of Hasimara Piped Water Supply Scheme Under Alipurduar Division, PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000434/2021-2022 | 2714/ALD | 23/02/2022 | 24/04/2022 | ASHIM KUMAR GHOSH | 34.64 | 34.64 | 100 | 49
Total | [13 empty] | 941.47 | 387.18 | 41.13