## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | SM/09884 | Augmentation | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Alipurduar - I Block,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 25/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 50 | 9.95 | 100
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | SM/09884 | Augmentation | Construction of 350cum OHR for Putimari TG Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000312/2021-2022 | 2188/ALD | 11/01/2022 | 16/03/2023 | TAPASH KUMAR BHOWMICK | 71.4 | 53.44 | 74.85 | 95
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | SM/09884 | Augmentation | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Putimari PWSS, Alipurduar Block under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,RWS Alipurduar - II Block | ORD/000364/2021-2022 | 2291/ALD | 24/01/2022 | 08/05/2025 | HARI CONSTRUCTION | 45.52 | 42.55 | 93.48 | 100
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | SM/09884 | Augmentation | Extension of UPVC pipeline for Putimari WSS under Dakshin Dhalkar Mousa under Alipurduar Division, P.H.E. Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000391/2021-2022 | 2305/ALD | 25/01/2022 | 24/02/2022 | PRAPTI DUTTA | 5.04 | 4.55 | 90.28 | 95
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | SM/09884 | Augmentation | Construction of Pump House, Boundary Wall and laying distribution system for PUTIMARI Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000386/2021-2022 | 2386/ALD | 31/01/2022 | 01/05/2022 | TAPASH KUMAR BHOWMICK | 93.77 | 93.18 | 99.37 | 96
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | SM/09884 | Augmentation | New Laying of UPVC/DI pipeline, Providing FHTC and other allied works for Augmentation of Putimari PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,RWS Alipurduar - II Block | ORD/000194/2022-2023 | 1221/ALD | 10/08/2022 | 26/05/2025 | HARI CONSTRUCTION | 38.9 | 25.91 | 66.59 | 100
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | SM/09884 | Augmentation | Extension of UPVC pipeline for Putimari WSS under Putimari Mousa under Alipurduar Division, P.H.E. Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000406/2021-2022 | 2313/ALD | 25/01/2022 | 24/02/2022 | AASHIRBAD ENTERPRISE | 5.04 | 5.04 | 100 | 93
8 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | SM/09884 | Augmentation | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Putimari Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000106/2022-2023 | 698/ALD | 08/06/2022 | 08/07/2022 | TAPASH DAS | 4.83 | 4.83 | 100 | 93
9 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | SM/09884 | Augmentation | Laying of UPVC pipeline and Tube well Boring by ODEX-165 Method of drilling for PUTIMARI Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000387/2021-2022 | 2387/ALD | 31/01/2022 | 01/04/2022 | TAPASH KUMAR BHOWMICK | 76.84 | 75.28 | 97.97 | 97
10 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | SM/09884 | Augmentation | Providing FHTC including Rising main and laying distribution system for PUTIMARI Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000388/2021-2022 | 2388/ALD | 31/01/2022 | 01/04/2022 | HARI CONSTRUCTION | 71.64 | 68.88 | 96.15 | 94
11 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | SM/09884 | Augmentation | Extension of UPVC pipeline for Putimari WSS under Dakshin Shibkata Mousa under Alipurduar Division, P.H.E. Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000390/2021-2022 | 2304/ALD | 25/01/2022 | 24/02/2022 | HARI CONSTRUCTION | 5.05 | 5.05 | 100 | 91
12 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | SM/09884 | Augmentation | Extension of UPVC pipeline for Putimari WSS under Putimari Mousa under Alipurduar Division, P.H.E. Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000405/2021-2022 | 2312/ALD | 25/01/2022 | 24/02/2022 | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 5.04 | 5.04 | 100 | 94
13 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | SM/09884 | Augmentation | Supply & delivery of Desktop CPU-AMD Ryzen5 2400, H320 Gigabyte Mother Board, 8GB DDR4 Ram, ATX Cabinet, SMPS 450 Watt,240 GB SSD,1 TB HDD & Epson printer L-1100 for the use at office of the Assistant Engineer, Alipurduar RWS Sub-Division, P.H.E. Dte. | HQ-A.E |  | ORD/000242/2022-2023 | 1152/ALD | 02/08/2022 | 09/08/2022 | CYBER NET | 0.99 | 0.99 | 100 | 94
14 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | SM/09884 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Putimari Water Supply Scheme TW No.-III under NMD-II,PHE Dte Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000005/2022-2023 | 533/NMD-II | 20/04/2022 | 20/05/2022 | TAPAN BISWAS | 7.83 | 7.72 | 98.57 | 100
15 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | SM/09884 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Putimari Water Supply Scheme TW No.-III under NMD-II,PHE.Dte, Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000916/2021-2022 | 407/NMD-II | 22/03/2022 | 21/04/2022 | MALAY KUMAR SAHA | 2.39 | 2.36 | 98.84 | 100
16 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | SM/09884 | Augmentation | Soil investigation work at 4 different places of Alipurduar District under Alipurduar Division PHE Dte. Part-4 Venue : Putimari 2)Mechpara 3)Mathura 4)Gangutia. | Alipurduar Sadar Sub Division |  | ORD/000362/2021-2022 | 2124/ALD | 05/01/2022 | 04/02/2022 | MABCO CONSULTANT, | 4.86 | 4.86 | 100 | 94
17 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | SM/09884 | Augmentation | Laying Distribution line with UPVC pipe at PUTIMARI WSS under Alipurduar Division , PHE Dte(Part - III) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000069/2022-2023 | 434/ALD | 13/05/2022 | 12/06/2022 | HARI CONSTRUCTION | 5.02 | 4.74 | 94.38 | 93
18 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | SM/09884 | Augmentation | Laying distribution system for Putimari PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000228/2022-2023 | 1104/ALD | 29/07/2022 | 28/08/2022 | HARIDAS GHOSH | 2.92 | 2.92 | 99.95 | 95
19 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | SM/09884 | Augmentation | Extension of UPVC pipeline for Putimari WSS under Uttar Dhalkar Mousa under Alipurduar Division, P.H.E. Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000407/2021-2022 | 2314/ALD | 25/01/2022 | 24/02/2022 | PRAPTI DUTTA | 5.04 | 5.04 | 100 | 92
20 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | SM/09884 | Augmentation | Quotation for new service connection at putimari W/SS TW No III Application No-4002956347 |  |  | VCH/000690/2022-2023 |  | 04/08/2022 | 04/08/2022 | WBSEDCL | 0.87 | 0 | 0 | 0
21 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | SM/09884 | Augmentation | Quotation for new service connection for PUTIMARI (Aug) Application no. 40025956347 |  |  | VCH/001282/2022-2023 | BP-43/22-23 | 08/08/2022 | 08/08/2022 | WBSEDCL | 0.87 | 0 | 0 | 0
22 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | SM/09884 | Augmentation | Supply, delivery of standby Automatically controlled diaphragm type chlorinator for accurate dosing of chlorine solution at Putimari Water Supply Scheme ,in the dist. of COOCHBEHAR under NMD-II, PHE. Dte. Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000792/2022-2023 | 270/NMD-II | 16/02/2023 | 03/03/2023 | DILIP MAHATO | 1.8 | 0 | 0 | 100
23 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | SM/09884 | Augmentation | Providing balance FHTC for Putimari PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000205/2023-2024 | 1558/ALD | 23/08/2023 | 22/09/2023 | HARI CONSTRUCTION | 3.35 | 0 | 0 | 0
24 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PUTIMARI PIPED WATER SUPPLY SCHEME | SM/09884 | Augmentation | Providing FHTC including Rising main and laying distribution system for PUTIMARI Piped Water Supply Scheme Under Alipurduar Division PHE DTE. |  |  | BILL/00602/2023-2024 |  | 29/02/2024 | 29/02/2024 | HARI CONSTRUCTION | 1.21 | 0 | 0 | 0
Total | [13 empty] | 962.8 | 462.38 | 48.02