## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME | SM/09887 | Augmentation | Quotation for new service connection at Hasimara W/SS Tw No-III Application No- 4002954503 |  |  | VCH/000686/2022-2023 |  | 02/08/2022 | 02/08/2022 | WBSEDCL | 1.63 | 0 | 0 | 0
2 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME | SM/09887 | Augmentation | Quotation for new service connection for HASIMARA W/SS T/W no. III , Application no. 4002954503 |  |  | VCH/001279/2022-2023 | BP-40/22-23 | 08/08/2022 | 08/08/2022 | WBSEDCL | 1.63 | 0 | 0 | 0
3 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME | SM/09887 | Augmentation | Quotation for new service connection at Hasimara W/SS Tw No-IV Application No- 4002954692 |  |  | VCH/000685/2022-2023 |  | 02/08/2022 | 02/08/2022 | WBSEDCL | 1.63 | 0 | 0 | 0
4 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME | SM/09887 | Augmentation | Quotation for new connection service connection at HASIMARA W/SS T/W no. IV ,Application no.4002954692 |  |  | VCH/001278/2022-2023 | BP-39/22-23 | 08/08/2022 | 08/08/2022 | WBSEDCL | 1.63 | 0 | 0 | 0
5 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME | SM/09887 | Augmentation | Laying of HDPE pipeline for Malangi Tea Garden Area within Hasimara Water Supply Scheme under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000375/2021-2022 | 2375/ALD | 31/01/2022 | 01/04/2022 | MADHAB SAHA | 74.82 | 5.1 | 6.82 | 94
6 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME | SM/09887 | Augmentation | Extension of pipeline from Malangi TW to Bharnobari TG area (booster line) under Hasimara PWSS at Kalchini Block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000025/2022-2023 | 20/ALD | 01/04/2022 | 31/05/2022 | AASHIRBAD ENTERPRISE | 14.64 | 0 | 0 | 50
7 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME | SM/09887 | Augmentation | Supply, delivery & installation of 30 KVA, Servo Motor operated Copper wound line voltage stabilizer of Hasimara Water Supply scheme T/W No.III NMD-II, PHE. Dte, Alipurduar. |  |  | ORD/000917/2021-2022 | 408/NMD-II | 22/03/2022 | 21/04/2022 | MAA TARA ENTERPRISE | 3.16 | 3.16 | 100 | 0
8 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME | SM/09887 | Augmentation | Supply, delivery & installation of Electro Mechanical Compopnents at HASIMARA W/S Scheme, P/H No. I(Handedover), under NMD-II, PHE, Dte. in the dist of Alipurduar. |  |  | ORD/000360/2022-2023 | 243/AMSD | 29/07/2022 | 13/08/2022 | S.K ELECTRICALS | 1.06 | 0 | 0 | 0
9 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME | SM/09887 | Augmentation | "Hiring of Motor Cab for site visit of the Assistant Engineer , Alipurduar Mechanical Sub- Division, P.H.E. Dte. under Northern Mechanical Division -II, P.H.E. Dte." |  |  | ORD/000695/2023-2024 | 202/AMSD | 28/07/2023 | 28/07/2024 | DILIP MAHATO | 4.16 | 0 | 0 | 0
10 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME | SM/09887 | Augmentation | Extension of pipeline from Santali TG connection line to upper line of Madhu TG area (booster line) under Hasimara TG PWSS at Kalchini Block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000024/2022-2023 | 19/ALD | 01/04/2022 | 31/05/2022 | AASHIRBAD ENTERPRISE | 12.61 | 0 | 0 | 49
11 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME | SM/09887 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Hasimara Water Supply Scheme TW No.-III under NMD-II,PHE Dte Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000006/2022-2023 | 534/NMD-II | 20/04/2022 | 20/05/2022 | M/S RATAN KUMAR DASGUPTA & CO. | 8.46 | 7.95 | 93.92 | 100
12 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME | SM/09887 | Augmentation | Construction of valve chamber, dismantling concrete road and other misc works at Malangi TG area within Hasimara W/S/S under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000077/2022-2023 | 442/ALD | 13/05/2022 | 12/06/2022 | MADHAB SAHA | 4.9 | 0 | 0 | 49
13 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME | SM/09887 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Hasimara Water Supply Scheme TW No.-IV under NMD-II PHE Dte Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000013/2022-2023 | 595/NMD-II | 05/05/2022 | 04/06/2022 | M/S B ENTERPRISE | 8.49 | 7.98 | 93.93 | 100
14 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME | SM/09887 | Augmentation | Supply, delivery & installation of 30 KVA, Servo Motor operated Copper wound line voltage stabilizer of HASIMARA Water Supply Scheme TW No.- IV under NMD-II, PHE. Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000882/2021-2022 | 400/NMD-II | 22/03/2022 | 21/04/2022 | M/S A.D. ENTERPRISE | 3.17 | 3.17 | 100 | 0
15 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME | SM/09887 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of HASIMARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000294/2021-2022 | 1992/ALD | 27/12/2021 | 27/03/2022 | MAHENDRA CHHETRI | 42.03 | 0 | 0 | 49
16 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME | SM/09887 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2022-2023 | 717/ALD | 13/06/2022 | 13/06/2022 | Resource Division | 49.83 | 0 | 0 | 0
17 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME | SM/09887 | Augmentation | Construction of HP Culvert for drainage purpose with 900 mm dia humepipe and construction of screening and inspection chamber at Hasimara PWSS HWS under Alipurduar Division PHE Dte.,Part-B | Alipurduar Sadar Sub Division,HQ-A.E | Birpara Sub Division | ORD/000215/2022-2023 | 1105/ALD | 29/07/2022 | 28/08/2022 | ALATYA CONSTRUCTION & CO. | 3.6 | 0 | 0 | 100
18 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME | SM/09887 | Augmentation | Construction of HP Culvert for drainage purpose with 900 mm dia humepipe and construction of screening and inspection chamber at Hasimara PWSS HWS under Alipurduar Division PHE Dte., Part-C | Alipurduar Sadar Sub Division,HQ-A.E | Birpara Sub Division | ORD/000216/2022-2023 | 1106/ALD | 29/07/2022 | 28/08/2022 | ALATYA CONSTRUCTION & CO. | 4.08 | 0 | 0 | 100
19 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME | SM/09887 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000083/2023-2024 | 107/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 12.32 | 0 | 0 | 0
20 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF HASIMARA WATER SUPPLY SCHEME | SM/09887 | Augmentation | Laying of DI pipe and connection with Tubewell, Construction of Pathway, Fencing work and other works at Malangi TG Pump House under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kumargram Block | ORD/000220/2022-2023 | 1110/ALD | 29/07/2022 | 14/04/2025 | MAHENDRA CHHETRI | 4.99 | 0 | 0 | 100
Total | [13 empty] | 258.85 | 27.35 | 10.57