## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF 'BANCHUKAMARI WATER SUPPLY SCHEME' | SM/09891 | Augmentation | Quotation for new service connection at banchukamari W/SS TW No-III, Application No-4002956342 |  |  | VCH/000689/2022-2023 | null | 04/08/2022 |  | WBSEDCL | 0.87 | 0 | 0 | 0
2 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF 'BANCHUKAMARI WATER SUPPLY SCHEME' | SM/09891 | Augmentation | Quotation for new service connection for BANCHUKAMARI T/W no. III Application no. 4002956342 |  |  | VCH/001289/2022-2023 | BP-44/22-23 | 08/08/2022 |  | WBSEDCL | 0.87 | 0 | 0 | 0
3 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF 'BANCHUKAMARI WATER SUPPLY SCHEME' | SM/09891 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of BANCHUKAMARI Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000315/2021-2022 | 2191/ALD | 11/01/2022 | 11/04/2022 | HITANGSHU CHOUDHURY | 21.92 | 0 | 0 | 56.33
4 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF 'BANCHUKAMARI WATER SUPPLY SCHEME' | SM/09891 | Augmentation | Extension and replacement of damaged pipeline and providing FHTC at Satkodali and surrounding area of Banchukamari PWSS. Alipurduar-I Block under Alipurduar Division, PHE Dte | Alipurduar RWS | Birpara Sub Division | ORD/000377/2021-2022 | 2377/ALD | 31/01/2022 | 01/04/2022 | MATRI ENTERPRISE | 56.5 | 10.74 | 19.02 | 0
5 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF 'BANCHUKAMARI WATER SUPPLY SCHEME' | SM/09891 | Augmentation | Supply, installation, commissioning of 15KVA copper wound line voltage corrector for BANCHUKAMARI water supply scheme TW no- III under JJM under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/002081/2023-2024 | 1207/NMD-II | 13/03/2024 | 12/04/2024 | D.K AND SONS | 2.39 | 1.19 | 49.85 | 100
6 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF 'BANCHUKAMARI WATER SUPPLY SCHEME' | SM/09891 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Banchukamari Water Supply Scheme TW No.-III under NMD-II,PHE.Dte Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000002/2022-2023 | 527/NMD-II | 19/04/2022 | 19/05/2022 | B.B CONCERNED | 7.75 | 6.77 | 87.34 | 100
Total | [13 empty] | 90.29 | 18.7 | 20.71