## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF 'PURBA CHEPANI WATER SUPPLY SCHEME' | SM/09893 | Augmentation | Construction of pump House, boundary wall, laying of UPVC pipe linr & Rising main connection for Purba Chepani PWSS proposed 4th TW SITE under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000519/2022-2023 | 3494/ALD | 23/03/2023 | 21/06/2023 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 41.66 | 20.16 | 48.39 | 48
2 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF 'PURBA CHEPANI WATER SUPPLY SCHEME' | SM/09893 | Augmentation | New Laying of UPVC/DI pipeline, Providing FHTC and other allied works for Augmentation of Purba Chepani PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000193/2022-2023 | 1220/ALD | 10/08/2022 | 09/10/2022 | SREE MAA CONSTRUCTION | 21.55 | 0 | 0 | 94
3 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF 'PURBA CHEPANI WATER SUPPLY SCHEME' | SM/09893 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Purba Chenpani Water Supply Scheme TW No.-III under NMD-II PHE Dte Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000769/2021-2022 | 1379/NMD-II | 22/12/2021 | 21/01/2022 | TAPAN BISWAS | 2.39 | 2.37 | 99.05 | 0
4 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF 'PURBA CHEPANI WATER SUPPLY SCHEME' | SM/09893 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Purba Chenpani Water Supply Scheme TW No.-III under NMD-II,PHE Dte Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000753/2021-2022 | 63/NMD-II | 21/01/2022 | 20/02/2022 | M/S KUNDU CONSTRUCTION | 7.75 | 7.73 | 99.77 | 0
Total | [13 empty] | 73.35 | 30.26 | 41.25