## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | Rejuvenation of Makrapara TG WSS. | SM/09895 | Augmentation | Shifting of pipeline along the road of Birpara-Makrapara Gomtu Road under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000447/2021-2022 | 2654/ALD | 21/02/2022 | 23/03/2022 | DILIP MAHATO | 3.62 | 3.11 | 85.91 | 0
2 | ALIPURDUAR |  | Alipurduar Division | Rejuvenation of Makrapara TG WSS. | SM/09895 | Augmentation | Laying of HDPE pipeline near existing PH No-01 village for the Makrapara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000554/2021-2022 | 3046/ALD | 21/03/2022 | 20/04/2022 | DILIP MAHATO | 4.95 | 0 | 0 | 42
3 | ALIPURDUAR |  | Alipurduar Division | Rejuvenation of Makrapara TG WSS. | SM/09895 | Augmentation | Construction of Pump House, Boundary Wall, and Tube well Boring by ODEX-195 method of drilling including Rising main for MAKRAPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Birpara A.E | Alipurduar Sub Division | ORD/000398/2021-2022 | 2389/ALD | 31/01/2022 | 01/05/2022 | INDRAYOODH BHOWAL | 27.18 | 23.11 | 85.03 | 0
4 | ALIPURDUAR |  | Northern Mechanical Division II | Rejuvenation of Makrapara TG WSS. | SM/09895 | Augmentation | Quotation for new service connection at Makrapara TW No- IV |  |  | BILL/00041/2022-2023 | BP-130/22-23 | 13/01/2023 | 13/01/2023 | WBSEDCL | 1.49 | 0 | 0 | 0
5 | ALIPURDUAR |  | Northern Mechanical Division II | Rejuvenation of Makrapara TG WSS. | SM/09895 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Rejuvenation of Makrapara TG Water Supply Scheme TW No.-I under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000808/2022-2023 | 415/NMD-II | 24/02/2023 | 26/03/2023 | BONANZA ENTERPRISE | 15.21 | 15.1 | 99.29 | 100
6 | ALIPURDUAR |  | Alipurduar Division | Rejuvenation of Makrapara TG WSS. | SM/09895 | Augmentation | Laying of distribution of HDPE pipeline and providing FHTC for Garochira area, Makrapara PWSS under Alipurduar Division, PHE DTE. | Birpara A.E | Birpara Sub Division,JUNIOR ENGINEER,RWS Falakata Block | ORD/000478/2021-2022 | 2897/ALD | 08/03/2022 | 07/05/2022 | DILIP MAHATO | 33.9 | 0 | 0 | 45
Total | [13 empty] | 86.35 | 41.33 | 47.86