## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME | SM/09898 | Augmentation | Construction of Pump House Boundary Wall Land development & pathway TW Boring (2nd Suite of OHR-1 ODEX 165) Raising Main for Jainti TG PWSS at Kumargram under Alipurduar Division. | HQ-A.E | RWS Kalchini Block | ORD/000335/2019-2020 | 2020/ALD | 20/03/2020 | 20/03/2020 | DAS CONSTRUCTION | 17.19 | 4.28 | 24.89 | 0
2 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME | SM/09898 | Augmentation | Extension pipeline (HDPE) for providing FHTC at 28th and 29th mile busty area under Jainti Water Supply Scheme, Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,HQ-A.E | Alipurduar Sub Division,RWS Kalchini Block | ORD/000224/2021-2022 | 1576/ALD | 22/11/2021 | 21/01/2022 | DEBAJYOTI SUTRADHAR | 25.75 | 1.06 | 4.14 | 69
3 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME | SM/09898 | Augmentation | Supply, Delivery and laying of Al. Ar cable for yard Lighting arrangement at jayanti Bungalow in the dist. Of Alipurduar under NMD-II ,P.H.E Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000716/2021-2022 | 1385/NMD-II | 22/12/2021 | 21/01/2022 | MUSTAFI CONCERN | 4.7 | 4.16 | 88.6 | 0
4 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME | SM/09898 | Augmentation | Supplying and delivery and fitting fixing of different outdoor decorative lighting fixture in front of new building at Jayanti bunglow in the dist. Of Alipurduar under NMD-II ,P.H.E Dte | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000761/2021-2022 | 1376/NMD-II | 22/12/2021 | 21/01/2022 | MUSTAFI CONCERN | 4.38 | 4.38 | 100 | 0
5 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME | SM/09898 | Augmentation | Supplying and delivery and fitting fixing of different outdoor decorative lighting fixture infront of new building at Jayanti bungalow in the district of Alipurduar under NMD-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000023/2022-2023 | 622/NMD-II | 13/05/2022 | 12/06/2022 | MUSTAFI CONCERN | 3.74 | 3.74 | 100 | 54
6 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME | SM/09898 | Augmentation | Laying balance portion pipeline and providing house connection at Jayanti Water Supply Scheme and Bhutiya Busty Area under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000202/2021-2022 | 975/ALD | 13/09/2021 | 13/10/2021 | GHOSH & SAHA CONSTRUCTION | 5.04 | 5.03 | 99.86 | 54
7 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME | SM/09898 | Augmentation | Tube well Boring by ODEX-195 method of drilling including Rising main for JAYANTI Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000401/2021-2022 | 2392/ALD | 31/01/2022 | 01/05/2022 | TAPASH KUMAR BHOWMICK | 12.78 | 11.81 | 92.39 | 44
8 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME | SM/09898 | Augmentation | Upgradation of Internal illumination system and allied works at Newly Constructed Rest Shed in Jayanti under Jayanti W/S Scheme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000720/2022-2023 | 45/NMD-II | 04/01/2023 | 03/02/2023 | ALPHA ENTERPRISE | 4.03 | 2.72 | 67.47 | 100
9 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME | SM/09898 | Augmentation | Extension pipeline (HDPE) for providing FHTC at Santalbari area under Jainti Water Supply Scheme, Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,HQ-A.E | Alipurduar Sub Division,RWS Kalchini Block | ORD/000222/2021-2022 | 1619/ALD | 23/11/2021 | 22/01/2022 | M/S BHOWMICK CONSTRUCTION | 24.53 | 0 | 0 | 60
10 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME | SM/09898 | Augmentation | Laying of HDPE pipeline & other misc work related to Jayanti WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,HQ-A.E | Alipurduar Sub Division,RWS Kalchini Block | ORD/000354/2021-2022 | 2119/ALD | 05/01/2022 | 04/02/2022 | TAPASH KUMAR BHOWMICK | 4.28 | 0 | 0 | 71
11 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME | SM/09898 | Augmentation | Supply ,delivery and Installation of pumping machinery of at newly constructed tubewell at Jayanti ,in the dist. Alipurduar , AMSD ,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000758/2021-2022 | 259/AMSD | 23/07/2021 | 07/08/2021 | MUSTAFI CONCERN | 0.96 | 0 | 0 | 0
12 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF JAYANTI WATER SUPPLY SCHEME | SM/09898 | Augmentation | Balance work of Jainty Rest Shed along with laying of delivery line from CWR of Jainti WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,HQ-A.E | Alipurduar Sub Division,RWS Kalchini Block | ORD/000431/2021-2022 | 2629/ALD | 18/02/2022 | 19/04/2022 | GHOSH & SAHA CONSTRUCTION | 13.4 | 1.53 | 11.4 | 64
Total | [13 empty] | 120.78 | 38.71 | 32.05