## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF 'PASCHIM KHAIRBARI WATER SUPPLY SCHEME' | SM/09900 | Augmentation | Supply, delivery & installation of Electro Mechanical Compopnents at PASCHIM KHAIRBARI W/S Scheme, T.W No. I (Replacement), under NMD-II, PHE, Dte. in the dist of Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000311/2022-2023 | 638/NMD-II | 20/05/2022 | 19/06/2022 | ALPHA ENTERPRISE | 2.87 | 2.87 | 100 | 0
2 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF 'PASCHIM KHAIRBARI WATER SUPPLY SCHEME' | SM/09900 | Augmentation | Laying of pipeline distribution system (Parallel and left out area) and other allied works at Paschim khairbari PWSS under Madarihat-Birpara Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000219/2025-2026 | 2921/ALD | 29/01/2026 | 14/04/2026 | GIRIRAJ ENTERPRISE | 24.6 | 0 | 0 | 0
Total | [13 empty] | 27.48 | 2.87 | 10.46