## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | REJUVINATION OF ' UTTAR MADARIHAT WATER SUPPLY SCHEME' | SM/09902 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of UTTAR MADARIHAT Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Birpara A.E | Alipurduar Sub Division | ORD/000322/2021-2022 | 2198/ALD | 11/01/2022 | 11/04/2022 | DILIP MAHATO | 20.99 | 15.11 | 71.98 | 72
2 | ALIPURDUAR |  | Alipurduar Division | REJUVINATION OF ' UTTAR MADARIHAT WATER SUPPLY SCHEME' | SM/09902 | Augmentation | Replacement of damaged pipeline in Madarihat Bazar Area PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000043/2023-2024 | 389/ALD | 19/05/2023 | 15/11/2023 | KAMALESH ROY | 5.46 | 4.63 | 84.81 | 95
3 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVINATION OF ' UTTAR MADARIHAT WATER SUPPLY SCHEME' | SM/09902 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvenation of Uttar Madarihat water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000857/2023-2024 | 2435/NMD-II | 11/08/2023 | 10/09/2023 | TALUKDAR ENTERPRISE | 12.13 | 9.63 | 79.38 | 100
4 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVINATION OF ' UTTAR MADARIHAT WATER SUPPLY SCHEME' | SM/09902 | Augmentation | New service connection charges for UTTAR MADARIHAT PWSS PH NO-III |  |  | BILL/02732/2023-2024 | BP-2023-24-623 | 20/02/2024 | 20/02/2024 | WBSEDCL | 7.47 | 0 | 0 | 0
5 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVINATION OF ' UTTAR MADARIHAT WATER SUPPLY SCHEME' | SM/09902 | Augmentation | ADDITIONAL QUOTATION FOR AUGUMANTION OF MADHARIHAT |  |  | BILL/00174/2024-2025 | BP-41/24-25 | 26/04/2024 | 26/04/2024 | WBSEDCL | 0.58 | 0 | 0 | 0
Total | [13 empty] | 46.64 | 29.37 | 62.98