## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF CHOTO SALKUMAR WATER SUPPLY SCHEME | SM/09903 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna ( for AWC and school & others) at Chhoto Salkumar WSS under Alipurduar Division, PHE Dte.Part-5 | Birpara A.E | Birpara Sub Division | ORD/000389/2021-2022 | 2303/ALD | 25/01/2022 | 24/02/2022 | AASHIRBAD ENTERPRISE | 5.03 | 0 | 0 | 61
2 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF CHOTO SALKUMAR WATER SUPPLY SCHEME | SM/09903 | Augmentation | Laying distribution line of UPVC and providing FHTC connection for Chhoto Salkumar Water Supply Scheme Area under Alipurduar Division, P.H.E. Dte. | Birpara A.E | Birpara Sub Division | ORD/000397/2021-2022 | 2311/ALD | 25/01/2022 | 11/03/2022 | AASHIRBAD ENTERPRISE | 5.01 | 0 | 0 | 62
3 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF CHOTO SALKUMAR WATER SUPPLY SCHEME | SM/09903 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of CHHOTO SALKUMAR Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Birpara A.E | Birpara Sub Division | ORD/000318/2021-2022 | 2194/ALD | 11/01/2022 | 11/04/2022 | KAJAL KUMAR DE | 21.92 | 14.23 | 64.92 | 46
4 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF CHOTO SALKUMAR WATER SUPPLY SCHEME | SM/09903 | Augmentation | Providing FHTC at surrounding area of Chhoto Salkumar Under Alipurduar Division, PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000445/2021-2022 | 2754/ALD | 24/02/2022 | 25/04/2022 | KAJAL KUMAR DE | 34.67 | 3.29 | 9.5 | 45
5 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF CHOTO SALKUMAR WATER SUPPLY SCHEME | SM/09903 | Augmentation | Laying of UPVC/DI/MS/CI distribution pipeline for Gap filling of Chhoto Salkumar PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000577/2021-2022 | 3132/ALD | 25/03/2022 | 24/04/2022 | PRITAM DAS | 5.04 | 0.82 | 16.24 | 71
6 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF CHOTO SALKUMAR WATER SUPPLY SCHEME | SM/09903 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVINATION OF CHOTO SALKUMAR water supply scheme, TW no III under Jal Jeevan Mission under NMD-II, PHE Dte. APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000852/2022-2023 | 635/NMD-II | 22/03/2023 | 21/04/2023 | PRAGATI CONSTRUCTION COMPANY | 10.86 | 7.93 | 73.06 | 100
7 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF CHOTO SALKUMAR WATER SUPPLY SCHEME | SM/09903 | Augmentation | Laying Distribution line of UPVC and DI with providing FHTC Connection for the Salkumar and Munshipara Water Supply Scheme Area under Alipurduar Division, PHE Dte. | Alipurduar RWS,Birpara A.E | Birpara Sub Division,RWS Alipurduar - I Block,RWS Madarihat - Birpara Block | ORD/000196/2021-2022 | 1317/ALD | 05/10/2021 | 12/01/2026 | DILIP MAHATO | 58.07 | 0 | 0 | 85
8 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF CHOTO SALKUMAR WATER SUPPLY SCHEME | SM/09903 | Augmentation | Supply & delivery of Stand by pumping machinery for Choto Salkumar water supply scheme, P/H No. II under JJM project in the dist. of Alipurduar under NMD-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000003/2024-2025 | 179/AMSD | 02/04/2024 | 17/04/2024 | M/S RATAN KUMAR DASGUPTA & CO. | 0.77 | 0 | 0 | 100
9 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF CHOTO SALKUMAR WATER SUPPLY SCHEME | SM/09903 | Augmentation | Supply & delivery of Stand by pumping machinery for Choto Salkumar water supply scheme, P/H No. I under JJM project in the dist. of Alipurduar under NMD-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/002320/2023-2024 | 127/AMSD | 05/03/2024 | 20/03/2024 | CHOWDHURY AND BASU ENTERPRISE | 0.77 | 0 | 0 | 100
Total | [13 empty] | 142.12 | 26.27 | 18.49