## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF 'LOKNATHPUR WATER SUPPLY SCHEME' | SM/09905 | Augmentation | Supply, installation, commissioning and Trial operation of Electro Mechanical components of LOKNATHPUR Water Supply Scheme TW No.-IV (NEAR DANGI AREA)under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000012/2020-2021 | 1034/NMD-II | 03/09/2020 | 02/12/2020 | SUBODH KUMAR BANIK | 6.41 | 0 | 0 | 0
2 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF 'LOKNATHPUR WATER SUPPLY SCHEME' | SM/09905 | Augmentation | Quotation for new service connection at Loknathpur W/SS Application No-4002937212 |  |  | VCH/000643/2022-2023 |  | 14/07/2022 | 14/07/2022 | WBSEDCL | 0.87 | 0 | 0 | 0
3 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF 'LOKNATHPUR WATER SUPPLY SCHEME' | SM/09905 | Augmentation | Quotation for Loknath pur w/s scheme T/W no. Y, under NMD-II PHE Dte. application no. 4002937212( New Connection) Ref no. 402828607 |  |  | VCH/001057/2022-2023 | BP-37/22-23 | 08/08/2022 | 08/08/2022 | WBSEDCL | 0.87 | 0 | 0 | 0
4 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF 'LOKNATHPUR WATER SUPPLY SCHEME' | SM/09905 | Augmentation | Quotation for new service connection at Loknathpur W/SS TW No-V Application No-4002937212 |  |  | VCH/000641/2022-2023 |  | 14/07/2022 | 14/07/2022 | WBSEDCL | 0.87 | 0 | 0 | 0
5 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF 'LOKNATHPUR WATER SUPPLY SCHEME' | SM/09905 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Loknathpur WSS under Alipurduar Division, PHE Dte. Part-5 | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000282/2021-2022 | 1851/ALD | 13/12/2021 | 12/01/2022 | GOUTAM KUMAR DAS | 5.04 | 0 | 0 | 63
6 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF 'LOKNATHPUR WATER SUPPLY SCHEME' | SM/09905 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of LOKNATHPUR Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000319/2021-2022 | 2195/ALD | 11/01/2022 | 11/04/2022 | GOUTAM KUMAR DAS | 20.89 | 0 | 0 | 0
7 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF 'LOKNATHPUR WATER SUPPLY SCHEME' | SM/09905 | Augmentation | Balance work of construction of boundary wall (2nd site) at Loknathpur WSS under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division |  | ORD/000484/2021-2022 | .2657/ALD | 21/02/2022 | 07/04/2022 | GOUTAM KUMAR DAS | 4.47 | 0 | 0 | 0
8 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF 'LOKNATHPUR WATER SUPPLY SCHEME' | SM/09905 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Loknathpur Water Supply Scheme TW No.- V under NMD-II, PHE. Dte, Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000927/2021-2022 | 410/NMD-II | 22/03/2022 | 21/04/2022 | MITRA ENTERPRISE | 2.39 | 2.38 | 99.61 | 0
9 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF 'LOKNATHPUR WATER SUPPLY SCHEME' | SM/09905 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Loknathpur water supply scheme TW No. V under NMD-II, PHE Dte. Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000008/2022-2023 | 556/NMD-II | 26/04/2022 | 26/05/2022 | S.S ENTERPRISES | 7.85 | 7.75 | 98.72 | 100
Total | [13 empty] | 49.66 | 10.13 | 20.4