## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Northern Mechanical Division II | Rejuvenation of Gargenda Tea Garden Water Supply Scheme | SM/09906 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Gargenda TG water supply scheme, TW no IV in the district of Alipurduar under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000833/2022-2023 | 519/NMD-II | 14/03/2023 | 13/04/2023 | DEY ENTERPRISE (BALLY) | 13.6 | 13.46 | 98.92 | 90
2 | ALIPURDUAR |  | Northern Mechanical Division II | Rejuvenation of Gargenda Tea Garden Water Supply Scheme | SM/09906 | Augmentation | Quotation for new service connection at Gargenda TG TW No- IV |  |  | BILL/00042/2022-2023 | BP-139/22-23 | 23/02/2023 | 23/02/2023 | WBSEDCL | 1.49 | 0 | 0 | 0
Total | [13 empty] | 15.09 | 13.46 | 89.18