## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF SALSALABARI WATER SUPPLY SCHEME | SM/09907 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Salsalabari Water Supply Scheme TW No.-III under NMD-II,PHE. Dte, Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000724/2021-2022 | 1377/NMD-II | 22/12/2021 | 21/01/2022 | PRAGATI CONSTRUCTION COMPANY | 2.39 | 2.39 | 100 | 0
2 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF SALSALABARI WATER SUPPLY SCHEME | SM/09907 | Augmentation | Construction of pumphouse, boundary wall,laying of UPVC pipeline & rising main connection for Salsalabari PWSS proposed 4th TW site PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000515/2022-2023 | 3400/ALD | 16/03/2023 | 14/06/2023 | BRAJA GOPAL SAHA | 39.58 | 0 | 0 | 0
Total | [13 empty] | 41.98 | 2.39 | 5.7