## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF 'TAPSHIKHATA WATER SUPPLY SCHEME' | SM/09908 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of TAPSHIKHATA Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000321/2021-2022 | 2197/ALD | 11/01/2022 | 11/04/2022 | DEBABRATA DUTTA | 21.58 | 0 | 0 | 68.67
2 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF 'TAPSHIKHATA WATER SUPPLY SCHEME' | SM/09908 | Augmentation | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Tapshikhata PWSS Under Alipurduar Division, PHE DTE. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000442/2021-2022 | 2750/ALD | 24/02/2022 | 25/04/2022 | AMBITIOUS ENTERPRISE | 36.94 | 15.64 | 42.32 | 68
3 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF 'TAPSHIKHATA WATER SUPPLY SCHEME' | SM/09908 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Tapshikhata WSS under Alipurduar Division, PHE Dte. Part-5 | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000349/2021-2022 | 2142/ALD | 06/01/2022 | 05/02/2022 | DEBAJYOTI SUTRADHAR | 5.02 | 0 | 0 | 52.25
4 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF 'TAPSHIKHATA WATER SUPPLY SCHEME' | SM/09908 | Augmentation | Supply, delivery of Standby PDB Cum MCC Panel and Submersible pumping machinery under Rejuvination of Tapshikhata water supply scheme under NMD-II,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000735/2022-2023 | 93/NMD-II | 10/01/2023 | 25/01/2023 | ALPHA ENTERPRISE | 4.86 | 4.7 | 96.68 | 55
5 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF 'TAPSHIKHATA WATER SUPPLY SCHEME' | SM/09908 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT TAPSHIKHATA PH NO III |  |  | BILL/00379/2023-2024 | BP-2023-24-137 | 24/05/2023 |  | WBSEDCL | 1.34 | 0 | 0 | 0
Total | [13 empty] | 69.74 | 20.34 | 29.16