## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF PAITKAPARA WATER SUPPLY SCHEME | SM/09910 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Paitkapara Tea Garden Water Supply Scheme TW No.-III under NMD-II,PHE.Dte, Alipurduar. |  |  | ORD/000913/2021-2022 | 404/NMD-II | 22/03/2022 | 21/04/2022 | SAIKAT SINHA | 2.39 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF PAITKAPARA WATER SUPPLY SCHEME | SM/09910 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling at 2nd site including laying distribution system , Rising main and providing FHTC for DAKSHIN PAITKAPARA PWSS under Alipurduar Division PHE DTE | Alipurduar RWS | Birpara Sub Division | ORD/000011/2022-2023 | 21/ALD | 01/04/2022 | 30/07/2022 | SOUVIK ROY PALADHI | 230.7 | 0 | 0 | 55
3 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF PAITKAPARA WATER SUPPLY SCHEME | SM/09910 | Augmentation | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of PAITKAPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar RWS | RWS Alipurduar - I Block,RWS Madarihat - Birpara Block | ORD/000296/2021-2022 | 1994/ALD | 27/12/2021 | 27/03/2022 | ANUP GUPTA | 20.99 | 0 | 0 | 80
4 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF PAITKAPARA WATER SUPPLY SCHEME | SM/09910 | Augmentation | Reparing of Pump House at 2nd TW site of PAITKAPARA PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000573/2024-2025 | 5387/ALD | 17/03/2025 | 16/05/2025 | DAS CONSTRUCTION | 0.79 | 0 | 0 | 0
5 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF PAITKAPARA WATER SUPPLY SCHEME | SM/09910 | Augmentation | Reparing of Pump House at HEADWORK site of PAITKAPARA PWSS Under Alipurduar Division PHE DTE. |  |  | ORD/000575/2024-2025 | 5389/ALD | 17/03/2025 | 16/05/2025 | DAS CONSTRUCTION | 0.95 | 0 | 0 | 0
Total | [13 empty] | 255.82 | 0 | 0