## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Alipurduar Division | Dheklapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10038 | New | Providing FHTC from existing distribution system as per specification for Dekhlapara PWSS. | Birpara A.E | Alipurduar Sub Division,Birpara Sub Division | ORD/000326/2023-2024 | 2423/ALD | 09/11/2023 | 08/01/2024 | SHYAMAL ROY | 7.21 | 0 | 0 | 0
2 | ALIPURDUAR | Madarihat | Alipurduar Division | Dheklapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10038 | New | CONS. FOR RESERVOIR (200 M3), RISING MAIN AND DISTRIBUTION LINE FOR DHEKLAPARA MAIN DIVISION CHA SUNDARAI WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION PHE DTE. | Birpara A.E | Alipurduar Sub Division | ORD/000030/2022-2023 | 284/ALD | 26/04/2022 | 23/09/2022 | SUBHAS CHANDRA ROY | 86.68 | 70.85 | 81.74 | 100
3 | ALIPURDUAR | Madarihat | Alipurduar Division | Dheklapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10038 | New | New service connection charges for Dheklapara T.G PWSS P/H no-I (Cha Sundari) |  |  | BILL/00489/2024-2025 | 325/24-25/PFMS | 02/12/2024 | 02/12/2024 | WBSEDCL | 5.04 | 0 | 0 | 0
4 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dheklapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10038 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Dheklapara TG Water Supply Scheme TW No.-I (Chha sundari) under Jal Jeevan Mission NMD-II,PHE.Dte, Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000589/2024-2025 | 59/NMD-II | 07/01/2025 | 07/08/2025 | M/S CHANDRANATH MUKHERJEE | 14.22 | 0 | 0 | 100
Total | [13 empty] | 113.15 | 70.85 | 62.62