## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Alipurduar Division | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10054 | New | Construction of boundary wall, pump house, tubewell, rising main for (Mouza- Lankapara TG, JL No. 30, Sheet No. 5, Plot No. 704) 327 units Cha Sundori Water Supply Scheme under Alipurduar Division PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000189/2023-2024 | 1280/ALD | 11/08/2023 | 05/08/2024 | ASHOK PRADHAN | 57.36 | 0 | 0 | 35
2 | ALIPURDUAR | Madarihat | Alipurduar Division | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10054 | New | Construction of boundary wall, pump house, tubewell, rising main and land development for (Mouza- Lankapara TG, JL No. 30, Sheet No. 7, Plot No. 920,921, 922 & 923 ) 375 units Cha Sundori Water Supply Scheme under Alipurduar Division PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000196/2023-2024 | 1486/ALD | 16/08/2023 | 14/12/2023 | SUBIR GHOSH | 55.7 | 0 | 0 | 0
3 | ALIPURDUAR | Madarihat | Alipurduar Division | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10054 | New | Sinking of one no. Big dia Tube Well (250 x 200 x 150 mm dia 270mtr) by Modified DTH - ODEX method of Cha-Sundori Project (JJM- SM/10054) within Lankapara Tea Garden Area Piped Water Supply Scheme, Madarihat-Birpara block of Birpara Sub-Division under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000345/2024-2025 | 3339/ALD | 20/09/2024 | 05/10/2024 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 32.35 | 0 | 0 | 51
4 | ALIPURDUAR | Madarihat | Alipurduar Division | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10054 | New | Laying of proposed Rising main (Length- 1085 mtr, 4817 mtr & 1320 mtr.) of Cha-Sundori Project (JJM- SM/10054) within Lankapara Tea Garden Area Piped Water Supply Scheme, Madarihat-Birpara block of Birpara Sub-Division under Alipurduar Division, PHE Dte.[As per new DPR guided by Planning Circle-II, PHE Dte.] | Birpara A.E | Birpara Sub Division | ORD/000267/2024-2025 | 3116/ALD | 30/08/2024 | 14/10/2024 | DILIP MAHATO (OPC) PRIVATE LIMITED | 36.54 | 0 | 0 | 28
5 | ALIPURDUAR | Madarihat | Alipurduar Division | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10054 | New | Making arrangement for pumping test with suitable pump and required column pipes etc. including all charges at 6 locations. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000209/2024-2025 | 1825/ALD | 14/06/2024 | 12/10/2024 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 15.96 | 0 | 0 | 30
6 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10054 | New | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Lankapara Water Supply Scheme TW No.-V under NMD-II,PHE Dte Alipurduar. |  |  | ORD/000823/2021-2022 | 202/NMD-II | 24/02/2022 | 26/03/2022 | M/S RATAN KUMAR DASGUPTA & CO. | 10.44 | 10.44 | 100 | 100
7 | ALIPURDUAR | Madarihat | Alipurduar Division | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10054 | New | Soil investigation work for Cha Sundori Project at 4 different places of Lankapara TG (3 nos GLR & 1 No OHR) within Alipurduar District under Alipurduar Division PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000489/2021-2022 | .2660/ALD | 21/02/2022 | 23/03/2022 | GLORY ENGINEERS SYNDICATE | 4.89 | 2.45 | 50 | 80
8 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10054 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Lankapara in Relation With Chaa Sundori Water Supply Scheme TWNo- I,II,III,IV under NMD-II,PHE.Dte,APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/001261/2023-2024 | 2988/NMD-II | 28/11/2023 | 28/12/2023 | SARKAR ELECTRIC | 59.29 | 0 | 0 | 58
9 | ALIPURDUAR | Madarihat | Alipurduar Division | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10054 | New | Hydro Geological investigation about water evaluation availability and quality parameter for both Ground and surface sources at Lankapara central Dooars Tea Estates within Alipurduar District |  |  | BILL/00215/2024-2025 | 164/24-25/PFMS | 12/08/2024 |  | IIT CONSULTATIVE PRACTICE | 9.74 | 0 | 0 | null
10 | ALIPURDUAR | Madarihat | Alipurduar Division | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10054 | New | Hydro Geological investigation about water evaluation availability and quality parameter for both Ground and surface sources at Lankapara central Dooars Tea Estates within Alipurduar District |  |  | BILL/00215/2024-2025 | 164/24-25/PFMS | 12/08/2024 |  | IIT CONSULTATIVE PRACTICE | 9.74 | 0 | 0 | null
11 | ALIPURDUAR | Madarihat | Alipurduar Division | Supply of Potable Drinking Water to Lankapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10054 | New | New Service Connection Charges for Lankapara TG PWSS PH NO-VII ( AT VES-4) Near Chha Sundari |  |  | BILL/00485/2024-2025 | 324/24-25/PFMS | 22/11/2024 |  | WBSEDCL | 16.11 | 0 | 0 | null
Total | [13 empty] | 308.12 | 12.88 | 4.18