## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/10170 | Augmentation | Providing House connection for KAMAKHYAGURI water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte.(PART-2) |  |  | ORD/000173/2020-2021 | 917/ALD | 16/10/2020 | 15/11/2020 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 4.98 | 4.9 | 98.4 | 57
2 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/10170 | Augmentation | New Laying of UPVC/DI Pipe Line, Providing FHTC & Other allied works at Uttar Kamakhyaguri PWSS Under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000211/2022-2023 | 1306/ALD | 22/08/2022 | 21/10/2022 | DILIP MAHATO | 28.04 | 21 | 74.86 | 57
3 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/10170 | Augmentation | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Uttar Kamakhyaguri Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000114/2022-2023 | 706/ALD | 08/06/2022 | 08/07/2022 | DEBAJYOTI SUTRADHAR | 4.95 | 4.95 | 100 | 57
4 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/10170 | Augmentation | Installation of additional new tube well by ODEX-165 method of drilling for Uttar Kamakhyaguri Water Supply Scheme under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000104/2022-2023 | 776/ALD | 20/06/2022 | 20/07/2022 | ANUP GUPTA | 6.99 | 5.44 | 77.8 | 57
5 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/10170 | Augmentation | Uttar Kamakhya guri, T/W no. V, Application no. 4002930579, Ref no. 402824641, |  |  | VCH/000699/2022-2023 | BP-27/22-23 | 15/07/2022 | 15/07/2022 | WBSEDCL | 0.87 | 0 | 0 | 0
6 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/10170 | Augmentation | Restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipeline of Uttar Kamakhyaguri WSS under Alipurduar Division, PHE Dte.(Part-A) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000167/2021-2022 | 1306/ALD | 05/10/2021 | 04/12/2021 | GOUTAM KUMAR DAS | 25.34 | 0 | 0 | 74
7 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/10170 | Augmentation | Restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipeline and Providing House Connection of Uttar Kamakhyaguri Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000226/2021-2022 | 1574/ALD | 22/11/2021 | 21/01/2022 | M/S PALIT ENTERPRISE | 48.63 | 29.64 | 60.96 | 78
8 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/10170 | Augmentation | Restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipeline of Uttar Kamakhyaguri WSS under Alipurduar Division, PHE Dte.(Part-A) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000180/2021-2022 | 1307/ALD | 05/10/2021 | 04/12/2021 | TAPASH DAS | 25.34 | 0 | 0 | 76
9 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/10170 | Augmentation | Construction of Pump House ,Boundary Wall and laying distribution system for Uttar Kamkhyaguri Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000424/2021-2022 | 2608/ALD | 17/02/2022 | 18/05/2022 | GOUTAM KUMAR DAS | 90.8 | 77.36 | 85.19 | 74
10 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/10170 | Augmentation | Construction of Pump House ,Boundary Wall, and Tube well Boring by Reverse Rotary method of drilling including Rising main for UTTAR KAMAKHYAGURI Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000426/2021-2022 | 2610/ALD | 17/02/2022 | 18/05/2022 | ANUP GUPTA | 23.99 | 0 | 0 | 0
11 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/10170 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Uttar Kamakhyaguri Water Supply Scheme TW No.- V under NMD-II, PHE. Dte, Alipurduar. |  |  | ORD/000915/2021-2022 | 0406/NMD-II | 22/03/2022 | 21/04/2022 | GURUKRIPA ENTERPRISE | 2.37 | 0 | 0 | 0
12 | ALIPURDUAR |  | Northern Mechanical Division II | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/10170 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Uttar Kamakhyaguri water supply scheme TW No. V under NMD-II, PHE Dte. Alipurduar. |  |  | ORD/000009/2022-2023 | 557/NMD-II | 26/04/2022 | 26/05/2022 | BLUE PINE | 7.85 | 0 | 0 | 0
13 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/10170 | Augmentation | Providing House connection for KAMAKHYAGURI water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-III | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000209/2020-2021 | 1163/ALD | 15/12/2020 | 13/02/2021 | TAPASH DAS | 19.94 | 7.66 | 38.4 | 77
14 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/10170 | Augmentation | Providing FHTC of Uttar Kamakhyaguri WSS under Alipurduar Division, PHE Dte. (Part-4) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000162/2021-2022 | 1304/ALD | 05/10/2021 | 04/12/2021 | DULAL MAJUMDER | 34.38 | 32.66 | 95 | 76
15 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/10170 | Augmentation | Construction of 400cum OHR for Augmentation of Uttar Kamakhyaguri Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000412/2021-2022 | 2580/ALD | 17/02/2022 | 16/08/2022 | DILIP MAHATO | 77.31 | 58.71 | 75.94 | 74
16 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/10170 | Augmentation | Land development and laying of UPVC pipeline at additional TW Site of Uttar Kamakhyaguri PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000203/2023-2024 | 1556/ALD | 23/08/2023 | 22/10/2023 | SREE MAA CONSTRUCTION | 8.6 | 8.54 | 99.27 | 100
17 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/10170 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2022-2023 | 715/ALD | 13/06/2022 | 13/06/2022 | Resource Division | 71.41 | 0 | 0 | 0
18 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/10170 | Augmentation | Laying of new UPVC/DI pipeline for filling of gap in the distribution system and laying of delivery line connection, providing FHTC, land development cons. Of surface drain, pathway and other allied work in connection with the Uttar Kamakhyaguri PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000347/2023-2024 | 2564/ALD | 29/11/2023 | 22/05/2025 | DEBAJYOTI SUTRADHAR | 46.9 | 5.15 | 10.97 | 65
19 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/10170 | Augmentation | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Head Quarter, Alipurduar Division, P.H.E. Dte.(from 01.01.2023 to 31.12.2023) | HQ-A.E |  | ORD/000414/2022-2023 | 2729/ALD | 30/12/2022 | 30/12/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 4.8 | 4.48 | 93.3 | 100
20 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF UTTAR KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/10170 | Augmentation | Laying of pipeline at PASCHIM NARATHALI by extension of pipeline from Uttar Kamakhyaguri PWSS under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000440/2021-2022 | 2746/ALD | 24/02/2022 | 10/12/2024 | AKANSHA COMMERCIAL PRIVATE LTD. | 93.92 | 23.12 | 24.62 | 100
Total | [13 empty] | 627.41 | 283.59 | 45.2