## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Alipurduar Division | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10173 | New | Repair of Pump House with additional Toilet at 2nd Pump House site of Madarihat WSS under Alipuduar Division, P.H.E. | Birpara A.E | Alipurduar Sub Division | ORD/000131/2020-2021 | 877/ALD | 14/10/2020 | 28/11/2020 | DILIP MAHATO | 2.13 | 0 | 0 | 91
2 | ALIPURDUAR | Madarihat | Alipurduar Division | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10173 | New | Providing House connection for BIRPARA PWSS, MADARIHAT-BIRPARA Block under Alipuduar Division, P.H.E. Dte |  |  | ORD/000370/2020-2021 | 1766/ALD | 19/02/2021 | 20/04/2021 | BILTU DAS | 39.46 | 33.54 | 85 | 83
3 | ALIPURDUAR | Madarihat | Alipurduar Division | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10173 | New | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of DIMA TG Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar RWS,HQ-A.E | RWS Alipurduar - I Block,RWS Kalchini Block,RWS Kumargram Block | ORD/000293/2021-2022 | 1991/ALD | 27/12/2021 | 02/09/2026 | GOBINDA BAGCHI | 20.87 | 0 | 0 | 90
4 | ALIPURDUAR | Madarihat | Alipurduar Division | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10173 | New | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000495/2021-2022 | 939/ALD | 08/09/2021 | 08/10/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 260 | 21.67 | 0
5 | ALIPURDUAR | Madarihat | Alipurduar Division | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10173 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna for AWC and school under Madarihat WSS under Alipurduar Division, PHE Dte. | Birpara A.E |  | ORD/000266/2021-2022 | 1831/ALD | 10/12/2021 | 09/01/2022 | RATAN DUTTA | 5.04 | 0.97 | 19.25 | 59
6 | ALIPURDUAR | Madarihat | Alipurduar Division | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10173 | New | Providing House connection for MADARIHAT PWSS under Alipuduar Division, P.H.E. Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000386/2020-2021 | 1806/ALD | 22/02/2021 | 23/04/2021 | DILIP MAHATO | 20.13 | 2.01 | 10 | 90
7 | ALIPURDUAR | Madarihat | Alipurduar Division | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10173 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna for Govt office and other Institution under Madarihat WSS under Alipurduar Division, PHE Dte. | Birpara A.E |  | ORD/000265/2021-2022 | 1830/ALD | 10/12/2021 | 09/01/2022 | BHAGWATI BHUJEL | 5.04 | 5.04 | 100 | 61
8 | ALIPURDUAR | Madarihat | Alipurduar Division | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10173 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at 2nd & 3rd site including laying distribution system , Rising main and providing FHTC for MADARIHAT TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE | Birpara A.E |  | ORD/000013/2022-2023 | 23/ALD | 01/04/2022 | 30/07/2022 | DILIP MAHATO | 213.9 | 154.11 | 72.05 | 84
9 | ALIPURDUAR | Madarihat | Alipurduar Division | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10173 | New | Construction of 350cum OHR for Madarihat TG Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E |  | ORD/000417/2021-2022 | 2586/ALD | 17/02/2022 | 16/08/2022 | DILIP MAHATO | 71.4 | 51.24 | 71.76 | 90
10 | ALIPURDUAR | Madarihat | Alipurduar Division | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10173 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at H/W site including laying distribution system and providing FHTC for MADARIHAT TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE | Birpara A.E | Alipurduar Sub Division,RWS Falakata Block | ORD/000008/2022-2023 | 18/ALD | 01/04/2022 | 30/07/2022 | DILIP MAHATO | 216.89 | 197.43 | 91.03 | 100
11 | ALIPURDUAR | Madarihat | Alipurduar Division | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10173 | New | Material Requisition To Resource Division |  |  | RTOR000009/2022-2023 | 491/ALD | 18/05/2022 | 18/05/2022 | Resource Division | 149.46 | 0 | 0 | 0
12 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10173 | New | Quotation for new service connection at Madarihat TG P/H No-III |  |  | VCH/001438/2022-2023 |  | 02/11/2022 | 02/11/2022 | WBSEDCL | 1.34 | 0 | 0 | 0
13 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10173 | New | Quotation for new service connection at MADARIHAT T.G, P/H no. I, Application no.4002997527 |  |  | VCH/001460/2022-2023 | BP-82/22-23 | 04/11/2022 | 04/11/2022 | WBSEDCL | 1.34 | 0 | 0 | 0
14 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10173 | New | Quotation for new service connection at Madarihat TG P/H No-I |  |  | VCH/001439/2022-2023 |  | 02/11/2022 | 02/11/2022 | WBSEDCL | 1.34 | 0 | 0 | 0
15 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10173 | New | Quotation for new service connection at Madarihat TG P/H No-II |  |  | VCH/001440/2022-2023 |  | 02/11/2022 | 02/11/2022 | WBSEDCL | 1.34 | 0 | 0 | 0
16 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10173 | New | Quotation for new service connection at MADARIHAT T.G, P/H no. II, Application no.4002997569 |  |  | VCH/001459/2022-2023 | BP-81/22-23 | 04/11/2022 | 04/11/2022 | WBSEDCL | 1.34 | 0 | 0 | 0
17 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10173 | New | Quotation for new service connection at MADARIHAT T.G, P/H no. III, Application no.4002997498 |  |  | VCH/001461/2022-2023 | BP-83/22-23 | 04/11/2022 | 04/11/2022 | WBSEDCL | 1.34 | 0 | 0 | 0
18 | ALIPURDUAR | Madarihat | Alipurduar Division | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10173 | New | Replacement of damaged pipeline in Madarihat Bazar Area PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000043/2023-2024 | 389/ALD | 19/05/2023 | 15/11/2023 | KAMALESH ROY | 5.46 | 0 | 0 | 95
19 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10173 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector of Madarihat TG PWSS, TW no .III in the district of Alipurduar under Northern Mechanical Division-II, PHE Dte | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000795/2022-2023 | 299/NMD-II | 18/02/2023 | 20/03/2023 | MUSTAFI CONCERN | 10.72 | 10.72 | 100 | 90
20 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10173 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector of Madarihat TG PWSS, TW no .I in the district of Alipurduar under Northern Mechanical Division-II, PHE Dte | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000794/2022-2023 | 291/NMD-II | 17/02/2023 | 19/03/2023 | SUNLIT | 10.73 | 10.73 | 100 | 80
21 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10173 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector of Madarihat TG PWSS, TW no .II in the district of Alipurduar under Northern Mechanical Division-II, PHE Dte | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000843/2022-2023 | 585/NMD-II | 18/03/2023 | 17/04/2023 | M/S MATRI CONSTRUCTION | 10.82 | 10.17 | 94.05 | 100
22 | ALIPURDUAR | Madarihat | Alipurduar Division | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10173 | New | Material Requisition To Resource Division |  |  | RTOR000113/2023-2024 | 137/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 14.03 | 0 | 0 | 0
Total | [13 empty] | 2004.14 | 735.96 | 36.72