## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME | SM/10174 | New | Supply of CIPE Special & CI Jeffy Coupling for Dakshin Paitkapara Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000107/2022-2023 | 699/ALD | 08/06/2022 | 08/07/2022 | HARIDAS GHOSH | 4.92 | 0 | 0 | 84
2 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME | SM/10174 | New | Quotation for new service connection at Dakshin Patkapara, P/H no.II, Application no.403007835 |  |  | VCH/001464/2022-2023 | BP-86/22-23 | 11/11/2022 | 11/11/2022 | WBSEDCL | 1.01 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME | SM/10174 | New | Quotation for new service connection for DAKSHIN PATKAPARA. Tube well no. I, Application no. 4003007857 |  |  | VCH/001450/2022-2023 |  | 07/11/2022 | 07/11/2022 | WBSEDCL | 1.01 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME | SM/10174 | New | Quotation for new service connection for DAKSHIN PATKAPARA. Tube well no. II, Application no. 4003007835 |  |  | VCH/001449/2022-2023 |  | 07/11/2022 | 07/11/2022 | WBSEDCL | 1.01 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME | SM/10174 | New | Quotation for new service connection at Dakshin Patkapara, P/H no.I, Application no.4003007857 |  |  | VCH/001463/2022-2023 | BP-85/22-23 | 11/11/2022 | 11/11/2022 | WBSEDCL | 1.01 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME | SM/10174 | New | Construction of 300cum OHR for Dakshin Paitkapara Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000416/2021-2022 | 2584/ALD | 17/02/2022 | 16/08/2022 | Z STAR COMMOTRADE PVT LTD. | 63.78 | 0 | 0 | 83
7 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME | SM/10174 | New | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000495/2021-2022 | 939/ALD | 08/09/2021 | 08/10/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 0 | 0 | 0
8 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME | SM/10174 | New | Material Requisition To Resource Division |  |  | RTOR000002/2022-2023 | 394/ALD | 11/05/2022 | 11/05/2022 | Resource Division | 11.54 | 0 | 0 | 0
9 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME | SM/10174 | New | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling at H/W site including laying distribution system and providing FHTC for DAKSHIN PAITKAPARA PWSS Under Alipurduar Division PHE DTE | Alipurduar RWS,Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000006/2022-2023 | 16/ALD | 01/04/2022 | 27/11/2022 | HARIDAS GHOSH | 230.68 | 0 | 0 | 86
10 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME | SM/10174 | New | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling at 2nd site including laying distribution system , Rising main and providing FHTC for DAKSHIN PAITKAPARA PWSS under Alipurduar Division PHE DTE | Alipurduar RWS | Birpara Sub Division | ORD/000011/2022-2023 | 21/ALD | 01/04/2022 | 30/07/2022 | SOUVIK ROY PALADHI | 230.7 | 0 | 0 | 55
11 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME | SM/10174 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DAKSHIN PATKAPARA AREA PWSS, TW no I (H/W SITE) in the district of ALIPURDUAR under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000840/2022-2023 | 0568/NMD-II | 17/03/2023 | 01/12/2024 | TALUKDAR ENTERPRISE | 9.88 | 0 | 0 | 100
12 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME | SM/10174 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector of Dakshin Paitkapara PWSS, TW no .II in the district of Alipurduar under Northern Mechanical Division-II, PHE Dte | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000850/2022-2023 | 625/NMD-II | 21/03/2023 | 20/04/2023 | SARKAR ELECTRIC | 9.93 | 0 | 0 | 100
13 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME | SM/10174 | New | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of PAITKAPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar RWS | RWS Alipurduar - I Block,RWS Madarihat - Birpara Block | ORD/000296/2021-2022 | 1994/ALD | 27/12/2021 | 27/03/2022 | ANUP GUPTA | 20.99 | 0 | 0 | 80
14 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME | SM/10174 | New | Construction of Boundary Wall and pathway for Dakshin Paitkapara PWSS under Alipurduar Division PHE DTE. | Alipurduar RWS,Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000237/2022-2023 | 1329/ALD | 24/08/2022 | 23/07/2025 | M/S BASU CONSTRUCTION AND CO | 36.21 | 0 | 0 | 82
15 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME | SM/10174 | New | Cons. Of balance portion of pump house, boundary wall, rising main, laying of DI and HDPE pipeline for 3rd site of Dakshin Paitkapara PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division,RWS Madarihat - Birpara Block | ORD/000241/2023-2024 | 1787/ALD | 29/08/2023 | 27/12/2023 | ANUP GUPTA | 22.82 | 0 | 0 | 40
Total | [13 empty] | 1845.47 | 0 | 0