## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Alipurduar Division | JAYBIRPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10177 | New | Laying of Distribution Line (HDPE and DI) for retrofitting of FHTC for BIRPARA WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000360/2020-2021 | 1754/ALD | 19/02/2021 | 05/04/2021 | BILTU DAS | 47.98 | 0 | 0 | 61
2 | ALIPURDUAR | Madarihat | Alipurduar Division | JAYBIRPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10177 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling including providing FHTC and Rising main for JAY BIRPARA TG AREA PWSS under Alipurduar Division PHE DTE. | Birpara A.E | Alipurduar Sub Division | ORD/000487/2021-2022 | 2911/ALD | 08/03/2022 | 06/07/2022 | ALOK ENTERPRISE | 156.25 | 64.37 | 41.2 | 50
3 | ALIPURDUAR | Madarihat | Alipurduar Division | JAYBIRPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10177 | New | Construction of OHR 200cum for Jay Birpara TG Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000422/2021-2022 | 2601/ALD | 17/02/2022 | 16/08/2022 | SUBHAS CHANDRA ROY | 55.36 | 46.9 | 84.71 | 80
4 | ALIPURDUAR | Madarihat | Alipurduar Division | JAYBIRPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10177 | New | Carrying of different dia AC pipes from Alipurduar Stackyard and withdrawing CI pipes at Alipurduar Sadar Sub-Division under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000094/2022-2023 | 458/ALD | 13/05/2022 | 12/06/2022 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.99 | 0 | 0 | 58
5 | ALIPURDUAR | Madarihat | Alipurduar Division | JAYBIRPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10177 | New | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000495/2021-2022 | 939/ALD | 08/09/2021 | 08/10/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 100 | 8.33 | 0
6 | ALIPURDUAR | Madarihat | Alipurduar Division | JAYBIRPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10177 | New | Material Requisition To Resource Division |  |  | RTOR000028/2023-2024 | 1273/ALD | 11/08/2023 | 11/08/2023 | Resource Division | 20.82 | 0 | 0 | 0
7 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | JAYBIRPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10177 | New | QUOTATION FOR NEW SERVICE CONNECTION AT JAYBIRPARA TG TW NO-I |  |  | BILL/00071/2023-2024 | BP-2023-24-64 | 13/05/2023 | 13/05/2023 | WBSEDCL | 1.46 | 0 | 0 | 0
8 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | JAYBIRPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10177 | New | QUOTATION FOR NEW SERVICE CONNECTION AT JAYBIRPARA TG TW NO-II |  |  | BILL/00070/2023-2024 | BP-2023-24-65 | 13/05/2023 | 13/05/2023 | WBSEDCL | 1.46 | 0 | 0 | 0
9 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | JAYBIRPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10177 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for JAY BIRPARA TG water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte.Alipurduar | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000825/2023-2024 | 2398/NMD-II | 09/08/2023 | 01/04/2025 | GEETA CONSTRUCTION | 21.71 | 0 | 0 | 65
10 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | JAYBIRPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10177 | New | Additional Quotation for JAYBIRPARA PH NO-2 against previous Application ID-4003127162 in the dist. of Alipurduar under NMD-II |  |  | BILL/00279/2025-2026 |  | 05/05/2025 | 05/05/2025 | WBSEDCL | 4.04 | 0 | 0 | 0
Total | [13 empty] | 1510.08 | 211.26 | 13.99