## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10178 | New | Entry of data of Functional Household Tape Connection (FHTC under JJM) of PWSS in website under Alipurduar Division, PHE Dte. (Part-B) | HQ-A.E |  | ORD/000584/2021-2022 | 1968/ALD | 24/12/2021 | 24/03/2022 | TAPASH DAS | 0.96 | 0.96 | 100 | 78
2 | ALIPURDUAR | Madarihat | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10178 | New | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000495/2021-2022 | 939/ALD | 08/09/2021 | 08/10/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 200 | 16.67 | 0
3 | ALIPURDUAR | Madarihat | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10178 | New | SUPPLY, INSTALLATION, COMMISSIONING AND TRIAL OPERATION OF ELECTRO MECHANICAL COMPONENTS OF RIGBORE T/W (1 NOS) FOR GOPALPUR TG ALONG WITH CONS. OF 1 NO. P/H OF SIZE 3.00M X 3.60M |  |  | ORD/000336/2020-2021 | 1486/ALD | 27/01/2021 | 28/03/2021 | DILIP MAHATO | 11 | 1.94 | 17.6 | 78
4 | ALIPURDUAR | Madarihat | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10178 | New | Entry of data of Functional Household Tape Connection (FHTC under JJM) of PWSS in website under Alipurduar Division, PHE Dte. (Part-C) | HQ-A.E |  | ORD/000591/2021-2022 | 361/ALD | 08/06/2021 | 06/09/2021 | TAPASH DAS | 0.96 | 0.96 | 100 | 77
5 | ALIPURDUAR | Madarihat | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10178 | New | Entry of data of Functional Household Tape Connection (FHTC under JJM) of PWSS in website under Alipurduar Division, PHE Dte. (Part-C) | HQ-A.E |  | ORD/000588/2021-2022 | 745/ALD | 11/08/2021 | 09/11/2021 | HARIDAS GHOSH | 0.96 | 0.96 | 100 | 74
6 | ALIPURDUAR | Madarihat | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10178 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at H/W site including laying distribution system and providing FHTC fo GOPALPUR TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | Birpara A.E | Alipurduar Sub Division | ORD/000016/2022-2023 | 26/ALD | 01/04/2022 | 11/11/2025 | ASHIT KUMAR SINGHA | 136.46 | 60 | 43.97 | 95
7 | ALIPURDUAR | Madarihat | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10178 | New | Carrying of different dia AC pipes from Alipurduar Stackyard and withdrawing CI pipes at Alipurduar Sadar Sub-Division under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000094/2022-2023 | 458/ALD | 13/05/2022 | 12/06/2022 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.99 | 0 | 0 | 58
8 | ALIPURDUAR | Madarihat | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10178 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at 2nd site including laying distribution system , Rising main and providing FHTC for GOPALPUR TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | Birpara A.E | Alipurduar Sub Division | ORD/000017/2022-2023 | 27/ALD | 01/04/2022 | 19/07/2024 | M/S DUTTA AND CO | 138.71 | 102.09 | 73.6 | 90
9 | ALIPURDUAR | Madarihat | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10178 | New | Construction of 250cum OHR for Gopalpur Tea Garden Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000423/2021-2022 | 2602/ALD | 17/02/2022 | 16/08/2022 | SASANKA ROY | 57.59 | 57.96 | 100.65 | 72
10 | ALIPURDUAR | Madarihat | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10178 | New | Material Requisition To Resource Division |  |  | RTOR000014/2022-2023 | 825/ALD | 28/06/2022 | 28/06/2022 | Resource Division | 26.08 | 0 | 0 | 0
11 | ALIPURDUAR | Madarihat | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10178 | New | Material Requisition To Resource Division |  |  | RTOR000017/2022-2023 | 828/ALD | 28/06/2022 | 28/06/2022 | Resource Division | 34.42 | 0 | 0 | 0
12 | ALIPURDUAR | Madarihat | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10178 | New | Construction of Tubewell by ODEX-165 method of drilling, construction of of pump house and boundary wall for Gopalpur PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000033/2023-2024 | 364/ALD | 18/05/2023 | 01/07/2025 | SWAPAN KUMAR SAHA | 24.47 | 15.02 | 61.39 | 100
13 | ALIPURDUAR | Madarihat | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10178 | New | Providing FHTC from existing distribution system as per specification for Gopalpur TG PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000257/2023-2024 | 1875/ALD | 07/09/2023 | 03/07/2024 | NARENDRA BHADANI. | 7.03 | 6.15 | 87.53 | 90
14 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10178 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Gopalpur TG water supply scheme, TW no II in the district of Alipurduar under Northern Mechanical Division-II PHE Dte APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000862/2022-2023 | 659/NMD-II | 24/03/2023 | 23/04/2023 | M/S ABHISEK ENGINEERING CONCERN | 9.91 | 9.91 | 100 | 90
15 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10178 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Gopalpur TG water supply scheme, TW no I in the district of Alipurduar under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000857/2022-2023 | 651/NMD-II | 24/03/2023 | 23/04/2023 | RMD TRADING | 9.91 | 9.77 | 98.51 | 100
16 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10178 | New | Quotation for new service connection at gopalpur tg TW No- I |  |  | BILL/00043/2022-2023 | BP-128/22-23 | 13/01/2023 | 13/01/2023 | WBSEDCL | 1.23 | 0 | 0 | 0
17 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10178 | New | Quotation for new service connection at Gopalpur TG TW No- II |  |  | BILL/00044/2022-2023 | BP-131/22-23 | 13/01/2023 | 13/01/2023 | WBSEDCL | 1.23 | 0 | 0 | 0
18 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10178 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for GOPALPUR TG Water Supply Scheme TW No.-III under NMD-II,PHE.Dte, Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000505/2024-2025 | 2638/NMD-II | 06/12/2024 | 02/06/2025 | M/S P.P ELECTRICALS | 10.74 | 0 | 0 | 100
19 | ALIPURDUAR | Madarihat | Alipurduar Division | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10178 | New | Material Requisition To Resource Division |  |  | RTOR000115/2023-2024 | 139/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 9.16 | 0 | 0 | 0
20 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10178 | New | New Service Connection Charges for Gopalpur TG |  |  | BILL/01412/2024-2025 | BP-405/24-25 | 30/10/2024 | 30/10/2024 | WBSEDCL | 5.59 | 0 | 0 | 0
Total | [13 empty] | 1687.41 | 465.73 | 27.6