## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Alipurduar Division | GANGUTIA TEA GARDEN AREA PIPED WATER SUPPLY SHEME | SM/10180 | New | Construction of OHR 200cum for Gangutia Water Supply Scheme under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000420/2021-2022 | 2599/ALD | 17/02/2022 | 16/08/2022 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 55.36 | 11.23 | 20.28 | 68
2 | ALIPURDUAR | Kalchini | Alipurduar Division | GANGUTIA TEA GARDEN AREA PIPED WATER SUPPLY SHEME | SM/10180 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling including providing FHTC, laying distribution system and Rising main for Gangutia Piped Water Supply Scheme Under Alipurduar Division PHE DTE | HQ-A.E | RWS Kalchini Block | ORD/000003/2022-2023 | 13/ALD | 01/04/2022 | 30/07/2022 | SHREE RANISATI ENTERPRISE | 193.63 | 124.7 | 64.4 | 67
3 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | GANGUTIA TEA GARDEN AREA PIPED WATER SUPPLY SHEME | SM/10180 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for GANGUTIA TG water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte.Alipurduar | Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/000841/2022-2023 | 571/NMD-II | 17/03/2023 | 16/04/2023 | SUMON ELECTRICAL | 21.73 | 17.9 | 82.36 | 0
4 | ALIPURDUAR | Kalchini | Alipurduar Division | GANGUTIA TEA GARDEN AREA PIPED WATER SUPPLY SHEME | SM/10180 | New | Carrying of different dia AC pipes from Alipurduar Stackyard and withdrawing CI pipes at Alipurduar Sadar Sub-Division under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000094/2022-2023 | 458/ALD | 13/05/2022 | 12/06/2022 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.99 | 0 | 0 | 58.14
5 | ALIPURDUAR | Kalchini | Alipurduar Division | GANGUTIA TEA GARDEN AREA PIPED WATER SUPPLY SHEME | SM/10180 | New | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000495/2021-2022 | 939/ALD | 08/09/2021 | 08/10/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 0 | 0 | 0
6 | ALIPURDUAR | Kalchini | Alipurduar Division | GANGUTIA TEA GARDEN AREA PIPED WATER SUPPLY SHEME | SM/10180 | New | Supply of CIPE Special & CI Jeffy Coupling for Gangutia Water Supply Scheme under Alipurduar Division P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000115/2022-2023 | 707/ALD | 08/06/2022 | 08/07/2022 | DAS CONSTRUCTION | 4.89 | 4.89 | 100 | 68
7 | ALIPURDUAR | Kalchini | Alipurduar Division | GANGUTIA TEA GARDEN AREA PIPED WATER SUPPLY SHEME | SM/10180 | New | Material Requisition To Resource Division |  |  | RTOR000030/2022-2023 | 1704/ALD | 21/09/2022 |  | Resource Division | 61.51 | 0 | 0 | 0
8 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | GANGUTIA TEA GARDEN AREA PIPED WATER SUPPLY SHEME | SM/10180 | New | Quotation for new service connection at Gangutia TG TW No I |  |  | BILL/00035/2022-2023 | BP-121/22-23 | 09/01/2023 |  | WBSEDCL | 1.34 | 0 | 0 | 0
9 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | GANGUTIA TEA GARDEN AREA PIPED WATER SUPPLY SHEME | SM/10180 | New | New Service Connection Charges for Gangutia TG PWSS P/HNO-II |  |  | BILL/02637/2023-2024 | BP-2023-24-600 | 15/02/2024 |  | WBSEDCL | 6.02 | 0 | 0 | 0
10 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | GANGUTIA TEA GARDEN AREA PIPED WATER SUPPLY SHEME | SM/10180 | New | New Service Connection Charges for Gangutia TG PWSS P/HNO-II |  |  | BILL/02637/2023-2024 | BP-2023-24-600 | 15/02/2024 |  | WBSEDCL | 6.02 | 0 | 0 | 0
Total | [13 empty] | 1551.48 | 158.71 | 10.23