## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | Laying Distribution line of UPVC & Di Pipe , with providing FHTC Connection for the Salkumarhat Water Supply Scheme Under Alipurduar Division PHE DTE (PART-A) | Alipurduar RWS | Birpara Sub Division | ORD/000131/2021-2022 | 1242/ALD | 27/09/2021 | 26/11/2021 | KAMALESH ROY | 25.25 | 4.65 | 18.43 | 9
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Salkumarhat PWSS, Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000479/2021-2022 | 2898/ALD | 08/03/2022 | 07/05/2022 | DILIP MAHATO | 48.52 | 0 | 0 | 54
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at 3rd site for SALKUMARHAT PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS | Birpara Sub Division | ORD/000066/2022-2023 | 338/ALD | 02/05/2022 | 31/07/2022 | SUBRATA DAS | 24.16 | 22.94 | 94.96 | 8
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at 4th site for SALKUMARHAT PWSS Under Alipurduar Division PHE DTE | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000067/2022-2023 | 339/ALD | 02/05/2022 | 31/07/2022 | SHYAMAL ROY | 24.17 | 9.7 | 40.13 | 10
5 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Salkumarhat Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000728/2023-2024 | 2299/NMD-II | 31/07/2023 | 30/08/2023 | MADHAB SAHA | 20.89 | 0 | 0 | 80
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | Repairing & renovation of Pump House, Pathway, Boundary wall (2nd site) & laying DI Pipe line at Salkumarhat WSS under Alipurduar Division PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000099/2021-2022 | 898/ALD | 03/09/2021 | 18/10/2021 | TAPASH DAS | 4.82 | 0 | 0 | 62
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | Cons. Of Rising line, pathway, surface drain, laying of DI and UPVC pipeline and restoration of FHTC at Salkumarhat PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division,JUNIOR ENGINEER | ORD/000222/2023-2024 | 1582/ALD | 24/08/2023 | 22/11/2023 | TAPASH DAS | 18.46 | 0 | 0 | 5
8 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | Quotation for new service connection at SALKUMAR HAT, P/H no. III, Application no. 4002994687 |  |  | VCH/001470/2022-2023 | BP-93/22-23 | 22/11/2022 |  | WBSEDCL | 1.42 | 0 | 0 | 0
9 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | Quotation for new service connection at Salkumarhat TW No-III, Application No- 4002994687 |  |  | BILL/00001/2022-2023 | null | 21/11/2022 |  | WBSEDCL | 1.42 | 0 | 0 | 0
10 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR SALKUMARHAT P/H NO.IV |  |  | BILL/00680/2023-2024 | BP-2023-24-194 | 22/06/2023 |  | WBSEDCL | 1.48 | 0 | 0 | 0
11 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF SALKUMARHAT PIPED WATER SUPPLY SCHEME | SM/10316 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR MUNSHIPARA P/H NO.III |  |  | BILL/00681/2023-2024 | null | 06/06/2023 |  | WBSEDCL | 1 | 0 | 0 | 0
Total | [13 empty] | 171.59 | 37.3 | 21.73